SECTION I:   PROJECT DESCRIPTION

- BACKGROUND:

POWERGRID, the Central Transmission Utility (CTU) of the country, is engaged in power transmission with the mandate for planning, co-ordination, supervision and control over complete inter-State transmission system. As on March’10 POWERGRID has established about 77,000 ckt kms of transmission lines at 765 kV, 400 kV, 220 kV & 132 kV EHVAC & +500 kV HVDC levels and 131 sub-stations with transformation capacity of about 89,000 MVA. This transmission network, spread over length and breadth of the country, is consistently maintained at an availability of over 99.7% through deployment of state-of-the-art Operation & Maintenance techniques at par with global standards. About 45% of total power generated in the country is wheeled through this transmission network.

POWERGRID has been contributing significantly towards development of Indian power sector by undertaking coordinated development of power transmission network along with effective and transparent operation of regional grids and through continuous innovations in technical & managerial fields.

To meet future demand, Ministry of Power, Government of India is envisaging addition of about 78,700 MW during XI Plan (2007-12). Investment programme of POWERGRID for XI Plan has been estimated based on envisaged generation capacity addition in Central sector and other generation projects including Ultra Mega Power Projects (UMPPs) for which transmission system is required to be built by POWERGRID. Based on this, an investment of about Rs. 55,000 Crore (USD 12 billion) is envisaged to be made by POWERGRID in XI Plan. To meet the funding requirement, POWERGRID is raising loans from Multilateral funding agencies including The World Bank, The ADB and domestic market. During XI plan, POWERGRID has tied-up about USD 2.0 billion loans from The World Bank and about USD 0.6 billion loans from the ADB for implementation of various projects of POWERGRID during XI and XII plan. The sub project is proposed to be funded by ADB as an additional project under Loan 2510 – IND (Tranche 2), National Powergrid Development Investment Programme in order to effectively utilize the entire loan amount of US$ 200 million.

1.1	BENEFITS OF THE PROJECT:

The main benefit of the project will be meeting the long term power requirement of DNH with reliability and security. Additionally, the project is likely to generate direct and indirect employment opportunities, promote industrial growth and stimulate overall development of the area. The basic infrastructure around the proposed substation will also improve substantially. POWERGRID, as a responsible corporate entity, always undertakes community development works around the location of its substations.

1.2   PROJECT DESCRIPTION

Objective

The objective of this system is to cater to long term power transfer requirement           of UT DNH.

Project Highlights

| a) | Project Name | : | Loop-in Loop-out (LILO) of Navsari - Boisar 400kV D/C line at proposed Kala Substation |
| --- | --- | --- | --- |
| b) | Location | : | DNH |
| c) | Beneficiary States | : | DNH, Gujarat, Maharashtra. |
| d) | Project Cost | : | 183.14 Crores (at 4th Quarter 2009 price level) |

Scope of work

- Transmission lines

Loop-in Loop-out (LILO) of Navsari - Boisar 400 kV D/C line at proposed Kala Substation – 7.5 Kms

- Substations

400/220kV GIS Substation at Kala in UT of DNH

A power map showing the transmission grid of Western Region highlighting the above scope of works is placed as Exhibit-1.

SECTION II: BASE LINE DATA

2.0  	The project is to be located in Union Territory of Dadra & Nagar Haveli in India. The basic details of the area under project are given below:

2.1     DADRA & NAGAR HAVELI (DNH):

Dadra & Nagar Haveli became a part of India in year 1961. It is located on the west Coast of India between 20° N and 20°25’ N latitude and between 72°50’E and 73°15’ E longitudes, comprising of 72 villages under two enclaves viz ‘Dadra’ and ‘Nagar Haveli’. The total geographic area of DNH is 491.0 sq. kms. It is surrounded on the west, north and east by Valsad district of Gujarat, on the south by Thane district and on the south-east by Nashik district of Maharastra. The location map of the subproject  area is shown as Map- 1.

Topographically, DNH is undulating and rolling. In the north east part the region is surrounded by the Sahyadri Ranges giving it a hilly terrain character and the central and remaining area is plain. The region lies in the watershed of the Daman Ganga river, which traverses through the region before meeting the Arabian Sea at Daman. The river is joined by three tributaries i.e. Piparika, Golak and Sakartod.

Land use Pattern

| Land use | Area in ‘000 ha | Percentage |
| --- | --- | --- |
| Total Geographical area | 49 |  |
| Reporting Area for land utilization | 49 | 100.00 |
| Forests | 20 | 40.82 |
| Not available for cultivation | 4 | 8.16 |
| Permanent Pasture & Grazing land | 1 | 2.04 |
| Land under misc. tree crops & groves | 0 | 0.00 |
| Culturable waste land | 0 | 0.00 |
| Fallow land & other than current fallows | 1 | 2.04 |
| Current fallows | 1 | 2.04 |
| Net area Sown | 22 | 44.90 |

(Ref: Land use statistics, Ministry of Agriculture, GOI, 2006)

Population: Details of Population as per 2001 census are as follows:

| Total Population | 220451 |
| --- | --- |
| Male Population | 121731 |
| Female Population | 98720 |
| Rural Population | 169995 |
| Urban Population | 50456 |
| Density (per Sq. Km) | 449 |
| Literacy Rate (%) | 60.03 |

Climate: The climate of the region is moderate and pleasant, without any significant temperature swings between summer and winter. The maximum temperature during summer is 370 C and during winters 330 C, whereas, minimum temperature during summer is about 230 C and during winters 80 C. Monsoon season is from June to September. The average rainfall varies from 2000 mm to 2500 mm.

Forest Resources

The forest cover in DNH, based on the interpretation of satellite data of December 2007 is 211 square km., which is 42.97 % of total geographical area (Map-2). In terms of forest canopy density classes, DNH has 114 square km of moderately dense forest and 97 square km of open forest. Comparisons of present forest cover with that of previous assessment shows a decline of 5 square km, which is largely attributed to encroachment within the forest area as per the report of Forest Survey of India. Various types of forests with their geographical area are shown below:

| Very Dense Forest | 0.00 % |
| --- | --- |
| Moderately Dense Forest | 23.22% |
| Open Forest | 19.76 % |
| Scrubs | 0.20 % |
| Non-Forest | 56.82 % |

The Union Territory of DNH consists of a single district with the same nomenclature through which the proposed line is passing.

Economy

Agriculture is the primary economic activity of DNH, providing employment to around 60 % of the total workforce. Paddy is the main food crop, which is cultivated in almost 40 % of the total net sown area. Other crops include ragi, millets, tur, nagli etc. The local population is also employed as forest labour by the co-operative societies to man the forest products. Animal husbandry is another contributor to the economy. The last decade has witnessed heavy industrialization in the region due to various tax sops offered to the industries in the region. Since then a steady growth in employment and output has been observed. The employment generation is growing at a rate of 5% per annum. Tourism in DNH is an upcoming industry, with systematic and concentrated efforts from the administration.

Power Scenario

The power requirement of DNH is being met by the Central Sector Power generating stations located in the western region. At present, the power allocation from the central sector is 270 MW. The power is supplied by Gujarat Electricity Board through a single circuit from Vapi-Silvassa and distributed to limited number of consumers. The first 66 KV substation was established at Amli in 1979. With the commissioning of the said substation, the electricity department is in a position to provide electricity to all villages. One more 220/66 KV 2 X 160 MVA substation at village Khadoli has been approved by the Ministry of power which is likely to be commissioned soon.

SECTION III:   POLICY, LEGAL & REGULATORY FRAMEWORK

3.0   	POWERGRID’s activities by their inherent nature and flexibility have negligible impacts on environmental and social attributes.  Indian laws relating to environmental and social issues have strengthened in the last decade both due to local needs and international commitments. POWERGRID undertakes its activities within the purview of Indian laws keeping in mind appropriate international obligations and guidelines with respect to environmental and social considerations of Funding Agencies.

- 3.1      ENVIRONMENTAL

- 3.1.1  Constitutional Provisions

Subsequent to the first United Nations Conference on Human Environment at Stockholm in June, 1972, which emphasized the need to preserve and protect the natural environment, the Constitution of India was amended through the historical 42nd Amendment Act, 1976 by inserting Article 48-A and 51-A (g) for protection and promotion of the environment under the Directive Principles of State Policy and the Fundamental Duties respectively. The amendment, inter alia provides:

"The State shall endeavour to protect and improve the environment and to safeguard the forests and wildlife of the country". (New Article 48A)

"It shall be the duty of every citizen of India to protect and improve the natural environment including forests, lakes, rivers and wildlife and to have compassion for living creatures”. (New Article 51 A(g))

Article 21 of the constitution provides, “no person shall be deprived of his life or personal liberty except according to procedure established by law”.

Article 21 is the heart of the fundamental rights and has received expanded meaning from time to time after the decision of the Supreme Court in 1978. The Article 21 guarantee fundamental right to life – a life of dignity to be lived in a proper environment, free of danger of disease and infection. Recently, Supreme Court has broadly and liberally interpreted the Article 21, transgressed into the area of protection of environment, and held that the protection of environment and citizens’ right to live in eco-friendly atmosphere are to be interpreted as the basic right guaranteed under Article 21.

Thus the Indian Constitution has now two fold provisions:

(a) On the one hand, it gives directive to the State for the protection and 
        improvement of environment.

  - On the other hand the citizens owe a constitutional duty to protect and

improve natural environment.

3.1.2  MANDATORY REQUIREMENTS (NATIONAL)

- MOP order/sanction under The Electricity Act, 2003:

Sanction of MOP, GOI is a mandatory requirement for taking up any new transmission project under the section 68(1) of The Electricity Act, 2003. The sanction authorizes POWERGRID to plan and coordinate activities to commission the new projects. Electricity act does not explicitly deal with environmental implications of activities related to power transmission. However, POWERGRID always integrates environmental protection within its project activities.

- Forest Clearance Under The Forest (Conservation) Act, 1980:

When transmission projects pass through forest land, clearance has to be obtained from relevant authorities under the Forest (Conservation) Act, 1980.  This Act was enacted to prevent rapid deforestation and environmental degradation.  State governments cannot de-reserve any forest land or authorize its use for any non-forest purposes without prior approval from the Central government.  POWERGRID projects, when involving forest areas, undergo detailed review and approval procedures to obtain a Forest Clearance certificate from MOEF, Government of India before starting any construction activity in the designated forest areas.

- Environmental Clearances under Environment (Protection) Act,1986:

Since transmission line projects are environmentally clean and do not involve any disposal of solid waste, effluents and hazardous substances in land, air and water, they are kept out of the purview of Environment (Protection) Act, 1986.  However, the recent amendment in the Environment (Protection) Act, 1986 made it necessary to obtain clearance from MoEF for power transmission projects in two districts in the Aravalis (viz., Alwar in Rajasthan and Gurgaon in Haryana). The Aravali ranges, in these two areas, are heavily degraded, hence, any industrial activity there becomes critical. Environment Impact Notification, 1994 lays down specific project categories that require clearance from MoEF. Power transmission projects are not included in this list.

- Batteries (Management and Handling) Rules, 2001:

MOEF vide its notification dt. 16th May, 2001 under the section of 6, 8 and 25 of the Environment (Protection) Act, 1986 has put certain restrictions on disposal of used batteries and its handling. As per the notification, it is the responsibility of bulk consumer (POWERGRID) to ensure that used batteries are not disposed of, in any manner, other than by deposing with the dealer/manufacturer/registered recycler/importer/reconditioner or at the designated collection centres – and to file half yearly return in prescribed form to the concerned State Pollution Control Board.

- Hazardous Wastes (Management and Handling)Amendment Rules, 2003:

MOEF vide its notification dt. 20th May, 2003 under the section of 6, 8 and 25 of the Environment (Protection) Act, 1986 has put used mineral oil under the category of hazardous waste which requires proper handling and disposal. As per the notification, all used oil is to be auctioned/sold to registered recyclers only and file annual return on prescribed form to the concerned State Pollution Control Board.

- Ozone Depleting Substances (Regulation and Control) Rules, 2000:

MOEF vide its notification dt. 17th July, 2000 under the section of 6, 8 and 25 of the Environment (Protection) Act, 1986 has notified rules for regulation /control of Ozone Depleting Substances under Montreal Protocol adopted on 16th September 1987. As per the notification certain controls and regulations have been imposed on manufacturing, import, export and use of these compounds. POWERGRID is following provisions of notification and is phasing out all equipment which uses these substances and planning to achieve CFC free organisation in near future.

- The Biological Diversity Act, 2002:

Under the United Nations Convention on Biological Diversity signed at Rio de Janeiro on the 5th day of June, 1992 of which India is also a party, MoEF has enacted the Biological Diversity Act, 2002 to provide for conservation of biological diversity, sustainable use of its components and fair and equitable sharing of the benefits arising out of the use of biological resources, knowledge and for matters connected therewith. As per the provisions of act certain areas which are rich in biodiversity and encompass unique and representative ecosystems are identified and designated as Biosphere Reserve to facilitate its conservation. All restrictions applicable to protected areas like National Park & Sanctuaries are also applicable to these reserves. POWERGRID will abide by the provision of act wherever applicable and try to totally avoid these biosphere reserves while finalizing the route alignment.

    - FUNDING AGENCIES:

- WB Operational Policies (OP) 4.01/ADB’s Safeguard Policy Statement (June 2009) and JBIC Environmental Guidelines: These outlines funding agencies policy and procedures for environmental assessment (EA) of different developmental projects. All these guidelines classified developmental projects into three categories (A-C) based on its possible environmental and social impacts. Though WB & ADB has another category F1 applicable only to projects involving a credit line through a financial intermediary.

Transmission line projects are categorized as category-B project having limited impact that can be further minimized through mitigative/management measures and would normally require only an environmental review.  POWERGRID takes remedial measures to prevent, minimize, mitigate, or compensate for adverse impact and improve environmental performance. Environment Assessment will take into account the natural environment, human health and safety, social aspects and trans- boundary and global environmental aspects. During EA process, public is also informed at every stage of project execution and their views are considered during decision-making process.

- 3.1.4   PRESCRIPTIVE FRAMEWORK (NATIONAL)

- Applicable Legislations

- 3.1.5   RELEVANT POLICIES

- National Conservation Strategy and Policy Statement on Environment and

Development, 1992

- Policy statement for Abatement of pollution, 1992

- National Environment Policy, 2006

- 3.2.0   SOCIAL

- 3.2.1  Constitutional Provisions

Constitutional provisions in regard to social safeguards are well enshrined in the preamble such as JUSTICE, social, economic and political; LIBERTY of thought, expression, belief, faith and worship; EQUALITY of status and of opportunity; FRATERNITY assuring the dignity of the individual and the unity and integrity of the Nation. Fundamental Rights and Directive Principles guarantee the right to life and liberty.  Health, safety and livelihood have been interpreted as part of this larger right.  Social safeguards provisions are dealt in detail in different Article such as Article-14, 15 17, 23, 24, 25, 46, 330, 332 etc. POWERGRID, through its document, ESPP, commits itself to implementing the said constitutional provision in true sprit to fulfill its environmental and social obligations and responsibilities.

- 3.2.2    MANDATORY REQUIREMENTS (NATIONAL)

- National Rehabilitation and Resettlement Policy, 2007:

Ministry of Rural Development, Government of India has notified a National policy on R&R for PAFs in Feb’04 applicable to all developmental projects where 500 or more families enmass in plain areas or 250 or more families enmass in hilly areas are displaced due to project activity. It essentially addresses the need to provide succour to the assetless rural poor, support the rehabilitation efforts of the resources and provide a broad canvas for an effective consultation between PAFs and authorities responsible for their R&R. It has also listed R&R measures and entitlements for different category of PAFs. Though the National policy as such is not applicable to POWERGRID because transmission projects do not involve displacement of such a large numbers of families since land required for substations is quite small, however, the entitlement benefits listed in the National policy for PAFs have been adopted by POWERGRID in its “Social Entitlement Framework” that is being implemented wherever land acquisition for substations is undertaken.

- Rights of Way And Compensation Under Electricity Act,2003:

The act has a provision for notifying transmission company under section 164 (B) to avail benefits of eminent domain provided under the Indian Telegraph Act, 1885. MOP,GOI vide gazette notification dated 23rd Dec’03 had already notified POWERGRID under this section of said act. Therefore, for the purpose of placing of any wires, poles, etc., POWERGRID has all the powers that the telegraph authority possesses.  Thus, POWERGRID can erect and construct towers without actually acquiring the land.  However, all damages due to POWERGRID activity are compensated at market rate. Power transmission schemes are always planned in such a way that the power of eminent domain is exercised responsibly.

- Provisions Under Land Acquisition Act, 1894, as amended in 1984:

- When land is acquired for sub-stations, POWERGRID will follow procedures laid down under the Land Acquisition Act (LA Act), 1894. POWERGRID sub-stations have never resulted in large scale displacement or loss of livelihoods. There have been only marginal impacts due to flexibility exercised by POWERGRID in selecting sites. The LA Act specifies that in all cases of land acquisition, no award of land can be made by the government authorities unless all compensation has been paid.

    - FUNDING AGENCIES

For POWERGRID, mandatory requirements vis-à-vis Funding Agencies are  comprehensive Resettlement and Rehabilitation (R&R) guidelines and an entitlement framework as per World Bank Operational Directives 4.30 (OP-4.12) and 4.20 and ADB’s Safeguard Policy Statement (June 2009).

- World Bank OD 4.30 (OP-4.12): Involuntary Resettlement:

This directive describes Bank Policy and procedures on involuntary resettlement as well as conditions that borrowers are expected to meet during operations involving resettlement of affected groups. It requires an entitlement framework aimed at restoration, replacement and participation of affected groups. A detailed social assessment and development of an action plan having list of measures for betterment/restoration of lost assets/income is required to be submitted to bank before start of project work. However where only a few people (e.g. about 100-200 individuals) are to be relocated at a particular location, appropriate compensation for assets, logistical support for moving and a relocation grant may be the only requirements, but the principle on which compensation is to be based will remain same as for larger groups.

- World Bank OD 4.20: Indigenous People (IP):

This directive describes World Bank policies and procedures for projects that affect indigenous people. The objective is to ensure that development benefits are socially and culturally compatible and that the IPs are consulted. Thus, the Indigenous People Development Plan/Tribal Development Plan is to be prepared as a prerequisite.  POWERGRID will not only incorporate the IP component whenever necessary, but will also pay attention to marginalized groups such as women, children, etc.

- ADB Safeguard Policy Statement (June 2009):

The SPS, June 2009 describes Bank Policy and operational procedures on three key safeguard areas viz Environmental, Involuntary Resettlement and Indigenous Peoples as well as a set of specific safeguard requirements that borrowers are expected to meet during operations when addressing social and environment impacts and risks. Its objective is to ensure social and environmental sustainability of projects through avoidance, minimization, mitigation and/or compensate of adverse impacts on environment and affected peoples. It also classified project into three categories like category-A where resettlement is significant and involve physical displacement of more than 200 persons, which require a detailed resettlement plan. Category-B where resettlement is not that significant and requires a short resettlement plan. Category-C where no resettlement of peoples are foreseen and neither require resettlement plan nor a resettlement framework.

POWERGRID emphasizes that displacement is not an issue with transmission projects because land below tower/line is not acquired and only a small piece of land is required for substations. However, all affected persons/families shall be provided compensation and rehabilitation assistance along with other measures as per POWERGRID's social entitlement framework which is based on these directives/manuals and National R&R Policy to restore income/livelihood of all affected persons.

- 3.2.4    PRESCRIPTIVE FRAMEWORK (NATIONAL)

- National and State-wide Laws and Policies Relating to Land Acquisition and Issues of R&R

    - Madhya Pradesh Pariyojana Ke Karan Visthapit Vyakti (Punsthapan) Adhiniyam, 1985

    - Maharashtra Project Affected persons Rehabilitation Act, 1986

- 3.2.5   RELEVANT POLICIES

- Resettlement and Rehabilitation Policy- Coal India Ltd., May,2008

- Resettlement and Rehabilitation Policy- NHPC Ltd., 2007

- Policy for Rehabilitation and Resettlement of Land Owners – Land Acquisition Oustees – Haryana State, December,2007;

- The Orissa Resettlement and Rehabilitation Policy, Orissa , May, 2006;

- Resettlement and Rehabilitation Policy – NTPC Ltd., June,2005;

# SECTION-IV: POWERGRID APPROACH FOR ROUTE SELECTION

- 4.0     ROUTE SELECTION - (ASSESSMENT & MANAGEMENT PROCESS)

- At the system planning stage itself one of the factors that govern the evolution of system is the possible infringement with the forest. Wherever such infringements are substantial, different alternative options are considered. The route/ site selection criteria followed by POWERGRID is detailed below:

- While identifying the transmission system for a generation project or as a part of National Power Grid, preliminary route selection is done by POWERGRID based on the topo sheets of Survey of India and Forest Atlas (Govt. of India's Publication).  During route alignment all possible efforts are made to avoid the forest area involvement completely or to keep it to the barest minimum, whenever it becomes unavoidable due to the geography of terrain or heavy cost involved in avoiding it.

- 4.1.1   STUDY OF ALTERNATIVES

- POWERGRID approach towards Route selection

- For selection of optimum route, the following points are taken into consideration:

- The route of the proposed transmission lines does not involve any human rehabilitation.

- Any monument of cultural or historical importance is not affected by the route of the transmission line.

- The proposed route of transmission line does not create any threat to the survival of any community with special reference to Tribal Community.

- The proposed route of transmission line does not affect any public utility services like playgrounds, schools, other establishments etc.

- The line route does not pass through any sanctuaries, National Park etc.

- The line route does not infringe with area of natural resources.

- In order to achieve this, POWERGRID undertakes route selection for individual transmission lines in close consultation with representatives from the Ministry of Environment and Forests and the Department of Revenue. Although under National law POWERGRID has right of eminent domain yet alternative alignments are considered keeping in mind the above-mentioned factors during site selection, with minor alterations often added to avoid environmentally sensitive areas and settlements at execution stage.

- As a rule, alignments are generally cited 10-15 km away from major towns,

whenever possible, to account for future urban expansion.

- Similarly, forests are avoided to the extent possible, and when it is not possible, a route is selected in consultation with the local Divisional Forest Officer, that causes minimum damage to existing forest resources.

- Alignments are selected to avoid wetlands and unstable areas for both financial and environmental reasons.

- In addition, care is also taken to avoid National parks and sanctuaries and any other forest area rich in wild life.

- Keeping above in mind the route of proposed line (LILO of Navsari - Boisar 400kV D/C line) has been so aligned that it takes care of above factors. As such different alternatives were studied with the help of Govt. published data like Forest atlas, Survey of India topo maps, satellite imageries etc. to arrive at most optimum route which can be taken up for detailed survey and assessment of environmental & social impacts for their proper management.

    - EVALUATION OF ROUTE ALIGNMENT ALTERNATIVES FOR LILO of NAVSARI - BOISAR 400 kV D/C LINE :

- In spite of very short line length of approximately 7.5 Kms, two alignments (Map-3) were studied with the help of published data/maps and walkover/GIS survey to arrive at most optimum route for detailed survey. The comparative details of these two alternatives are as follows:

| Sl. No. | Description | Alignment I | Alignment II |
| --- | --- | --- | --- |
| 1 | Route Particulars |  |  |
| i | Route length in KMs | 7.50 | 10.00 |
| ii | Terrain | 10% hilly terrain without any tough hill. Rest 90% plain terrain. | 10% hilly terrain without any tough hill. Rest 90% plain terrain |
| 2 | Env. Details |  |  |
| i | Major town in alignment (Nearby) | Udhwa | Udhwa |
| ii | House within ROW | Nil | Nil |
| iii | Forest in Km/Ha | 1 Km | 3.1 Km |
| iv | Type of forest | Reserved/ Social | Reserved/ Social |
| v | Density of forest | 0.1-0.4 | 0.3-0.5 |
| vi | Type of fauna & flora | Flora: Teak, Terminalia, Khair, Amla, Tendu etc. Fauna: Panther, Bhekar, Peacock, Titar, Wildpig etc. | Flora: Teak, Terminalia, Khair, Amla, Tendu etc. Fauna: Panther, Bhekar, Peacock, Titar, Wildpig etc. |
| vii | Endangered species, if any | Nil | Nil |
| viii | Historical/cultural monument | Nil | Nil |
| ix | Any other relevant information | Nil | Nil |
| 3 | Compensation Cost (Crores) |  |  |
| i | Crop | To be assessed at the time of detailed survey. | To be assessed at the time of detailed survey. |
| ii | Forest | Rs. 0.41 | Rs. 1.28 |
| 4 | No. of crossing |  |  |
| i | Road (SH) | 3 | 2 |
| ii | Railway | NIL | NIL |
| iii | Trans. Line | 1 (400 KV) | 1 (400 KV) |
| iv | River crossing | 1 (minor) | 1 (minor) |
| 5 | Construction problem | Nil | Villagers’ Resistance |
| 6 | O&M problem | Nil | Nil |
| 7 | Overall Remarks | Recommended | Not Recommended |
| 8 | Reasons for selection of final route | It is evident from the table that the total line length, the extent of forest involvement and the density of forest involved in Alt.-I are less than those in Alt.-II. |  |

It may be seen from above that Alternative-I is the most optimum route as it involves minimum ecological sensitive areas like forest and has a shorter line length compared to the other alternative. Hence alternative–I has been recommended for detailed survey.

# SECTION-V: SCREENING OF POTENTIAL ENVIRONMENT IMPACT

# AND ITS MANAGEMENT

- 5.0	IMPACT DUE TO PROJECT LOCATION AND DESIGN

Environmental impact of transmission line projects are not far reaching and are mostly localized to ROW.  However, transmission line project has some affects on natural and socio-culture resources.  These impacts can be minimized by careful route selection. In order to get latest information and further optimization of route modern survey techniques/tools like GIS, GPS aerial photography are also applied.  Introduction of GIS and GPS in route selection result in access to updated/latest information, through satellite images and further optimization of route having minimal environmental impact. Moreover, availability of various details, constraints like topographical and geotechnical details, forest and environmental details etc. help in planning the effective mitigative measures including engineering variations depending upon the site situation/location. However, in the instant project these techniques were not used due to short line length of 7.5 Kms and detail survey by conventional method is proposed.  Although, all possible measures have been taken during the finalization of route alignment for the proposed transmission line but due to peculiarity of terrain and demography of the area where project is being implemented, some environmental impacts may be there. The explanations in brief with regard to specific environment review criteria based on preliminary survey are as follows:

- (i)	Resettlement

- As described earlier all measures are undertaken by POWERGRID at line routing stage itself to avoid settlements such as cities, villages etc. It may be seen from the above description of proposed route alignment and also keeping in mind that no land is acquired for tower foundation as per existing law, the project does not require any resettlement of villagers.

- The proposed project also envisages construction of a 400/220 kV substation at Kala in DNH. After exploring various alternative sites, a site located on government land has been finalized. The substation site doesn’t involve any private land and no resettlement issues are involved. However, R&R issues related to substation land shall be dealt separately as per provisions of ESPP and agreed entitlement matrix with ADB.

- (ii)	 Land value depreciation

- Based on past experience land prices are generally expected to rise in the areas receiving power.  Further, transmission lines generally pass through uninhabited area, agriculture fields and forests, where the land-use is not going to change in foreseeable future. Therefore, the value of land will not be adversely affected to a significant degree.

- (iii) Historical/cultural monuments/value

- As per the POWERGRID’s policy of route selection only that route alignment is finalized which avoids all the historical and cultural monuments. As per the preliminary assessment carried out during finalization of route alignment in consultation with State revenue authorities and ASI, no such physical/cultural monuments are coming in the proposed route alignment.

- (iv) Encroachment into precious ecological areas

- As already explained, all precautions are taken to avoid routing of line through forest and other ecological sensitive areas like National park/Sanctuaries. When inspite of best efforts, it is impossible to avoid forest areas completely, various route alternatives are considered and the one with the least ecological impacts is selected. Keeping this objective in mind, two different route alternatives were considered for the routing of transmission line and alternative-I was selected for detailed survey as it involved minimum forest area. As an additional precautionary measure, POWERGRID will provide construction crews with fuel wood or alternative fuels against collection of fuel wood from nearby forest.

- Transmission lines can serve as new access routes into previously inaccessible or poorly accessible forests, thereby accelerating forest and wildlife loss. In such cases, POWERGRID cannot take action itself, but local Forest Department personnel will normally assess the dangers and take appropriate action, such as establishing guard stations at the entrance to the forest etc. cost of which is borne by POWERGRID and is included in the compensatory afforestation scheme.  Given the already easy access and degraded conditions at the proposed projects sites, this problem is not expected to be encountered.  Nonetheless, POWERGRID staff will report to the Forest Department any noticeable encroachment induced by the Projects.

- (v)	Encroachment into other valuable lands

- Impacts on agricultural land will be restricted to the construction phase and when large-scale maintenance measures are required. Some stretch of the line will pass through Agricultural fields. Agricultural land will be lost at the base of the tower, which is estimated to be 0.2-1 sq. m per average farm holding (Fig-1). The proposed project envisages to construct 7.5 Km of line which will involve approximately 30 towers (13 DA-Type, 5 DB-Type, 5 DC-Type, 7 DD-Type). Construction of 30 towers will result in a maximum possible loss of approx. 30 sq. m. or 0.003 ha. of land  which is quite negligible. The transmission line having total line length of 7.5 Km and approx. 90% portion of it will pass through plains having crops. However, exact numbers of towers coming on such field which may impact crops and number of families likely to be impacted shall be ascertained only after detailed and check survey and fixing of tower locations. As detailed/check survey activity is part of erection contract and will be finalized only after award of contract and completion of detailed/check survey and tower spotting.

- In areas where lines will traverse agricultural land, compensation will be paid to owners for any crop damage incurred as a result of construction activities. POWERGRID field staff will consult affected villagers and local revenue department and apprise him about the project and tower location, which shall be erected in the agricultural land, for compensation.  Revenue department after evaluating the loss due to construction activity and productivity of land arrives at the compensation cost which is paid to farmer. A provision of Rs. 8.00 lakhs towards crop compensation is made in the cost estimate of the project to meet the requirement during construction. Agricultural activities will be allowed to continue following the construction period. If bunds or other on-farm works are disturbed during construction or maintenance, they will be restored to the owner's satisfaction following cessation of construction or maintenance activities. In the event that private trees are felled during construction or maintenance operations, compensation will be paid to the owner in an amount determined by the estimated loss of products from the tree over an eight year period (for fruit bearing trees). Agricultural lands under private ownership will be identified, and in accordance with normal POWERGRID procedures compensation will be paid to the affected villagers. Detailed procedure for tree/crop compensation is placed as Annexure-I

- (vi)  Interference with other utilities and traffic

- As per regulations enacted by Government of India, it is mandatory for POWERGRID to seek clearance prior to construction from department of Railways, Telecommunications and wherever necessary from aviation authorities that are likely to be affected by the construction of transmission lines. The transmission lines affect nearby telecommunication circuits by causing electrical interference.  A standing committee -- Power Telecom Co-ordination Committee (P.T.C.C.) has been constituted by Government of India to plan and implement the mitigating measures for the induced voltage which may occur to nearby telecom circuit and suggest necessary protection measures to be adopted. The committee suggests measures like rerouting of the telecom circuits, conversion of overhead telecom circuits into cables etc. to minimize the interference. The cost of such measures is determined by the Committee and is shared by POWERGRID and Telecom Department on the basis of prevailing norms and guidelines.  Though the exact cost to mitigate the impacts of induction in neighboring telecom circuits would vary from case to case, the cost on an average works out to be Rs.50000/- per km for POWERGRID.

- Wherever transmission line crosses the railways, clearance is taken from that department.  In general, the system is planned and executed in such a way that adequate clearance is maintained between transmission lines on the one hand, and railways, civil aviation and defense installations on the other.  Wherever the transmission lines pass by the airports the towers beyond specified height are painted in alternate orange and white stripes for easy visibility and warning lights are placed atop these towers.

- (vii) Interference with drainage pattern

- As the transmission lines are constructed aerially and the blockage of ground surface is limited to area of tower footings which is very small, there is little possibility of affecting drainage pattern.  In the infrequent instances where the drainage is affected, flow will be trained and guided to safe zones.

- 5.1	ENVIRONMENTAL PROBLEMS DUE TO DESIGN

- Escape of polluting materials

- The equipments installed on lines and substations are static in nature and do not generate any fumes or waste materials.

- (ii)	Explosion/fire hazards

- During the survey and site selection for transmission lines and sub-stations, it has been ensured that these are kept away from oil/gas pipelines and other sites with potential for creating explosions or fires.

- Fires due to flashover from lines can be a more serious problem in deciduous forest. Since forest involved is mostly semi-evergreen in the proposed project it is not going to be a problem. Apart from this state of art safety instruments are installed in the substations on both the ends so that line gets tripped within milliseconds in case of fault.

- (iii)   Erosion hazards due to inadequate provision for resurfacing of exposed area

- Adequate measures are taken to re-surface the area where excavation works are done.  Topsoil disturbed during the development of sites will be used to restore the surface of the platform. Infertile and rocky material will be dumped at carefully selected dumping areas and used as fill for tower foundations.

- (iv)	Environmental aesthetics

- Since spacing between the towers in case of 400 KV lines is approx. 400 meters these will not affect the visual aesthetics of the localities particularly when it is ensured to route the lines as far away from the localities as possible.   POWERGRID takes up plantation of trees to buffer the visual effect around its substations and to provide better living conditions.  Wherever POWERGRID feels it appropriate, discussions will be held with local Forest Department officials to determine feasibility of planting trees along roads running parallel to transmission lines to buffer visual effect in these areas.  In addition, towers may be painted grey or green to merge with the background.

- (v)	Noise/vibration nuisances

- The equipments installed at sub-station are mostly static and are so designed that the noise level always remains within permissible limits i.e. 85 dB as per Indian and International standard- 7194.  POWERGRID had monitored noise/sound level by measuring it at different places in and around reactor and transformer (at 1 m distance). The noise level was found to be ranging from 75 to 83 well within permissible limit of 85 dB. To contain the noise level within the permissible limits whenever noise level increases beyond permissible limits, measures like providing sound and vibration dampers and rectification of equipments are undertaken.

- In addition, plantations of sound absorbing species like Casuarinas, Tamarind, Banyan and Neem etc. are raised at the sub-stations that reduce the sound level appreciably.

- (vi)  Blockage of wildlife passage

- Since the line is passing through mostly agricultural, wasteland and involvement of forest area is limited to bare minimum, possibility of disturbance to wild life are remote.

- 5.2	ENVIRONMENTAL PROBLEMS DURING CONSTRUCTION PHASE

- (i)	Uncontrolled silt runoff

- The Project involves only small scale excavation for tower foundations at scattered locations that are re-filled with excavated material therefore uncontrolled silt run off is not expected.

- (ii)  Nuisance to nearby properties

- As already described in preceding paras, during site selection due care is taken to keep the transmission line and substations away from settlements.  Further, all the construction activities will be undertaken through the use of small mechanical devices e.g. tractors and manual labour, therefore, nuisance to the nearby properties if any, is not expected.

- (iii)  Interference with utilities and traffic and blockage of access way

- Access to the site will be along existing roads or village paths; minor improvements to paths may be made where necessary, but no major construction of roads will be necessary either during construction or as a part of maintenance procedures.

- As and when a transmission line crosses any road/ railways line, the terminal towers are located at sufficient distance so as not to cause any hindrance to the movement of traffic.  Stringing at the construction stage is carried out during lean traffic period in consultation with the concerned authorities and angle towers are planted to facilitate execution of work in different stages.

- (iv)	Inadequate resurfacing for erosion control

- Since proposed line is to be constructed mostly in plain area, erosion problem is not anticipated. However, if due to terrain at some points transmission towers may be placed on slopes and erosion prone soils, internationally accepted engineering practices will be undertaken to prevent soil erosion.  This will include cutting and filling slopes wherever necessary.  The back cut slopes and downhill slopes will be treated with revetments. As explained in above paras, adequate steps shall be taken to resurface the area after construction. Wherever sites are affected by active erosion or landslides, both biological and engineering treatment will be carried out, e.g. provision of breast walls and retaining walls, and sowing soil binding grasses around the site. Furthermore, construction is generally undertaken outside the rainy season. As the proposed line is mostly passing through plain areas these problems are not anticipated.

- (v)	Inadequate disposition of borrow area

- As mentioned earlier the transmission tower foundations involve excavations on small scale basis and the excavated soil is utilized for back filling.  In case of substations generally the sites are selected in such a manner that the volume of cutting is equal to volume of filling avoiding borrowing of the area.

- (vi)   Protection of Worker's health/safety

- Provisions for workers' health and safety will be guided by the Safety Regulations/Safety Manual published by POWERGRID, and included in tender documents. Various aspects such as, work and safety regulations, workmen's compensation, insurance are adequately covered under the Erection Conditions of Contract (ECC), a part of bidding documents.

- In addition training is imparted to the workers in fire fighting and safety measures.  Safety tools like helmet, safety belt, gloves etc. are provided to them in accordance to the provisions of Safety Manual.  First aid facilities will be made available with the labour gangs, and doctors called in from nearby towns when necessary.  The number of outside (skilled) labourers will be quite small, of the order of 25-30 people per group. The remaining workforce of unskilled labourers will be comprised of local people.  Workers are also covered by the statutory Workmen (Compensation) Act.

POWERGRID has a dedicated unit to oversee all health and safety aspects of its project under the Operation Service Deptt. POWERGRID has framed guidelines/checklist for workers’ safety as its personnel are exposed to live EHV apparatus and transmission lines. These guidelines/checklist include work permits and safety precautions for work on the transmission lines both during construction and operation (Annexure-2) and is monitored regularly by site in-charge and corporate Operation Services. In addition training is imparted to the workers in fire fighting and safety measures.  Safety tools like helmet, safety belt, gloves etc. are provided to them in accordance to the provisions of Safety Manual.  First aid facilities will be made available with the labour gangs, and doctors called in from nearby towns when necessary.  The number of outside (skilled) labourers will be quite small, of the order of 25-30 people per group. The remaining workforce of unskilled labourers will be comprised of local people.  Workers are also covered by the statutory Workmen (Compensation) Act.  Regular health checkups are conducted for construction workers. The construction sites and construction workers’ houses will be disinfected regularly if required. In order to minimize/checking of spread of socially transmitted diseases e.g. HIV/AIDS etc. POWERGRID will conduct awareness building programs on such issues for the construction workers.

5.3	ENVIRONMENTAL PROBLEMS RESULTING FROM OPERATION

- (i)   O&M Staff/Skills less than acceptable resulting in variety of adverse effects

- The O&M program in POWERGRID is normally implemented by sub-station personnel for both, the lines as well as sub-stations.  However, in respect of the long distance transmission lines there are monitoring offices which are located at various points en-route. Monitoring measures employed include patrolling and thermo-vision scanning. The supervisors and managers entrusted with O&M responsibilities are intensively trained for necessary skills and expertise for handling these aspects.

- A monthly preventive maintenance program will be carried out to disclose problems related to cooling oil, gaskets, circuit breakers, vibration measurements, contact resistance, condensers, air handling units, electrical panels and compressors. Any sign of soil erosion is also reported and rectified. Monitoring results are published monthly, including a report of corrective action taken and a schedule for future action.

Exposure to Electro Magnetic Fields (EMF) There have been some concerns about possible increased risk of cancer from exposure to electromagnetic radiation from overhead transmission lines and research has been undertaken into this matter throughout the world. A World Health Organization (WHO) review also in 1996 held as part of the International EMF Project concluded that:

“From the current scientific literature there is no convincing evidence that exposure to radiation field shortens the life span of humans or induces or promotes cancer”.

No EMF exposure guidelines have been drawn in India though exposure guidelines have been drawn up outside India including:

- State Transmission Lines Standards and Guidelines in the USA;

- International Commission on Non-Ionizing  Radiation Protection (ICNIRP);

- US National Council on Radiation; and

- American Conference on Government and Industrial Hygienist (ACGIH).

The maximum value of magnetic field within ROW of 400 kV DC overhead power transmission line is approximately 40 T. The ICNIRP guidelines present limiting exposure to EMFs, although it adds that the levels quoted should not be interpreted as distinguishing ‘safe’ from ‘unsafe’ EMF levels. The ICNIRP guideline for the general public (up to 24 hours a day) is a maximum exposure level of 1,000 mG or 100 T. A study carried out by Central Power Research Institute (CPRI) on POWERGRID lines reveals that the EMF about 1 m above ground near a 400 kV single circuit transmission line range from 3 – 7.2 T in the RoW. The impact of EMF is also dependent on the duration of exposure and therefore no significant adverse impact is envisaged.  POWERGRID complies with international norms for field strength limits which are certified by Power Technologies Inc, USA. POWERGRID is following the approved international standards and design, which are absolutely safe. Based on the studies carried out by different countries on the safety of EHV lines in reference to EMF affect POWERGRID have also carried out such studies with the help of PTI, USA and CPRI, Bangalore on their design. The studies inferred that the POWERGRID design are safe and follow the required international standard. (Synopsis of the Power Technologies Inc. report enclosed as Annexure-3)

Poly Chlorinated Biphenyls (PCBs) due to its high heat capacity, low flammability and low electrical conductivity was extensively used as insulating material in capacitors and transformers. But after the finding that these PCBs are non-biodegradable and has carcinogenic tendency, its use in electrical equipments as insulating medium has been banned all over the world long back. However, it has been reported in some studies that chances of contamination of oil with PCB is possible. Keeping that in mind, POWERGRID has discontinued procurement electrical equipments containing PCB more than 2 mg/kg and specification (as per IEC 61619 or ASTM D4059) is being stated in the tender document. POWERGRID in association with NGC, UK has setup a Regional Testing Laboratories for testing of existing oil for PCB traces and results of this suggests that PCB contamination is not an issue with POWERGRID. The World Bank has also made following comments after a detailed study on Management of PCBs in India:

“ Power Grid were the most advanced in testing for PCBs of the organizations visited for this project. They have established a procedure for identification of the presence of PCBs in transformer oil and more detailed analysis for positive identification sample. To date no significant concentrations of PCBs have been detected. Power Grid do not appear to have any significant issues regarding PCB management and have initiated a testing program. The experience & laboratories of Power Grid could be used to provide a national PCB auditing service”.

5.4     CRITICAL ENVIRONMENTAL REVIEW CRITERIA

(i)	Loss of irreplaceable resources

The transmission projects do not involve any large scale excavation and land is lost to the extent of 0.2-1 sq m only for each foundation. A total of 4.6 ha of forest land will be affected along 1 km of 7.5 km stretch long transmission line and as per regulation, afforestation will be undertaken to compensate the loss of forest area.  Moreover, provision of an artificial recharge pit of approx. 50 m3 in the substations to harvest roof top, run off water from colony & switchyard area, shall help in recharging the ground water resulting in conservation of precious natural resource like water.

(ii)	 Accelerated use of resources for short-term gains

The project will not be making use of any natural resources occurring in the area during construction as well as maintenance phases.  The construction material such as tower members, cement etc shall come from factories while the excavated soil shall be used for backfilling to restore the surface.  Thus the project shall not cause any accelerated use of resources for short term gains.

(iii)   Endangering of species

During alignment survey, Forest officials also confirmed that no endangered species of flora and fauna exist in the project area as well as no forest having good biodiversity is getting affected. Thus, there is no possibility of endangering/causing extinction of any species.

(iv)	Promoting undesirable rural-to urban migration

The project will not cause any submergence or loss of land holdings that normally trigger migration. It also does not involve acquisition of any private land holdings.  Hence, there is no possibility of any migration.

In some instances, it has been seen that increase in economic and employment opportunities due to project activity may promote some kind of migration.  However, considering the size of the instant project and location of the subproject area migration of people is not foreseen.

5.5    PUBLIC CONSULTATION:

Public consultation/information is an integral part of the project implementation. Public is informed about the project at every stage of execution. During survey also POWERGRID’s site officials meet people and inform them about the routing of transmission lines.  During the construction, every individual, on whose land tower is erected and people affected by ROW, are consulted.

Apart from this, public consultation using different technique like Public Meeting, Small Group Meeting, informal Meeting  as  per  Environmental Social Policy  & Procedures of POWERGRID  (ESPP) shall also be carried out during different activities of project cycle. During such consultation the public is informed about the project in general and in particular about the following:

- complete project plan (i.e. its route and terminating point and substations, if any, in between);

- POWERGRID design standards in relation to approved international standards;

- health impacts in relation to EMF;

- measures taken to avoid public utilities such as school, hospitals, etc.;

- other impacts associated with transmission lines and POWERGRID’s approach to minimizing and solving them;

- land acquisition details, proposed R&R measures and compensation packages in line with POWERGRID’s policy;

- Trees and crop compensation process.

The process of such consultation will be continued during project implementation and even during O&M stage.

For the LILO transmission line public consultation was held on 10.08.2010 at villages Amboli and Udhwa, as the said transmission line is passing through these two villages (Plate 1&2). The villagers have been briefed about the tentative route of the LILO transmission line. The villages were also informed about various nation building works being carried out by POWERGRID in the filed of power transmission and benefits of the project to UT of Dadra and Nagar Haveli. The meeting was attended by the Sarpanchs of the villages, other villagers and officials of POWERGRID. The details of discussion during public consultation along with photographs are enclosed as Annexure-4.

5.6	CONCLUSIONS:

As it is evident from the above mentioned discussions that DNH is a rich area as far as forest resources are concerned. However, through the process of careful route selection, POWERGRID is able to avoid forest areas to the maximum extent possible. Thus, it can be concluded that the route selected is the most optimum route for the proposed transmission line. The infrastructural constraints are very real and pose a limiting factor on the development of the area.  The above facts while on the one hand underline the need for implementation of the project for overall development of the area and on another hand suggests that a detailed EIA may not be necessary.

# SECTION-VI:  ORGANISATIONAL SUPPORT & ENVIRONMENT

# MANAGEMENT PLAN

6.0      ENVIRONMENTAL MONITORING PROGRAM IN POWERGRID:

- Monitoring is a continuous process for POWERGRID projects at all the stages be it the site selection, construction or maintenance.

- The success of POWERGRID lies in its strong monitoring systems.  Apart from the site managers reviewing the progress on daily basis regular project review meetings are held at least on monthly basis which is chaired by Executive Director of the region wherein apart from construction issues the environmental aspects of the projects are discussed and remedial measures taken wherever required.  The exceptions of these meetings are submitted to the Directors and Chairman and Managing Director of the Corporation.  The progress of various on-going projects is also informed to the Board of Directors. Following is the organization support system for proper implementation and monitoring of Environmental & Social Management Plan. Flow chart of organization support structure is depicted in Exhibit -2.

- 6.1     CORPORATE LEVEL

- An Environmental Management Cell at corporate level was created within POWERGRID in 1992 and subsequently upgraded to an Environment Management Department (EMD) in 1993 and in 1997 it has been further upgraded to Environment & Social Management Deptt. (ESMD) by incorporating social aspect of project. Briefly, the ESMD's responsibilities are as follows:

- Advising and coordinating RHQs and Site to carry out environmental and social surveys for new projects.

- Assisting RHQs and site to finalize routes of entire power transmission line considering environmental and social factors that could arise enroute

- Help RHQs and Site to follow-up with the state forest offices and other state departments in expediting forest clearances and the land acquisition process of various ongoing and new projects

- Act as a focal point for interaction with the M0EF for expediting forest clearances and follow-ups with the Ministry of Power.

- Imparts training to POWERGRID’s RHQs & Site officials on environment and social issues and their management plan.

- 6.2     REGIONAL LEVEL

- At each of its 9 (nine) Regional Offices, POWERGRID has  Environmental and Social Management Cell (ESMC) to manage Environmental and Social issues and to coordinate between ESMD at the Corporate level and the Divisional Headquarters. The key functions envisaged for ESMC are:

- Advising and coordinating field offices to carry out environmental and social surveys for new projects envisaged in the Corporate Investment Plan

- Assisting the ESMD and site to finalize routes of entire power T/L considering the environmental and social factors that could arise en-route

- To follow-up forest clearances and land acquisition processes with state forest offices and other state departments for various ongoing and new projects

- Acting as a focal point for interaction with the ESMD and site on various environmental and social aspects.

  - SITE OFFIECE

- At site, POWERGRID has made the Site-incharge responsible for implementing the Environmental and Social aspect of project and the team is termed as Environmental and Social Management Team (ESMT). Key functions of the ESMT are:

- Conduct surveys on environmental and social aspects to finalize the route for the power transmission projects

- Conduct surveys for the sites  being considered for land acquisition

- Interact with the Forest Departments to make the forest proposal and follow it up for MOEF clearance.

- Interact with Revenue Authorities for land acquisition and follow it up with Authorized Agencies for implementation of Social Management Plan (SMP).

- Implementation of Environment  Management Plan (EMP) and SMP

- Monitoring of EMP and SMP and producing periodic reports on the same.

It may be noted that POWERGRID is well equipped to implement and monitor its environment and Social Management plans.

- As regards monitoring of impacts on ecological resources particularly in Forest, Sanctuary or National Park, it is generally done by the concerned Divisional Forest Officer, Chief Wildlife Warden and their staff as a part of their normal duties.  As no forest area is involved in the instant project such monitoring/provision shall not be applicable to proposed project.  A detailed Environment Management Plan (EMP) including monitoring plan for all possible environmental and social impact and its proper management has been drawn (Table- 6.1) and will be implemented during various stage of project execution. A budget estimate towards tree/crop compensation and EMP implementation is prepared and is placed at Annexure-5. Since many provisions of EMP are to be implemented by contractor, in order to ensure proper monitoring EMP has been included in the contract document. (Annexure-6)

- 6.4      ENVIRONMENTAL REVIEW  :

Periodic review by corporate ESMD and higher management including review by POWERGRID CMD of all environmental and social issues is under taken to ensure that EMP and other measures are implemented at site. Besides it annual review by independent Auditor under ISO: 14001 shall also be undertaken for compliance of agreed policy and management plan.

Table-6.1 Environment Management Plan

| Project activity /stage | Potential impact | Proposed mitigation measure | Parameter to be monitored | Measurement and frequency | Institutional responsibility | Implementation schedule |
| --- | --- | --- | --- | --- | --- | --- |
| Pre-construction |  |  |  |  |  |  |
| Location of transmission towers and transmission line alignment and design | Exposure to safety related risks | Setback of dwellings to overhead line route designed in accordance with permitted level of power frequency and the regulation of supervision at sites. | Tower location and line alignment selection with respect to nearest dwellings | Setback distances to nearest houses - once | POWERGRID | Part of tower siting survey and detailed alignment survey and design |
| Equipment specifications and design parameters | Release of chemicals and gases in receptors (air, water, land) | PCBs not used in substation transformers or other project facilities or equipment. | Transformer design | Exclusion of PCBs in transformers stated in tender specification - once | POWERGRID | Part of tender specifications for the equipment |
|  |  | Processes, equipment and systems not to use chlorofluorocarbons (CFCs), including halon, and their use, if any, in existing processes and systems should be phased out and to be disposed of in a manner consistent with the requirements of the Government | Process, equipment and system design | Exclusion of CFCs stated in tender specification – once | POWERGRID | Part of tender specifications for the equipment |
|  |  |  |  | Phase out schedule to be prepared in case still in use – once |  | Part of equipment and process design |
| Transmission line design | Exposure to electromagnetic interference | Transmission line design to comply with the limits of electromagnetic interference from overhead power lines | Electromagnetic field strength for proposed line design | Line design compliance with relevant standards - once | POWERGRID | Part of detailed alignment survey and design |
| Substation location and design | Exposure to noise | Design of plant enclosures to comply with noise regulations. | Expected noise emissions based on substation design | Compliance with regulations - once | POWERGRID | Part of detailed siting survey and design |
| Location of transmission towers and transmission line alignment and design | Impact on water bodies and land | Consideration of tower location at where they could be located to avoid water bodies or agricultural land. | Tower location and line alignment selection (distance to water and/or agricultural land) | Consultation with local authorities and land owners - once | POWERGRID | Part of tower siting survey and detailed alignment survey and design |
|  | Social inequities | Careful route selection to avoid existing settlements | Tower location and line alignment selection (distance to nearest dwellings or social institutions) | Consultation with local authorities and land owners - once | POWERGRID | Part of detailed tower siting and alignment survey and design |
|  |  | Minimise need to acquire agricultural land | Tower location and line alignment selection (distance to agricultural land) | Consultation with local authorities and land owners - once | POWERGRID | Part of detailed tower siting and alignment survey and design |
| Involuntary resettlement or land acquisition | Social inequities | Compensation paid for temporary/ permanent loss of productive land as per LAA & its process | RAP implementation | Consultation with affected parties – once in a quarter | POWERGRID | Prior to construction phase |
| Encroachment into precious ecological areas | Loss of precious ecological values/ damage to precious species | Avoid encroachment by careful site and alignment selection | Tower location and line alignment selection (distance to nearest designated ecological protection area) | Consultation with local forest authorities - once | POWERGRID | Part of detailed siting and alignment survey /design |
| Transmission line through forestland | Deforestation and loss of biodiversity | Avoid encroachment by careful site and alignment selection | Tower location and line alignment selection (distance to nearest protected or reserved forest) | Consultation with local authorities - once | POWERGRID | Part of detailed siting and alignment survey/design |
|  |  | Minimise the need by using existing towers, tall towers and RoW, wherever possible |  | Consultation with local authorities and design engineers - once |  |  |
|  |  | Obtain statutory clearances from the Government | Statutory approvals from Government | Compliance with regulations – once for each subproject |  |  |
| Encroachment into farmland | Loss of agricultural productivity | Use existing tower footings/towers wherever possible | Tower location and line alignment selection | Consultation with local authorities and design engineers - once | POWERGRID | Part of detailed alignment survey and design |
|  |  | Avoid siting new towers on farmland wherever feasible | Tower location and line alignment selection | Consultation with local authorities and design engineers - once |  | Part of detailed siting and alignment survey /design |
|  |  | Farmers compensated for any permanent loss of productive land | Design of Implementation of Crop Compensation (based on affected area) | Consultation with affected parties – once in a quarter |  | Prior to construction phase |
|  |  | Farmers/landowners compensated for significant trees that need to be trimmed/ removed along RoW. | Design of Implementation of Tree compensation (estimated area to be trimmed/removed) | Consultation with affected parties – once in a quarter |  | Prior to construction phase |
|  |  |  | Statutory approvals for tree trimming /removal | Compliance with regulations – once for each subproject |  | Part of detailed siting and alignment survey /design |
| Noise related | Nuisance to neighbouring properties | Substations sited and designed to ensure noise will not be a nuisance. | Noise levels | Noise levels to be specified in tender documents - once | POWERGRID | Part of detailed equipment design |
| Interference with drainage patterns/Irrigation channels | Flooding hazards/loss of agricultural production | Appropriate siting of towers to avoid channel interference | Tower location and line alignment selection (distance to nearest flood zone) | Consultation with local authorities and design engineers - once | POWERGRID | Part of detailed alignment survey and design |
| Escape of polluting materials | Environmental pollution | Transformers designed with oil spill containment systems, and purpose-built oil, lubricant and fuel storage system, complete with spill cleanup equipment. | Equipment specifications with respect to potential pollutants | Tender document to mention specifications - once | POWERGRID | Part of detailed equipment design /drawings |
|  |  | Substations to include drainage and sewage disposal systems to avoid offsite land and water pollution. | Substation sewage design | Tender document to mention detailed specifications - once | POWERGRID | Part of detailed substation layout and design /drawings |
| Explosions/Fire | Hazards to life | Design of substations to include modern fire control systems/firewalls. | Substation design compliance with fire prevention and control codes | Tender document to mention detailed specifications - once | POWERGRID | Part of detailed substation layout and design /drawings |
|  |  | Provision of fire fighting equipment to be located close to transformers. |  |  |  |  |
| Construction |  |  |  |  |  |  |
| Equipment layout and installation | Noise and vibrations | Construction techniques and machinery selection seeking to minimize ground disturbance. | Construction techniques and machinery | Construction techniques and machinery creating minimal ground disturbance - once at the start of each construction phase | POWERGRID (Contractor through contract provisions) | Construction period |
| Physical construction | Disturbed farming activity | Construction activities on cropping land timed to avoid disturbance of field crops (within one month of harvest wherever possible). | Timing of start of construction | Crop disturbance –Post harvest as soon as possible but before next crop - once per site | POWERGRID (Contractor through contract provisions) | Construction period |
| Mechanized construction | Noise, vibration and operator safety, efficient operation | Construction equipment to be well maintained. | Construction equipment – estimated noise emissions | Complaints received by local authorities - every 2 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
|  | Noise, vibration, equipment wear and tear | Turning off plant not in use. | Construction equipment – estimated noise emissions and operating schedules | Complaints received by local authorities - every 2 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
| Construction of roads for accessibility | Increase in airborne dust particles | Existing roads and tracks used for construction and maintenance access to the line wherever possible. | Access roads, routes (length and width of new access roads to be constructed) | Use of established roads wherever possible - every 2 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
|  | Increased land requirement for temporary accessibility | New access ways restricted to a single carriageway width within the RoW. | Access width (meters) | Access restricted to single carriageway width within RoW - every 2 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
| Temporary blockage of utilities | Overflows, reduced discharge | Temporary placement of fill in drains/canals not permitted. | Temporary fill placement (m3) | Absence of fill in sensitive drainage areas - every 4 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
| Site clearance | Vegetation | Marking of vegetation to be removed prior to clearance, and strict control on clearing activities to ensure minimal clearance. | Vegetation marking and clearance control (area in m2) | Clearance strictly limited to target vegetation - every 2 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
| Trimming/cutting of trees within RoW | Fire hazards | Trees allowed growing up to a height within the RoW by maintaining adequate clearance between the top of tree and the conductor as per the regulations. | Species-specific tree retention as approved by statutory authorities (average and maximum tree height at maturity, in meters) | Presence of target species in RoW following vegetation clearance – once per site | POWERGRID (Contractor through contract provisions) | Construction period |
|  | Loss of vegetation and deforestation | Trees that can survive pruning to comply should be pruned instead of cleared. | Species-specific tree retention as approved by statutory authorities | Presence of target species in RoW following vegetation clearance – once per site | POWERGRID (Contractor through contract provisions) | Construction period |
|  |  | Felled trees and other cleared or pruned vegetation to be disposed of as authorized by the statutory bodies. | Disposal of cleared vegetation as approved by the statutory authorities (area cleared in m2) | Use or intended use of vegetation as approved by the statutory authorities – once per site | POWERGRID (Contractor through contract provisions) | Construction period |
| Wood/vegetation harvesting | Loss of vegetation and deforestation | Construction workers prohibited from harvesting wood in the project area during their employment, (apart from locally employed staff continuing current legal activities). | Illegal wood /vegetation harvesting (area in m2, number of incidents reported) | Complaints by local people or other evidence of illegal harvesting - every 2 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
| Surplus earthwork/soil | Runoff to cause water pollution, solid waste disposal | Soil excavated from tower footings disposed of by placement along roadsides, or at nearby house blocks if requested by landowners. | Soil disposal locations and volume (m3) | Acceptable soil disposal sites - every 2 weeks | POWER GRID (Contractor through contract provisions) | Construction period |
| Substation construction | - Loss of soil | Fill for the substation foundations obtained by creating or improving local water supply ponds or drains, with the agreement of local communities. | Borrow area siting (area of site in m2 and estimated volume in m3) | Acceptable borrow areas that provide a benefit - every 2 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
| Substation construction | Water pollution | Construction activities involving significant ground disturbance (i.e. substation land forming) not undertaken during the monsoon season. | Seasonal start and finish of major earthworks | Timing of major disturbance activities - prior to start of construction activities | POWERGRID (Contractor through contract provisions) | Construction period |
| Site clearance | Vegetation | Tree clearances for easement establishment to only involve cutting trees off at ground level or pruning as appropriate, with tree stumps and roots left in place and ground cover left undisturbed. | Ground disturbance during vegetation clearance (area, m2) | Amount of ground disturbance - every 4 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
|  |  |  | Statutory approvals | Statutory approvals for tree clearances – once for each site | POWERGRID (Contractor through contract provisions) | Construction period |
| Tower construction – disposal of surplus earthwork/fill | Waste disposal | Excess fill from tower foundation excavation disposed of next to roads or around houses, in agreement with the local community or landowner. | Location and amount (m3)of fill disposal | Appropriate fill disposal locations - every 2 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
| Storage of chemicals and materials | Contamination of receptors (land, water, air) | Fuel and other hazardous materials securely stored above high flood level. | Location of hazardous material storage; spill reports (type of material spilled, amount (kg or m3) and action taken to control and clean up spill) | Fuel storage in appropriate locations and receptacles - every 2 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
| Construction schedules | Noise nuisance to neighbouring properties | Construction activities only undertaken during the day and local communities informed of the construction schedule. | Timing of construction (noise emissions, [dB(A)]) | Daytime construction only - every 2 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
| Provision of facilities for construction workers | Contamination of receptors (land, water, air) | Construction workforce facilities to include proper sanitation, water supply and waste disposal facilities. | Amenities for Workforce facilities | Presence of proper sanitation, water supply and waste disposal facilities - once each new facility | POWERGRID (Contractor through contract provisions) | Construction period |
| Encroachment into farmland | Loss of agricultural productivity | Use existing access roads wherever possible | Usage of existing utilities | Complaints received by local people /authorities - every 4 weeks | POWERGRID (Contractor through contract provisions) | Construction period |
|  |  | Ensure existing irrigation facilities are maintained in working condition | Status of existing facilities |  |  |  |
|  |  | Protect /preserve topsoil and reinstate after construction completed | Status of facilities (earthwork in m3) |  |  |  |
|  |  | Repair /reinstate damaged bunds etc after construction completed | Status of facilities (earthwork in m3) |  |  |  |
|  | Social inequities | Compensation for temporary loss in agricultural production | Implementation of Crop compensation (amount paid, dates, etc.) | Consultation with affected parties – once in a quarter | POWERGRID | Prior to construction |
| Uncontrolled erosion/silt runoff | Soil loss, downstream siltation; | Need for access tracks minimised, use of existing roads. | Design basis and construction procedures (suspended solids in receiving waters; area re-vegetated in m2; amount of bunds constructed [length in meter, area in m2, or volume in m3]) | Incorporating good design and construction management practices – once for each site | POWERGRID (Contractor through contract provisions) | Construction period |
|  |  | Limit site clearing to work areas |  |  |  |  |
|  |  | Regeneration of vegetation to stabilise works areas on completion (where applicable) |  |  |  |  |
|  |  | Avoidance of excavation in wet season |  |  |  |  |
|  |  | Water courses protected from siltation through use of bunds and sediment ponds |  |  |  |  |
| Nuisance to nearby properties | Losses to neighbouring land uses/ values | Contract clauses specifying careful construction practices. | Contract clauses | Incorporating good construction management practices – once for each site | POWERGRID (Contractor through contract provisions) | Construction period |
|  |  | As much as possible existing access ways will be used. | Design basis and layout | Incorporating good design engineering practices – once for each site |  |  |
|  |  | Productive land will be reinstated following completion of construction | Reinstatement of land status (area affected, m2) | Consultation with affected parties – twice – immediately after completion of construction and after the first harvest |  |  |
|  | Social inequities | Compensation will be paid for loss of production, if any. | Implementation of Tree/Crop compensation (amount paid) | Consultation with affected parties – once in a quarter | POWERGRID | Prior to construction |
| Inadequate siting of borrow areas | Loss of land values | Existing borrow sites will be used to source aggregates, therefore, no need to develop new sources of aggregates | Contract clauses | Incorporating good construction management practices – once for each site | POWERGRID (Contractor through contract provisions) | Construction period |
| Health and safety | Injury and sickness of workers and members of the public | Contract provisions specifying minimum requirements for construction camps | Contract clauses (number of incidents and total lost-work days caused by injuries and sickness) | Contract clauses compliance – once every quarter | POWERGRID (Contractor through contract rovisions) | Construction period |
|  |  | Contractor to prepare and implement a health and safety plan. |  |  |  |  |
|  |  | Contractor to arrange for health and safety training sessions |  |  |  |  |
| Inadequate construction stage monitoring | Likely to maximise damages | Training of POWERGRID environmental monitoring personnel | Training schedules | Number of programs attended by each person – once a year | POWERGRID | Routinely throughout construction period |
|  |  | Implementation of effective environmental monitoring and reporting system using checklist of all contractual environmental requirements | Respective contract checklists and remedial actions taken thereof. | Submission of duly completed checklists of all contracts for each site - once |  |  |
|  |  | Appropriate contact clauses to ensure satisfactory implementation of contractual environmental mitigation measures. | Compliance report related to environmental aspects for the contract | Submission of duly completed compliance report for each contract - once |  |  |
| Operation and Maintenance |  |  |  |  |  |  |
| Location of transmission towers and transmission line alignment and design | Exposure to safety related risks | Setback of dwellings to overhead line route designed in accordance with permitted level of power frequency and the regulation of supervision at sites. | Compliance with setback distances (“as-built” diagrams) | Setback distances to nearest houses – once in quarter | POWERGRID | During operations |
| Equipment submerged under flood | Contamination of receptors (land, water) | Equipment installed above the high flood level (HFL) by raising the foundation pad. | Substation design to account for HFL (“as-built” diagrams) | Base height as per flood design - once | POWERGRID | During operations |
| Oil spillage | Contamination of land/nearby water bodies | Substation transformers located within secure and impervious sump areas with a storage capacity of at least 100% of the capacity of oil in transformers and associated reserve tanks. | Substatio bunding (Oil sump) (“as-built” diagrams) | Bunding (Oil sump) capacity and permeability - once | POWERGRID | During operations |
| Inadequate provision of staff/workers health and safety during operations | Injury and sickness of staff /workers | Careful design using appropriate technologies to minimise hazards | Usage of appropriate technologies (lost work days due to illness and injuries) | Preparedness level for using these technologies in crisis – once each year | POWERGRID | Design and operation |
|  |  | Safety awareness raising for staff. | Training/awareness programs and mock drills | Number of programs and percent of staff /workers covered – once each year |  |  |
|  |  | Preparation of fire emergency action plan and training given to staff on implementing emergency action plan |  |  |  |  |
|  |  | Provide adequate sanitation and water supply facilities | Provision of facilities | Complaints received from staff /workers every 2 weeks |  |  |
| Electric Shock Hazards | Injury/mortality to staff and public | Careful design using appropriate technologies to minimise hazards | Usage of appropriate technologies (number of injury incidents, lost work days) | Preparedness level for using these technologies in crisis – once a month | POWERGRID | Design and Operation |
|  |  | Security fences around substations | Maintenance of fences | Report on maintenance – every 2 weeks |  |  |
|  |  | Barriers to prevent climbing on/dismantling of transmission towers | Maintenance of barriers |  |  |  |
|  |  | Appropriate warning signs on facilities | Maintenance of warning signs |  |  |  |
|  |  | Electricity safety awareness raising in project areas | Training /awareness programs and mock drills for all concerned parties | Number of programs and percent of total persons covered – once each year |  |  |
| Operations and maintenance staff skills less than acceptable | Unnecessary environmental losses of various types | Adequate training in O&M to all relevant staff of substations and transmission line maintenance crews. | Training/awareness programs and mock drills for all relevant staff | Number of programs and percent of staff covered – once each year | POWERGRID | Operation |
|  |  | Preparation and training in the use of O&M manuals and standard operating practices. |  |  |  |  |
| Inadequate periodic environmental monitoring. | Diminished ecological and social values. | Power Grid staff to receive training in environmental monitoring of project operations and maintenance activities. | Training/awareness programs and mock drills for all relevant staff | Number of programs and percent of staff covered – once each year | POWERGRID | Operation |
| Equipment specifications and design parameters | Release of chemicals and gases in receptors (air, water, land) | Processes, equipment and systems using cholofluorocarbons (CFCs), including halon, should be phased out and to be disposed of in a manner consistent with the requirements of the Government. | Process, equipment and system design | Phase out schedule to be prepared in case still in use – once in a quarter | POWERGRID | Operations |
| Transmission line maintenance | Exposure to electromagnetic interference | Transmission line design to comply with the limits of electromagnetic interference from overhead power lines | Required ground clearance (meters) | Ground clearance - once | POWERGRID | Operations |
| Noise related | Nuisance to neighbouring properties | Substations sited and designed to ensure noise will not be a nuisance. | Noise levels (dB(A)) | Noise levels at boundary nearest to properties and consultation with affected parties if any - once | POWERGRID | Operations |