| Sl. No. | Clause | Existing provision | Amended provision |
| --- | --- | --- | --- |
| 1. | GCC clause No: 7 | The payment terms would be as follows: - 100% payment shall be made within 30 days of completion and inspection and acceptance of job & receipt of the invoices. - No compensation, whatsoever, shall be made for the items/jobs rejected during inspection/acceptance of the work executed. | Replace GCC Clause No. 7 with the following: The payment terms would be as follows: - 100% payment shall be made within 30 days of completion and inspection and acceptance of job & receipt of the invoices. - No compensation, whatsoever, shall be made for the items/jobs rejected during inspection/acceptance of the work executed. - Stages of payment for the BOQ line items 1, 2, 3 & 8 shall be as per Table No.-1 given below. |
| 2. | ITC clause No: 14.2 | …………….. The payment terms would be as follows: - 100% payment shall be made within 30 days of completion and inspection and acceptance of job & receipt of the invoices. - No compensation, whatsoever, shall be made for the items/jobs rejected during inspection/acceptance of the work executed. | Replace ITC Clause No. 14.2 with the following: ………………. The payment terms would be as follows: - 100% payment shall be made within 30 days of completion and inspection and acceptance of job & receipt of the invoices. - No compensation, whatsoever, shall be made for the items/jobs rejected during inspection/acceptance of the work executed. - Stages of payment for the BOQ line items 1, 2, 3 & 8 shall be as per Table No.-I given below. |

| Table No.-1 |  |  |
| --- | --- | --- |
| BOQ. Line item No. | Description | % of Payment |
| 1. | Master Plan |  |
| a | On submission of conceptual master plan, Landscaping and bulk services with alternatives and acceptance by POWERGRID | 40% of unit rate |
| b | On approval of master plan, Landscaping and bulk services by POWERGRID | 50% of unit rate |
| c | On submission of final as built drawings completion certificate from statutory authorities/ POWERGRID | 10% of unit rate |
| 2 | Design & Drawing of Residential Buildings |  |
| a | On submission of concept design/ drawings with alternatives and acceptance by POWERGRID | 10% of unit rate |
| b | On submission of tender documents including specification, schedule of items, BOQs, drawings, NIT cost estimates, BPS etc. as per specification & acceptance by POWERGRID/ Statutory authorities | 20% of unit rate |
| c | On submission of construction drawings and documents as per specification and approval of POWERGRID at various stages detailed below: |  |
| i | On approval of architectural building plans, elevations, sections and all structural drawings | 30% of unit rate |
| ii | On approval of all architectural drawings and balance structural drawings required for competition | 10% of unit rate |
| iii | On approval of all drawings for plumbing, sanitary, electrical, etc. including all other service drawings required for completion of entire project | 20% of unit rate |
| iv | On submission of final as built drawings completion certificate from statutory authorities/ POWERGRID | 10% of unit rate |
| 3 | Design & Drawing of Non-Residential Buildings |  |
| a | On submission of concept design/ drawings with alternatives and acceptance by POWERGRID | 10% of unit rate |
| b | On submission of tender documents including specification, schedule of items, BOQs, drawings, NIT cost estimates, BPS etc. as per specification & acceptance by POWERGRID/ Statutory authorities | 20% of unit rate |
| c | On submission of construction drawings and documents as per specification and approval of POWERGRID at various stages detailed below: |  |
| i | On approval of architectural building plans, elevations, sections and all structural drawings | 30% of unit rate |
| ii | On approval of all architectural drawings and balance structural drawings required for competition | 10% of unit rate |
| iii | On approval of all drawings for plumbing, sanitary, electrical, etc. including all other service drawings required for completion of entire project | 20% of unit rate |
| iv | On submission of final as built drawings completion certificate from statutory authorities/ POWERGRID | 10% of unit rate |
| 8 | Interior designing including layout of furniture, fixture, colour scheme and details of false ceiling, partitions, paneling etc. |  |
| a | On submission of concept design/drawings with alternatives and acceptance by POWERGRID. | 10% of unit rate |
| b | On submission of tender documents including specification, schedule of items, BOQs, drawings, NIT cost estimates, BPS etc. as per specification & acceptance by POWERGRID. | 30% of unit rate |
| c | On submission of construction drawings and documents as per specification and approval of POWERGRID at various stages detailed below: |  |
| i | On submission & approval by POWERGRID of all architectural construction/shop drawings for interior & finishing works required for completion. | 30% of unit rate |
| ii | On submission & approval by POWERGRID of all architectural construction/ shop drawings after incorporating various time to time revision for interior & finishing works required for completion of entire project. | 20% of unit rate |
| iii | On submission of final as built drawings completion certificate from statutory authorities/ POWERGRID | 10% of unit rate |