| S. No. | Clause Ref.No. | Existing Provision | Amended Provisions |
| --- | --- | --- | --- |
|  |  | Volume-I of the Bidding Documents |  |
| 1. | ITB 2.1 in BDS | Replace ITB 2.1 with following: This Invitation for Bids, issued by the Employer is open to all firms including company(ies), Government owned Enterprises registered and incorporated in India as per Companies Act, 1956, barring Government Department as well as foreign bidders/MNCs not registered and incorporated in India and those bidders with whom business is banned by the Employer. # Any Bidder ………. ……………………………................................... ………………………………………………….. Further, the firm has to be a ‘Class-I local supplier’ as defined under Public Procurement (Preference to Make in India) Order, 2017 issued by Department for promotion of Industry and Internal Trade (DPIIT), Ministry of Commerce and Industry, Government of India vide order dated 15/06/2017, its revision dated 16/09/2020 (PPP-MII Order) read in conjunction with ‘Public Procurement (Preference to Make in India) to provide for Purchase Preference (linked with local content) in respect of Power Sector’ order dated 28/07/2020 , 17/09/2020 and 16/11/2021 issued by Ministry of Power (MoP Order) and subsequent modifications/ amendments if any Presently, the local content requirement to categorize a supplier as ‘Class-I local supplier’ is minimum 60%. Firms who are not ‘Class-I local supplier‘ shall not be eligible to bid. Further, entities of …………... …………………………………………………………………… | Replace ITB 2.1 with following: This Invitation for Bids, issued by the Employer is open to all firms including company(ies), Government owned Enterprises registered and incorporated in India as per Companies Act, 1956, barring Government Department as well as foreign bidders/MNCs not registered and incorporated in India and those bidders with whom business is banned by the Employer. # Any Bidder ………. ……………………………................................... ………………………………………………….. Further, the firm has to be a ‘Class-I local supplier’ as defined under Public Procurement (Preference to Make in India) Order, 2017 issued by Department for promotion of Industry and Internal Trade (DPIIT), Ministry of Commerce and Industry, Government of India vide order dated 15/06/2017, its revision dated 16/09/2020 (PPP-MII Order) read in conjunction with ‘Public Procurement (Preference to Make in India) to provide for Purchase Preference (linked with local content) in respect of Power Sector’ order dated 16/11/2021 issued by Ministry of Power (MoP Order) and subsequent modifications/ amendments if any Presently, the local content requirement to categorize a supplier as ‘Class-I local supplier’ is minimum 60%. Firms who are not ‘Class-I local supplier‘ shall not be eligible to bid. The ‘Class-I local supplier’ shall give a self-certification in his bid in the given format, indicating the percentage of Local Content and certifying that the item offered meets the Local Content requirement for ‘Class –I local supplier’ and shall give details of the location(s) at which value addition is made. Further, in case of packages above Rs. 10 Cr, the ‘Class-I local supplier’ shall provide a certificate from statutory auditor or cost auditor of the company (in the case of companies) or from a practicing cost accountant or practicing chartered accountant (in respect of suppliers other than companies) giving the percentage of Local Content. Any false declaration regarding Local Content by the bidder shall be a transgression of Integrity Pact and action shall be taken in line with provisions of the Integrity Pact and in line with the provisions of the PPP-MII Order. Further, in case price reduction during e-RA, the ‘Class –I local supplier’ shall ensure that the item offered meets the Local Content requirement considering the revised prices. Further, entities of …………... …………………………………………………………………… |
| 2. | ITB 31.5 | Add new clause | Add a new sub clause ITB 31.5 as under: POWERGRID reserves the right to enter into separate contracts for GIS Substation Package SS-90 independent of each other as per the following: - Extn. of 765/400kV Nizamabad GIS substation including 765kV Bus ducts, Bushings, 400kV GIS bays etc. under Augmentation of Transformation Capacity in Southern Region. - (a) Extn. of 400/230kV Tuticorin-II GIS S/S for installation of 4th ICT & (b) Extn. of 400/230kV Tuticorin-II GIS S/S for installation of 5th ICT under Transmission System for Tirunelveli and Tuticorin Wind Energy Zone (Tamil Nadu) (5OOMW). - Extn. of 400kV Nizamabad GIS substation under Consultancy services to TSTRANSCO Accordingly, the terms and conditions as per the bidding documents shall be applicable independently to these separate contracts. |
| 3. | Clause 1.1 Appendix-1, TERMS AND PROCEDURES OF PAYMENT, Section-VI | 1.1 Supply of Goods Portion A. Interest Bearing Advance (Optional*): Ten percent (10%) of the Ex-works price component of Main Equipment/Materials (including Mandatory Spares), shall be paid as an interest bearing initial advance after signing the Contract Agreement and on submission of (a) Proforma invoice(s), (b) Advance Bank Guarantee for 110% (one hundred ten percent) of the amount of Advance, in line with GCC Clause 9.2, (c) Performance Securities in line with GCC Clause 9.3 and (d) Detailed PERT Network/Bar chart and its approval by the Employer. Provided further that Proforma Invoice(s) for advance payment along with all supporting documents is submitted by the Contractor to the Employer within 3 months from the date of Notification of Award. In case the Contractor does not submit the requisite documents including applicable Bank Guarantee(s)/Security(ies) within the aforesaid period, the advance shall not be payable. The Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. Note: * This payment is an optional payment. The Contractor has the option of taking the interest bearing initial advance or otherwise. Interest rate applicable on advance payment to the Contractor shall be at the rate equal to one year MCLR rate [One year Tenor rate p.a.] published by State Bank of India prevailing as on the date of drawal of advance. The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid. The interest will be charged considering proportionate adjustment of advance against progressive payment as per 1.1 (C.1) below. The interest shall be calculated on daily progressive balances outstanding as on the date of recovery/adjustment. It is the Employer’s understanding that as per extant provisions, GST is not payable on interest paid on the amount of Advance. The Contractor is, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account. Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest within 3 months from the end of the quarter in which adjustment of advance has been made for claiming refund from Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate. In case, the Contractor opts not to take interest bearing advance as above, it would be mandatory for him to submit the documents listed at Sl. No. (c) and (d) above within twenty eight (28) days of issuance of NOA. (The above is to be incorporated in case the Contractor has opted for the interest bearing initial advance, as declared by it in its bid in the relevant Attachment to Bid Form). B. It would be mandatory for contractor to fulfill the following conditions mentioned at as per terms & conditions of Contract and agreed work schedule: a) Approval of all designs, drawings & guaranteed technical particulars as identified in Technical Specifications, Volume-II of the Bidding Documents. b) Approval of all quality plans and sub-vendor list. c) Approval of type test reports in case type tests are not required to be repeated. C Progressive Payment Payment of the Ex-works price of Main Equipment/ materials (including Mandatory Spares) for each consignment shall be made progressively on certification of the Employer and on the basis of work performed using the following guidelines: C.1 Sixty percent (60%)** of the Ex-Works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid progressively on submission of documents indicated hereinunder: (a) Evidence of despatch (R/R or receipted L/R) (b) Contractor’s GST invoice, claim & packing list identifying contents of each shipment. (c) Insurance policy/certificate (d) Manufacturer’s/Contractor’s guarantee certificate of Quality. (e) Material Inspection Clearance Certificate (MICC) for despatch issued by the Employer’s representative and the Contractor’s factory inspection report. (f) Test certificate (g) the details of items, components, raw materials, services etc. procured/availed from MSEs, if any, for the preceding 6 months, in respect of all the contracts in the respective executing Region of POWERGRID as per format enclosed at Section VI, Forms, Volume-I of the bidding documents. (h) Value- addition certificate on half-yearly basis (Sep 30 and Mar 31), duly certified by the Statutory Auditors of the Domestic Manufacturer, that the claims of value-addition made for the product during the preceding 6 months are in accordance with the ‘Policy for providing preference to Domestically Manufactured Iron & Steel Products in Government Procurement’. ** In case, the Contractor opts not to take interest bearing initial advance or has opted to take interest bearing initial advance but the advance payment has become inadmissible for the reason specified in 1.1 A above, then this payment shall be 70% instead of 60%. C.2 Twenty percent (20%) of the Ex-works price of Main Equipment/ materials (excluding Mandatory Spares) shall be paid on receipt and storage at site and on physical verification and furnishing of necessary certificate by Employer’s representative. However, for Mandatory Spares, balance thirty percent (30%) payment of the Ex-works price component shall be released on receipt & storage of the same at site, physical verification and taking over by the Employer’s representative. D Final Payment Balance 10% (Ten percent) of the Ex-works price component of Main Equipment/Materials (excluding Mandatory Spares) shall be paid as per the following: - 5% (Five percent) on Successful completion of erection, testing and commissioning of individual bays. b) 5% (Five percent) on proof of submission of required number of reproducibles, O&M Manuals, approved drawings, data sheets, test report, pamphlets and manuals of mandatory spares, maintenance & testing equipment and on successful completion of erection, testing and commissioning of GIS bays and issuance of Taking Over Certificate. However, in case of delay in testing and commissioning & issuance of taking over certificate by Employer beyond six (6) months from the date of receipt of equipment at site, the last 10% of Ex-Works price of respective equipment shall be paid after issuance of a certificate by Employer’s representative that the equipment have been received in good condition and on submission of a bank guarantee of equivalent amount, which shall be kept valid initially for a period of twelve (12) months or until three (3) months after the expected date of commissioning (in case it is possible to anticipate the same), whichever is earlier, provided all other conditions as per above are complied with by the Contractor. If the commissioning does not take place within the validity period of BG, the validity of BG shall be extended from time to time. The bank guarantee shall, however, be released within one month of successful commissioning of the respective equipment by the Employer. | - Supply of Goods Portion A1. Interest Bearing Advance (Optional*): Ten percent (10%) of the Ex-works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid as an interest bearing initial advance after signing the Contract Agreement and on submission of (a) Proforma invoice(s), (b) Advance Bank Guarantee for 110% (one hundred ten percent) of the amount of Advance, in line with GCC Clause 9.2, (c) Performance Securities in line with GCC Clause 9.3 and (d) Detailed PERT Network/Bar chart and its approval by the Employer. Provided further that the Proforma Invoice(s) for advance payment along with all supporting documents is submitted by the Contractor to the Employer within 3 months from the date of Notification of Award. In case the Contractor does not submit the requisite documents including applicable Bank Guarantee(s)/Security(ies) within the aforesaid period, the advance shall not be payable. The Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. Note: * This payment is an optional payment. The Contractor has the option of taking the interest bearing initial advance or otherwise. Interest rate applicable on advance payment to the Contractor shall be at the rate equal to one year MCLR rate [One year Tenor rate p.a.] published by State Bank of India prevailing as on the date of drawal of advance. The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid. The interest will be charged considering proportionate adjustment of advance against progressive payment as per 1.1(B) below. The interest shall be calculated on the daily progressive balances outstanding as on the date of recovery/adjustment. It is the Employer’s understanding that as per extant provisions, GST is not payable on interest paid on the amount of Advance. The Contractor is, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account. Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest within 3 months from the end of the quarter in which adjustment of advance has been made for claiming refund from Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate. In case, the Contractor opts not to take interest bearing advance as above, it would be mandatory for him to submit the documents listed at Sl. No. (c), and (d) above within twenty-eight (28) days of issuance of NOA. (The above is to be incorporated in case the Contractor has opted for the interest bearing initial advance, as declared by it in its bid in the relevant Attachment to Bid Form). A2. Interest Bearing Engineering Advance (Optional**): Further advance of Ten percent (10%) of the Ex-works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid as an interest-bearing interim advance on: a) Approval of all designs, drawings & guaranteed technical particulars as identified in Technical Specifications, Volume-II of the Bidding Documents. b) Approval of all quality plans and sub-vendor list. c) Approval of type test reports in case type tests are not required to be repeated. d) Detailed invoice e) Submission of an unconditional & irrevocable Bank Guarantee in favour of the Employer for 110% (one hundred ten percent) of the amount of Interim Engineering Advance as per the proforma attached with Section-VI: Forms, Conditions of Contract, Volume-I of the Bidding Documents. The Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. Note: ** This payment is an optional payment. The Contractor has the option of taking the interest-bearing Engineering advance or otherwise. Interest rate applicable on advance payment to the Contractor shall be at the rate equal to one-year MCLR rate [One year Tenor rate p.a.] published by State Bank of India prevailing as on the date of drawal of advance. The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid. The interest will be charged considering proportionate adjustment of advance against progressive payment as per 1.1(B) below. The interest shall be calculated on the daily progressive balances outstanding as on the date of recovery/adjustment. It is the Employer’s understanding that as per extant provisions, GST is not payable on interest paid on the amount of Advance. The Contractor is, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account. Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest within 3 months from the end of the quarter in which adjustment of advance has been made for claiming refund from Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate. B Progressive Payment Payment of the Ex-works price of Main Equipment/ materials (including Mandatory Spares) for each consignment shall be made progressively on certification of the Employer and on the basis of work performed using the following guidelines: B.1 Fifty percent (50%)*** of the Ex-Works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid progressively on submission of documents indicated hereinunder: (a) Evidence of dispatch [Consignment Note (R/R or L/R)] (b) Contractor’s GST invoice, claim & packing list identifying contents of each shipment. (c) Insurance policy/certificate (d) Manufacturer’s/Contractor’s guarantee certificate of Quality. (e) Material Inspection Clearance Certificate (MICC) for despatch issued by the Employer’s representative and the Contractor’s factory inspection report (f) Test certificate (g) Additional performance securities, if required, as per Technical Specification. (h) the details of items, components, raw materials, services etc. procured/availed from MSEs, if any, for the preceding 6 months, in respect of all the contracts in the respective executing Region of POWERGRID as per format enclosed at Section VI, Forms, Volume-I of the bidding documents. (i) Value- addition certificate on half-yearly basis (Sep 30 and Mar 31), duly certified by the Statutory Auditors of the Domestic Manufacturer, that the claims of value-addition made for the product during the preceding 6 months are in accordance with the ‘Policy for providing preference to Domestically Manufactured Iron & Steel Products in Government Procurement’. *** In case, the Contractor opts not to take interest bearing initial advance {or has opted to take interest bearing initial advance but the advance payment has become inadmissible for the reason specified in 1.1 A1 above} and interest-bearing engineering advance then this payment shall be 70% instead of 50%. Further, in case, the Contractor opts not to take interest bearing initial advance, but takes interest bearing engineering advance, then this payment shall be 60% instead of 50% and in case, the Contractor opts to take interest bearing initial advance, but does not take interest bearing engineering advance, then this payment shall be 60%, instead of 50%. B.2 Twenty percent (20%) of the Ex-works price of Main Equipment/ materials shall be paid on receipt and storage at site and on physical verification and furnishing of necessary certificate by Employer’s representative. However, for Mandatory Spares, balance thirty percent (30%) payment of the Ex-works price component shall be released on receipt & storage of the same at site, physical verification and taking over by the Employer’s representative. C Final Payment Balance 10% (Ten percent) of the Ex-works price component of Main Equipment/Materials (excluding Mandatory Spares) shall be paid as per the following: - 5% (Five percent) on Successful completion of erection, testing and commissioning of individual bays. - 5% (Five percent) on proof of submission of required number of reproducibles, O&M Manuals, approved drawings, data sheets, test report, pamphlets and manuals of mandatory spares, maintenance & testing equipment and on successful completion of erection, testing and commissioning of all GIS bays and issuance of Taking Over Certificate. However, in case of delay in testing and commissioning & issuance of taking over certificate by Employer beyond six (6) months from the date of receipt of equipment at site, the last 10% of Ex-Works price of respective equipment shall be paid after issuance of a certificate by Employer’s representative that the equipment have been received in good condition and on submission of a bank guarantee of equivalent amount, which shall be kept valid initially for a period of twelve (12) months or until three (3) months after the expected date of commissioning (in case it is possible to anticipate the same), whichever is earlier, provided all other conditions as per above are complied with by the Contractor. If the commissioning does not take place within the validity period of BG, the validity of BG shall be extended from time to time. The bank guarantee shall, however, be released within one month of successful commissioning of the respective equipment by the Employer. In view of the above, Appendix 1 (Terms and Procedures of Payment) is revised and attached herewith. |
| 4. | Appendix –2 ,PRICE ADJUSTMENT, Section-VI | Appendix – 2 PRICE ADJUSTMENT The prices shall remain firm and fixed during the currency of the Contract. | Appendix – 2 (rev01) PRICE ADJUSTMENT 1. General 1.1 Prices for work and materials covered under the scope of this Specification shall be furnished by the bidder in the manner specified in the Bid Form & Price Schedules. The bidder shall quote base prices for the Ex-Works price component of the equipment/materials (Transformer & Insulating Oil, CVT, SA, PVC/XLPE insulated Power & Control Cables), the complete equipment procured as spares (Transformer, CVT, SA, PVC/XLPE insulated Power & Control Cables), Substation Structures and installation (including civil works) price component of the equipment/materials. These price components for certain equipment/ materials, as specified, shall be subject to price adjustment to reflect changes in the cost of labour and material components as per the provisions given below: 1.2 All Ex-Works Price Components for GIS equipment, Installation Hardware, Control and Relay Panels, PLCC Equipment, Wave Traps, Bus Post Insulators, Fire Protection Systems, Illumination System, L.T. Switchgear, IPS Aluminium Tube, Spares, Maintenance & Testing Equipment, for tower accessories such as danger plate, phase plate, circuit plates, number plate, anti-climbing device, span marker, bird guards, pipe, counterpoise earthing, obstruction lights, Flexible Copper Bond etc. and other items not specifically mentioned below shall remain firm and no price adjustment shall be applicable for the price components of these items.. 1.3 Other Charges viz. inland transportation, inland insurance, type test charges, computer studies (if any) & training charges survey, soil investigation & painting of towers etc. shall be firm and no price variation shall be payable for these components. 2. Ex-Works Price Component a. AIS Equipment: Capacitive Voltage Transformer / Surge Arrestor P1 = P0 x {0.15 + a x (A1/A0) + b x (B1/B0) + c x (C1/C0) + d x (D1/D0) + l x (L1/L0)} – P0 Where, P1 = Price adjustment amount expressed in currency of Bid, for each shipment. P0 = Ex-works price of the respective equipment, in currency of Bid. A, B, C, D & L = Published recognized price indices of raw materials used in the equipment and labour. a, b, c & d = Value of corresponding coefficients of raw materials used and the sum of which should be between 0.55 to 0.65. l = Coefficient for labour component. These coefficients are estimated percentage of major raw material/labour component involved in the Ex-works price of equipment such that their summation shall be equal to 0.85. b. PVC/XLPE Insulated Power and Control Cables P1 = P0 x {0.85 + 0.15 x (A1/A0)} – P0 + (M1 – M0) Where, P1 = Price adjustment amount per Km. of cable. P0 = Ex-works price per Km. of cable. A = Price index for PVC/XLPE as published by IEEMA. M1 – M0 = Change in metal component of the ex-works price of particular type & size of cable. Where, M = Weight in MT of metal per Km. of Cable x Price index of metal per MT as published by IEEMA. The Bidder has to specify in his Bid metal component per Km. for each type and size of cable. c. Sub Station Structures (including Bolts & Nuts) For Lattice & Pipe Structures (including washers, foundation bolts and Bolts & Nuts). P1 = P0 x {0.15 + 0.58x (A1/A0) + 0.16 x (B1/B0) + 0.11 x (L1/L0)} – P0 Where, P1 = Price adjustment amount expressed in currency of Bid, for each shipment. P0 = Ex-works price, in currency of Bid. A = Average Indicative Market Price of Steel Angles of size 50 x 50 x 6 mm of all cities in Rs/MT as published by Joint Plant Committee (JPC), inclusive of GST. B = Price indices of electrolytic zinc as published by IEEMA. L = Indian field labour index – namely All India average consumer price index for Industrial Workers (monthly) (Base: 2016= 100), as published by Labour Bureau, Shimla, Government of India (www.labourbureau.nic.in). These coefficients are estimated percentage of major raw material/labour component involved in the Ex-works price such that their summation shall be equal to 0.85. 2.1 i) Subscript '0' refers to indices as on thirty (30) days prior to date of opening of Bids, for materials & labour. ii) Subscript '1' refers to indices as applicable on: a) Sixty (60) days prior to the date of shipment for Labour. b) At the expiry of two third (2/3) period from the date of base index to the shipment of material in case of CVT and SA. c) Sixty (60) days prior to the date of shipment for materials in case of LT Transformer, Transformer, Cable and Substation Structure. 2.2 The total adjustment for CVT, SA, PVC/XLPE insulated Power & Control Cables and Sub-Station Structures (including bolts & nuts) shall be subject to a ceiling of ± 20% individually of respective Ex-Works price of CVT, SA, PVC/XLPE insulated Power & Control Cables and Sub-Station Structures (including bolts & nuts). The price adjustment for the Ex-Works price component for LT Transformer & Transformer for each shipment will not be subject to any ceiling. 2. Installation (including Civil Works) Price Component The formula for calculation of the monthly price adjustments for Installation (including civil works) price component shall be as under: A. Installation price component (including Civil Works but excluding ‘Supply & Placement of Reinforcement Steel’ and ‘Concreting’) ER1 = ER0 { 0.20 + 0.80 x (L1/L0) } – ER0 Where, ER1 = Price adjustment amount for the Installation price component (excluding supply & placement of steel and concreting) for each billing ER0 = Price for Installation (excluding supply & placement of steel and concreting and including civil works), done in billing period as established by the Contract. L = Indian field labour index – namely All India average consumer price index for Industrial Workers (monthly) (Base: 2016= 100), as published by Labour Bureau, Shimla, Government of India (www.labourbureau.nic.in). B. Supply and Placement of Reinforcement Steel: ER1 = ER0 [0.20 + 0.10 x (A1/A0) + 0.05 x (L1/L0) + 0.65 x (B1/B0)] – ER0 Where, ER1 = Price adjustment amount payable on price components of Supply and Placement of Steel. ER0 = Value of supply & placement of steel in billing period as established by Contract. A = Wholesale Price Index Number for `HSD’(Individual Commodity) (monthly) (Base: 2011-12=100), as published by Office of Economic Advisor, Ministry of Commerce & Industry(www.eaindustry.nic.in). L = Indian field labour index – namely All India average consumer price index for Industrial Workers (monthly) (Base: 2016= 100), as published by Labour Bureau, Shimla, Government of India (www.labourbureau.nic.in). B = Wholesale Price Index Number for `Manufacture of Basic Metals’(Group Item) (monthly) (Base: 2011-12=100), as published by Office of Economic Advisor, Ministry of Commerce & Industry(www.eaindustry.nic.in). C. Concreting ER1 = ER0 [0.20 + 0.20 x (A1/A0) + 0.10 x (L1/L0) + 0.30 x (B1/B0) + 0.20 x (C1/C0)] – ER0 Where, ER1 = Price adjustment amount payable on price components of concreting. ER0 = Value of concreting in billing period as established by Contract. A = Wholesale Price Index Number for `HSD’(Individual Commodity) (monthly) (Base: 2011-12=100), as published by Office of Economic Advisor, Ministry of Commerce & Industry(www.eaindustry.nic.in). L = Indian field labour index – namely All India average consumer price index for Industrial Workers (monthly) (Base: 2016= 100), as published by Labour Bureau, Shimla, Government of India (www.labourbureau.nic.in). B = Wholesale Price Index Number for `Manufacture of cement, lime and plaster’(Group Item) (monthly) (Base: 2011-12=100), as published by Office of Economic Advisor, Ministry of Commerce & Industry (www.eaindustry.nic.in) C = Wholesale Price Index Number for `Cutting, shaping and finishing of stone’(Group Item) (monthly) (Base: 2011-12=100), as published by Office of Economic Advisor, Ministry of Commerce & Industry(www.eaindustry.nic.in). 3.1 i) Subscript '0' will correspond to thirty (30) days prior to date of opening of Bids. ii) Subscript '1' will correspond to the month of billing for indices and average of the month for the exchange rate. 3.2 The total price adjustment amount for Installation (including civil works) price component shall not be subject to any ceiling whatsoever. 4. The Bidders are required to estimate and indicate the values of different coefficients for each of the items in the price variation formulae within the specified range such that their summation is as specified in the Bidding Documents. Where no value or ‘-’ or ‘shall be furnished later’ is specified against the coefficient, the same will be deemed to be zero and the fixed component would be suitably adjusted. If the values of all coefficients in price variation formulae indicated by the Bidder are within the specified range but their sum exceeds the summation specified in the Bidding Documents, the values of the coefficients shall be pro-rata adjusted such that the summation remains as per the provisions of the Bidding Documents. If the values of all coefficients indicated by the Bidder are within the specified range but their summation is less than the value specified in the Bidding Documents, the values of the coefficients as indicated by the Bidder shall be considered as such and the fixed component in the price variation formulae would be suitably adjusted. Further, if any of values of the coefficients indicated by the Bidder is out of the range specified in the Bidding Documents, the lower of the values, as indicated by the Bidder vis-à-vis lower value of the range for that coefficient specified in the Bidding Documents, shall be considered and the fixed component would be suitably adjusted. 5. The above price adjustment provision shall be invoked by either party subject to the following further conditions: a) For the purpose of Price Adjustment on ex-works price components of the equipment, the date of shipment for Goods shall mean scheduled date of shipment or actual date of shipment, whichever is earlier. Scheduled date of shipment will be ex-works date of dispatch, governed by the accepted PERT Network/Bar Chart. Similarly, for the purpose of Price Adjustment on Installation price component, the Billing period shall mean the billing period as per Contract time schedule i.e., the agreed Bar Chart or actual period, whichever is earlier. The Billing period for various Installation activities will be as per agreed Installation Bar Chart indicating monthly schedule of Installation activities for completion of works. However, when the Employer’s specific approval for advancement of shipment/installation activities has been obtained in such case the said advanced date shall be treated as the schedule date of shipment/installation activities for the purpose of working out the price adjustment payable. No price increase shall be allowed beyond the original delivery/ Installation dates unless specifically stated in the Time Extension Letter, if any, issued by the Employer. The Employer will, however, be entitled to any decrease in the Contract Price which may be caused due to lower price adjustment amount in case of delivery of Goods/ Installation beyond the original delivery/Installation dates. Therefore, in case of delivery of Goods/ Installation beyond the original delivery/ Installation dates, the liability of the Employer shall be limited to the lower of the price adjustment amount which may work out either on schedule date or actual date of dispatch of Goods/ Installation. b) In case IEEMA does not publish any of the price indices, as mentioned above, the Bidder shall indicate any nationally recognized published index for respective items and the source of the same shall be furnished in the Bid. c) In case of non-publication of applicable indices on a particular date, which happens to be the applicable date for Price Adjustment purposes, the published indices prevailing immediately prior to the particular date shall be applicable. d) If the Price Adjustment amount works out to be positive, the same is payable to the Contractor by the Employer and if it works out to be negative, the same is to be recovered by the Employer from the Contractor. e) The Contractor shall promptly submit price adjustment invoices for the supplies made/work done, positively within three (3) months from the date of shipment/ work done, whether it is positive or negative. In view of the above, Appendix 2 (Price Adjustment) is revised and attached herewith. |
|  | Volume-II of the Bidding Documents |  |  |
| 1. | Annexure-III, Section Project | Annexure-III, BREAK UP OF MANDATORY SPARES | ANNEXURE DELETED |
| 2. | Clause No. 9.6, Section-Project, Rev. 0 | STANDARD MANDATORY SPARES Annexure 10 Rev1, attached with Section GIS Rev5A, stand deleted. For GIS spare Annexure-III attached with Section: Project is to be referred only. | STANDARD MANDATORY SPARES Annexure 10 Rev1, attached with Section GIS Rev5A, stands deleted. |
| 3. | Clause No. 9.7 (new clause), Section-Project, Rev. 0 | Nil (New Clause added) | Mandatory spares: - Any equipment which is not supplied as main equipment or part of main equipment, mandatory spare for that is not applicable. - In case contractor offers circuit breaker, dis-connector, current transformer, SF6/Air Bushing etc. under main equipment of higher rating than equipment rating specified in the specifications, the mandatory spare of same higher rating offered by contractor identical to main equipment offered in the package shall be required to be supplied against spares without any cost implication to POWERGRID. - Under Mandatory Spare BPS item “220kV GIS- Single phase of Current Transformer (4 Cores) with associated enclosure and primary conductor complete in all respect”, The following shall be considered as Break-Up of Quantity of 2 Nos. specified in BPS: - 01 no. of 3000A Single phase of Current Transformer (4 Cores) with associated enclosure and primary conductor complete in all respect - 01 No. of 1600A Single phase of Current Transformer (4 Cores) with associated enclosure and primary conductor complete in all respect. |
| 4. | Clause No. 9.8 (new clause), Section-Project, Rev. 0 | Nil (New Clause added) | It is recognized that the Contractor may have standardized the GIS design/equipment rating based on the manufacturer’s standard practice. Alternate proposals, offering higher rating equipment (without additional cost implication), will also be considered provided such equipment meets the specified minimum designs rating, standard and performance requirements. |
| 5. | Clause No. 9.9 (new clause), Section-Project, Rev. 0 | Nil (New Clause added) | BPS item “3150A, 63KA, 1 SEC SINGLE PHASE 420KV SF6 TO AIR BUSHING” shall be considered inclusive of associated support structures along with necessary base plate & foundation bolts. |
| 6. | Clause No. 9.10 (new clause), Section-Project, Rev. 0 | New Clause added | For Portable Partial Discharge(PD) monitoring system in GIS: The paragraph under clause no. 27.4 of Section-GIS Rev-05A (i.e. It shall be capable for measuring PD in charged GIS environment as EHV which shall have bandwidth in order of 100 MHz–2GHz with possibility to select a wide range of intermediate bandwidths for best measurement results. The principle of operation shall be based on UHF principle of detection. The instrument should also be able to detect partial discharges in cable joints and terminations) is amended as follows: “It shall be capable for measuring PD in charged GIS environment as EHV which shall have bandwidth in order of 100 MHz–2GHz. The principle of operation shall be based on UHF principle of detection. The instrument should also be able to detect partial discharges in cable joints and terminations” |
| 7. | Annexure IV_GIS Module Description, Section-Project, Rev. 0 | Annexure IV_GIS Module Description | Annexure IV_GIS Module Description Rev.01 |
| 8. | Clause No. 9.11 (new clause), Section-Project, Rev. 0 | New Clause added | Clause 2.1 (a) of Section GTR, Rev-15 is amended as below: "All equipment/materials/items, as per Annexure-K (Rev 01), as applicable under present scope of works, shall be procured and supplied from domestic manufacturers only with Minimum Local Content for individual items as listed in the above annexure. Any imported equipment/material/item/parts/component (comprising of embedded systems) to be supplied under the contract shall be tested in the certified laboratories to check for any kind of embedded malware/trojans/cyber threats and for adherence to Indian Standards as per the directions issued by Ministry of Power/Govt. of India from time to time. In case of such import from specified “prior reference” countries, the requirement of prior permission from the Govt. of India including protocol for testing in certified and designated laboratories by Ministry of Power/Govt. of India shall also be complied with by the contractor. The bidder/contractor shall list out the products and components producing Toxic e-waste under the contract and shall furnish to the Employer the procedure of safe disposal at the time of closing of the contract." |
|  |  | Volume-III of the Bidding Documents |  |
| 1. | Bid Price schedule, Second Envelope | In view of the breakup of Mandatory spares [ref amendment under volume-II above], the Price Schedule has been revised and is enclosed herewith, which shall replace the previous Price Schedule of the Bidding Documents. NOTE: Bidder shall upload Price Schedule on PRANIT portal as per provisions under Sl. No. 39 in BDS, Section-III, Volume-I. |  |
| 2.. | Bid Form and Attachments, First Envelope | In view of the provisions of Interest Bearing Engineering Advance and Price Adjustment (ref amendment under volume-I above) , the Bid Form and Attachment has been revised and is enclosed herewith, which shall replace the previous Bid Form and Attachment of the Bidding Documents. |  |