Appendix-1(rev01)

TERMS AND PROCEDURES OF PAYMENT

In accordance with the provisions of GCC Clause 8 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules.  Payments will be made in the currencies quoted by the Bidder unless otherwise agreed between the parties. The Contractor may make applications for payment in respect of part deliveries as work proceeds.

1.	TERMS OF PAYMENT

In addition to the Conditions stipulated under GCC Clause 8, the following terms & Conditions will apply.

  - Supply of Goods Portion

A1. Interest Bearing Advance (Optional*): Ten percent (10%) of the Ex-works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid as an interest bearing initial advance after signing the Contract Agreement and on submission of

(a) Proforma invoice(s),

(b) Advance Bank Guarantee for 110% (one hundred ten percent) of the amount of Advance, in line with GCC Clause 9.2,

(c) Performance Securities in line with GCC Clause 9.3 and

(d) Detailed PERT Network/Bar chart and its approval by the Employer.

Provided further that the Proforma Invoice(s) for advance payment along with all supporting documents is submitted by the Contractor to the Employer within 3 months from the date of Notification of Award. In case the Contractor does not submit the requisite documents including applicable Bank Guarantee(s)/Security(ies) within the aforesaid period, the advance shall not be payable. The Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law.

Note: * This payment is an optional payment. The Contractor has the option of taking the interest bearing initial advance or otherwise.

Interest rate applicable on advance payment to the Contractor shall be at the rate equal to one year MCLR rate [One year Tenor rate p.a.] published by State Bank of India prevailing as on the date of drawal of advance. The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid. The interest will be charged considering proportionate adjustment of advance against progressive payment as per 1.1(B) below. The interest shall be calculated on the daily progressive balances outstanding as on the date of recovery/adjustment. It is the Employer’s understanding that as per extant provisions, GST is not payable on interest paid on the amount of Advance. The Contractor is, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account.

Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest within 3 months from the end of the quarter in which adjustment of advance has been made for claiming refund from Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate.

In case, the Contractor opts not to take interest bearing advance as above, it would be mandatory for him to submit the documents listed at Sl. No. (c), and (d) above within twenty-eight (28) days of issuance of NOA.

(The above is to be incorporated in case the Contractor has opted for the interest bearing initial advance, as declared by it in its bid in the relevant Attachment to Bid Form).

A2. Interest Bearing Engineering Advance (Optional**): Further advance of Ten percent (10%) of the Ex-works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid as an interest-bearing interim advance on:

a)	Approval of all designs, drawings & guaranteed technical particulars as identified in Technical Specifications, Volume-II of the Bidding Documents.

b)	Approval of all quality plans and sub-vendor list.

c)	Approval of type test reports in case type tests are not required to be repeated.

d)	Detailed invoice

e)	Submission of an unconditional & irrevocable Bank Guarantee in favour of the Employer for 110% (one hundred ten percent) of the amount of Interim Engineering Advance as per the proforma attached with Section-VI: Forms, Conditions of Contract, Volume-I of the Bidding Documents.

The Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law.

Note: ** This payment is an optional payment. The Contractor has the option of taking the interest-bearing Engineering advance or otherwise.

Interest rate applicable on advance payment to the Contractor shall be at the rate equal to one-year MCLR rate [One year Tenor rate p.a.] published by State Bank of India prevailing as on the date of drawal of advance. The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid. The interest will be charged considering proportionate adjustment of advance against progressive payment as per 1.1(B) below. The interest shall be calculated on the daily progressive balances outstanding as on the date of recovery/adjustment. It is the Employer’s understanding that as per extant provisions, GST is not payable on interest paid on the amount of Advance. The Contractor is, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account.

Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest within 3 months from the end of the quarter in which adjustment of advance has been made for claiming refund from Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate.

B	Progressive Payment

Payment of the Ex-works price of Main Equipment/ materials (including Mandatory Spares) for each consignment shall be made progressively on certification of the Employer and on the basis of work performed using the following guidelines:

B.1	Fifty percent (50%)*** of the Ex-Works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid progressively on submission of documents indicated hereinunder:

(a)	Evidence of dispatch [Consignment Note (R/R or L/R)]

(b)	Contractor’s GST invoice, claim & packing list identifying contents of each shipment.

(c)	Insurance policy/certificate

(d)	Manufacturer’s/Contractor’s guarantee certificate of Quality.

(e)	Material Inspection Clearance Certificate (MICC) for despatch issued by the Employer’s representative and the Contractor’s factory inspection report

(f)	Test certificate

(g) Additional performance securities, if required, as per Technical Specification.

(h) 	the details of items, components, raw materials, services etc. procured/availed from MSEs, if any, for the preceding 6 months, in respect of all the contracts in the respective executing Region of POWERGRID as per format enclosed at Section VI, Forms, Volume-I of the bidding documents.

(i) Value- addition certificate on half-yearly basis (Sep 30 and Mar 31), duly certified by the Statutory Auditors of the Domestic Manufacturer,  that the claims of value-addition made for the product during the preceding 6 months are in accordance with the ‘Policy for providing preference to Domestically Manufactured Iron & Steel Products in Government Procurement’.

***      In case, the Contractor opts not to take interest bearing initial advance {or has opted to take interest bearing initial advance but the advance payment has become inadmissible for the reason specified in 1.1 A1 above} and interest-bearing engineering advance then this payment shall be 70% instead of 50%. Further, in case, the Contractor opts not to take interest bearing initial advance, but takes interest bearing engineering advance, then this payment shall be 60% instead of 50% and in case, the Contractor opts to take interest bearing initial advance, but does not take interest bearing engineering advance, then this payment shall be 60%, instead of 50%.

B.2	Twenty percent (20%) of the Ex-works price of Main Equipment/ materials shall be paid on receipt and storage at site and on physical verification and furnishing of necessary certificate by Employer’s representative. However, for Mandatory Spares, balance thirty percent (30%) payment of the Ex-works price component shall be released on receipt & storage of the same at site, physical verification and taking over by the Employer’s representative.

C	Final Payment

Balance 10% (Ten percent) of the Ex-works price component of Main Equipment/Materials (excluding Mandatory Spares) shall be paid as per the following:

- 5% (Five percent) on Successful completion of erection, testing and commissioning of individual bays.

- 5% (Five percent) on proof of submission of required number of reproducibles, O&M Manuals, approved drawings, data sheets, test report, pamphlets and manuals of mandatory spares, maintenance & testing equipment and on successful completion of erection, testing and commissioning of all GIS bays and issuance of Taking Over Certificate.

However, in case of delay in testing and commissioning & issuance of taking over certificate by Employer beyond six (6) months from the date of receipt of equipment at site, the last 10% of Ex-Works price of respective equipment shall be paid after issuance of a certificate by Employer’s representative that the equipment have been received in good condition and on submission of a bank guarantee of equivalent amount, which shall be kept valid initially for a period of twelve (12) months or until  three (3) months after the expected date of commissioning (in case it is possible to anticipate the same), whichever is earlier, provided all other conditions as per above are complied with by the Contractor. If the commissioning does not take place within the validity period of BG, the validity of BG shall be extended from time to time. The bank guarantee shall, however, be released within one month of successful commissioning of the respective equipment by the Employer.

1.2	Type Test Charges- Not Applicable

Payment shall be made only for the type tests actually conducted as per the Contract.  The charges for type tests shall be paid along with the progressive payment on dispatch for the first consignment of Equipment for which the type test has been conducted and on fulfillment of  the following conditions.

(i) 	Successful completion of all the type tests as directed by the Employer,

(ii) 	Approval of the test results by the Employer

(iii)	Furnishing of GST invoice for the Equipment along with Type Test charges.

1.3	Supply of Services Portion:

Inland Transportation, In-transit insurance, Loading & unloading Charges

Inland transportation and In-transit insurance charges shall be paid to the Contractor on pro-rata basis, as per the unit rates indicated in the Contract Agreement, after receipt of materials/items at site and on presentation of the Bill of supply or any other documents prescribed under GST Law alongwith supporting documents by the Contractor. However, these charges will be subject to a limitation that the aggregate of all invoices does not exceed the total amount indicated in the Contract Agreement. It is the Employer’s understanding that as per extant provisions, on the charges for supply of services related to Inland transportation, In-transit insurance, loading and unloading by the Contractor to the Employer, GST is not payable. The Contractor is, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account.

1.4	Supply of Services Portion: Price Component for Installation

A.	Interest Bearing Advance (Optional) Ten percent (10%):

A.1	1st Installment: 5% (five) of the total Installation price component shall be paid as an interest bearing advance on submission of (a) Proforma invoice, (b) Establishment of Contractor’s site offices for preparatory to mobilisation for Installation establishment, (c) Advance Bank Guarantee for [{110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice(s)}] in line with GCC Clause 9.2 and (d) Performance Securities in line with GCC Clause 9.3.

A.2	2nd Installment: 5% (five) of the total Installation price component shall be paid as an interest bearing advance on submission of (a) Proforma invoice, (b) On start of equipment erection*, (c) Advance Bank Guarantee for [{110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice(s)}] in line with GCC Clause 9.2 and (d) A declaration by the contractor stating that 1st Installment (5%) of advance has been utilized against the mobilization works for the subject contract.

*	After the release of 2nd Installment, the rate of recovery of the advance shall be re-adjusted.

Provided further that the Proforma Invoice(s) for advance payment along with all supporting documents is submitted by the Contractor to the Employer within 3 months from the date of fulfillment of the requisite activities, as per the L2 network. In case the Contractor  does not submit the requisite documents including applicable Bank Guarantee(s)/ Security(ies) within the aforesaid period, the advance shall not be payable.

The Contractor, shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law.

Note: ^^: This payment is an optional payment. The Contractor has the option of taking the interest bearing advance or otherwise.

Interest rate applicable on advance payment to the Contractor shall at the rate equal to one year MCLR rate [One year Tenor rate p.a.] published by State Bank of India prevailing as on the date of drawal of advance. The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid. The interest will be charged considering proportionate adjustment of advance against progressive payment for the work done as per 1.4(B) below. The interest shall be calculated on the daily progressive balances outstanding as on the date of recovery/adjustment. It is the Employer’s understanding that as per extant provisions, GST is not payable on Interest paid on the amount of Advance. The Contractor may, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account.

(The above is to be incorporated in case the Contractor has opted for the interest bearing initial advance, as declared by it in its bid in the relevant Attachment to Bid Form).

Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest within 3 months from the end of the quarter in which adjustment of advance has been made for claiming refund from Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate.

In case, the Contractor opts not to take interest bearing advance as above, it would be mandatory for him to submit the document listed at Sl. No.  (d) above within twenty eight (28) days of issuance of NOA.

B	Progressive Payment

B1.	Seventy percent (70%)^^ shall be paid on completion the each of the items of Erection activity and on successful completion of quality check point involved in Installation, submission of the details of items, components, raw materials, services etc. procured/availed from MSEs, if any, for the preceding 6 months, in respect of all the contracts in the respective executing Region of POWERGRID as per format enclosed at Section VI, Forms, Volume-I of the bidding documents and certification by Employer’s representative and on submission of GST invoice.

^^ This payment shall be 75% instead of 70% in the following cases:

- the Contractor opts not to take 1st Installment interest bearing initial advance or has opted to take 1st Installment interest bearing initial advance but the advance payment has become inadmissible for the reason specified in 1.4 (A) above

- the Contractor opts not to take 2nd Installment interest bearing initial advance or has opted to take 2nd Installment interest bearing initial advance but the 2nd Installment advance payment has become inadmissible for the reason specified in 1.4 (A) above, and 1st  Installment interest bearing initial advance has been paid to the Contractor.

^^ This payment shall be 80% instead of 70% in case, the Contractor  opts not to take interest bearing initial advance or has opted to take interest bearing initial advance but the advance payment has become inadmissible for the reason specified in 1.4 (A) above.

Further, one of the conditions for release of first progressive payment / subsequent payment shall be submission of ‘Safety Plan’ alongwith all requisite documents in line with GCC clause on Safety Precaution and proforma provided in this Section – Sample Forms and Procedure and approval of the same by the Engineer In-Charge.

B2. 	Ten percent (10%) of Price Component for Installation shall be paid bay-wise on physical construction of individual bay including liquidation of defects/deficiencies on the Sub-station bay and certification of the same by Employer’s representative and on submission of GST invoice.

C.	Final Payment

Final 10% payment shall be made as follow:

5% (Five percent) of the Installation price component shall be paid on commissioning of individual bay and

balance 5% (Five percent) of the Installation price component shall be paid on commissioning of all GIS bays and issuance of Taking Over Certificate.

1.5	Training Charges- Not Applicable

Training Charges shall be paid on successful completion of training and on approval of the same by the Employer and on furnishing GST invoice for the Training Charges.

1.6	Payment towards Price adjustment

Any variation in Contract price due to price adjustment provision of Appendix-2 shall be effected on presentation of debit note/credit note, as prescribed under the GST law, supported by calculations as per formulae specified therein along with documentary evidence for different indices applicable for Price Adjustment.

1.6.1	Any increase in Contract price due to price adjustment provision shall be payable as follows:

Supply of Goods Portion:

90% (ninety percent) of the price adjustment amount for the respective shipment shall be paid on receipt of said shipment at site and issuance of Debit Note, as prescribed under the GST law, by the Contractor. Balance 10% (ten percent) of the price adjustment amount shall be paid alongwith the final payment.

Any interest on GST payable due to increase in Contract price due to price adjustment shall be to the Contractor’s account and Employer shall not reimburse any amount on this account.

Supply of Services Portion:

90% (ninety percent) of the price adjustment amount for the respective billing period shall be paid after certification by Employer’s representative for quantum of work done in the said billing period and issuance of Debit Note, as prescribed under the GST law, by the Contractor. Balance 10% (ten percent) of the price adjustment amount shall be paid alongwith the final payment.

Any interest on GST payable due to increase in Contract price due to price adjustment shall be to the Contractor’s account and Employer shall not reimburse any amount on this account.

1.6.2	For any reduction in Contract Price due to price adjustment provisions the Contractor shall issue ‘Credit note’, as prescribed under the GST law.  Further, the reduction in Contract Price shall be effected by recovering 100% of the reduction amount along with applicable GST, if any charged earlier, from Contractor’s invoices falling immediately due for payment or any other payments.

1.6.3    In case negative PV invoice is submitted by the contractor after the specified timeline as per the contract, interest shall be charged on said amount less provisional amount withheld on this account, if any, for the period elapsed beyond the specified timeline and date of submission of PV bill by the contractor. Rate of Interest shall be equal to one year MCLR rate [One Year Tenor rate p.a] published by State Bank of India as applicable on the last date of specified timeline. Further, the amount of interest worked out on negative PV shall be recovered from Contractor’s invoices falling immediately due for payment or any other payments under the contract.

1.7	Payment towards Taxes

Taxes and duties applicable as per Indian Tax laws, concerning Supply of Goods and Services in respect of transaction between the Employer and the Contractor, shall be reimbursed by the Employer as follows:

(a) 	GST, if applicable, on Advance payment shall   be reimbursed along with the Advance payment.

(b)  	In case of Ex-works supply of goods, GST shall be reimbursed along with progressive payment on dispatch.

(c)   	In case of Installation, the remaining GST (GST charged on invoice less GST on advance) shall be reimbursed along with Progressive payment on completion of Erection activity.

(d)    GST on type test shall be reimbursed after successful completion of the Type test and along with the progressive payment on dispatch for the first consignment of Equipment for which the type test has been conducted.

(e) 	GST on Training charges shall be reimbursed on successful completion of Training.

(f)  	100% GST reimbursable on account of increase in Contract price due to price adjustment shall be reimbursed along with the 90% payment of the Price adjustment amount.

All GST payment except GST applicable on Advance shall be against GST invoices/debit notes raised by the Contractor as specified under the GST Act and related Rules, Notifications, etc as notified by the Government in this regard. In the event that the Contractor fails to provide the invoice/debit note in the form and manner prescribed under the GST Act and Rules, the Employer shall not be liable to make any payment against such invoice/debit note. Reimbursement of GST payment against Advance payment shall be against proforma invoice(s). Further, the Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. Payment towards taxes & duties shall be released by the Employer directly to the Contractor.

2.	PAYMENT PROCEDURES

2.1	Method of Payment

The Employer shall make payments promptly within thirty (30) days of submission of an invoice/claim by the Contractor, complete in all respects and supported by the requisite documents and fulfillment of stipulated conditions, if any.

All invoices/claims shall be raised by the Contractors in the name of Owner acting through POWERGRID.

All payments to be made directly to the Contractor shall be made by the Employer though electronic payment mechanism (e-payment) for which necessary details shall be tied up during execution of the Contract. However, a request for payment to be released through cheque shall be considered on case to case basis and merit of the same.

Note:	Pro-rata shall refer to functionally complete part(s) of the facilities, for which unit rates are identified in the contract.

2.2	Bill Tracking System

Prior to submission of bills in physical form, the Contractor shall submit its bills using POWERGRID’s Vendor Bill Tracking System as per procedure detailed herein below. Further, the Contractor may also track the status of its bills using POWERGRID’s ‘On-line Vendor Bill Tracking System’. To use this system the Contractor is required to get itself registered once online at POWERGRID’s ERP Portal with the link URL (https://etender.powergrid.in). Once registered, the Contractor   may track status of bills submitted, passed and paid by POWERGRID’s Corporate Centre and Regional Office(s) under this Contract and other Contracts awarded on it by POWERGRID by following the method detailed herein below:

- Once registered, the Contractor can log-in to POWERGRID’s Vendor Bill Tracking System (BTS) with Vendor Log-In ID and Password.

- After login as at (a) above, Contractor  is required to make the entry on POWERGRID’s ERP Portal under the tab “Submit New Invoice” and shall fill all details along with the MSE status. Upon submission, a 16 digit unique BTS number will be generated and the Contractor will receive an automated e-mail forwarding the unique BTS number.

- The physical bills alongwith printed copy of e-mail received from BTS (unique BTS number) shall be submitted by the Contractor.

- On receipt of physical bill, concerned POWERGRID’s official shall online acknowledge the receipt of bill. This action will trigger an automated mail to the Contractor  intimating that the physical copy of the bill has been received and is under verification / processing. However, on receipt of incomplete bill and/or non-receipt of physical bill by POWERGRID official, the incomplete bills/ digital entry in BTS ( as the case may be) shall be returned to the Contractor by POWERGRID, which can be viewed under the tab “Invoice Returned”.

- The day the payment is made, a mail stating the “Bill number, net payment amount and details of the bank from where the payment has been made” will be sent to the Contractor.

- The status of Bill submitted by the Contractor can be checked through the BTS number under tab “Invoice Submitted”.