| S. No. | Clause | Provision of Bidding Documents | Bidder’s Query | POWERGRID's Reply |
| --- | --- | --- | --- | --- |
|  | ITB 22.5 in BDS, Vol-I of bidding documents | The prices shall be in accordance with the following: Fixed Price. Prices quoted by the Bidder shall be fixed during the Bidder’s performance of the contract and not subject to variation on any account. A bid submitted with an adjustable price quotation will be treated as non-responsive and rejected | Price variation on account of labor index is a standard accepted practice within Powergrid including for existing maintenance contract and was also a part of previous ULDC schemes. Hence We request to please include this clause to support bidder with managing inflation. We are sharing a similar scope contract document for your reference which includes PV clause. | Refer Amendment No-II |
|  | GCC 1.1(e) & 1.1(ee), Vol-I of Bidding documents | The Time for successful Completion of subject package shall be as per the following details: 18 Months for all utilities | 18 Months Completion time is not practical due to below reasons: 1. NRLDC Upgradation project cover wider Geographical area. 2. Site Surveys, Design & Engineering itself is time taking job as it covers various constiuents stake 3. Lead time of OEMs (especially Switches, Routesr are high to the tune of 6-8 months) and hence effect the FAT and subsequent execution schedule 4. Being a technology oriented solution (including cyber security solution) needs reasonable time We request to kindly extend the completion schedule to 30 months | Provisions of Bidding documents remain unchanged. |
|  |  |  | As per the tender document, Time for Completion of the project is given as 18 months. Considering the size of the project 18 months duration insufficient. We propose the duration to be extended upto 30 months w.r.t Time For Completion. |  |
|  |  |  | Kindly consider time for completion as at least 24 months considering size and activities of the project. |  |
|  | ITB 9.3 (b), Vol-I of Bidding documents | For this package bids from joint venture is not permitted and accordingly Form:14 & Form:15 are not applicable. Further, other references of Joint Venture in the Bidding Documents including references in Section-VI: Sample Forms and Procedures are not applicable. | We are an Indian SME having experience and expertise to execute & implement SCADA-EMS Projects & Systems as System Integrators & Technology Implementors. Considering the Make-In-India initiative by Government of India and the considerable large size of the project (Rs. 1152.81 Crore without taxes), we request you to permit JV/Consortium of companies to participate in this tender in addition to the Technical Collaborator (SCADA-EMS Software OEM). | Provisions of Bidding documents remain unchanged. |
|  | ITB 37.1, Vol-I of Bidding documents | … For the purpose of the aforesaid, the ‘Indicative Estimated Cost for e-RA’ is Rs. 1152.81 Crore; … | Kindly confirm if the estimated cost is including taxes or excluding taxes. | Provision of Bidding documents are amply clear. |
|  | ITB 1.1, Vol-I of Bidding documents | The Employer for; NRLDC, HP SLDC, Balance 8 SLDCs … | Kindly confirm that all the approvals will be accorded by Powergrid only and no separate approvals from individual Employers will be required. | Provision of Bidding documents are amply clear. |
|  | GCC 24.3, SCC, Vol-I of Bidding documents | Replacement of Battery bank due to poor capacity: The Contractor shall be responsible for the replacement of faulty battery cells during entire period of contract (including extension of Comprehensive Maintenance contract, if any). Irrespective of the design/expected life of the supplied batteries, replacement of faulty batteries and or entire battery bank up to the completion of one year DLP and 6 years AMC period including extension of contract, if any, shall be in the scope of the contractor, without any cost implication to the Owner. | The Execution + DLP + AMC period is minimum 8.5 years as per RFP and is about 10 years practically. Estimating battery prices for such long period will not be possible for bidders. We request you to consider procurement of such items at your own cost after DLP (1 year) + AMC (2 years) or permit price variation as per reference prices at the time of bidding. | Provisions of Bidding documents remain unchanged. |
|  | GCC 33.2.3, Vol-I of Bidding documents | Percentage for the Change Proposal under this Clause shall be limited to Fifteen (15) percent. | Kindly confirm that the percent variation will be applicable to individual item quantities and not based on price of the entire contract. | Provisions of Bidding documents are amply clear and remain unchanged. |
|  | GCC 10.11, Vol-I of Bidding documents | Taxes and Duties : Statutory variation is allowed and equitable adjustments will be made in the contract price. However it is also mentioned in sub clause no. 10.11 (last para) that : In respect of raw materials, intermediary components etc and the taxes, duties & levies applicable locally, neither the Employer nor the Contractor shall be entitled to any claim arising due to increase or decrease in the rate of Tax, introduction of a new Tax or abolition of an existing Tax in the course of the performance of the Contract. | In Sub clause 10.11, 2nd last para talks about equitable adjustment is possible in case of changes in taxes and duties however in the last para it is mentioned that taxes, duties & levies applicable locally, any change in the tax/ introduction of new tax can not be claimed during performance of the contract. Thus, it contradicts. Kindly confirm whether equitable adjustment in the contract price is allowed in case of any statutory variations during the performance of the contract. | Provision of Bidding documents are amply clear |
|  | GCC 18.3.3.17, Vol-I of Bidding documents | The Contractor shall deploy one dedicated Safety Staff(s) for every 200 kms of a Transmission Line Project. In case, the Contractor fails to deploy Qualified Safety Officer(s)/Safety Staff(s) under each Contract, as specified, then the Contractor shall be responsible for payment of a sum of Rs. 15,00,000/- per quarter till the Safety Officer(s)/Safety Staff(s) is deployed, to be deposited with the Employer, which will be retained in the Safety Corpus Fund pursuant to GCC Sub-Clause 18.3.3.26 | This clause is applicable to transmission line project and hence the same is not applicable to this project which is a control center project in a controlled environment and hence we request you to delete / amend the clause accordingly. | Provisions of Bidding documents are amply clear and remain unchanged. |
|  | GCC 18.3.3.24, Vol-I of Bidding documents | If the Contractor does not take adequate safety precautions and/or fails to comply with the Safety Rules as prescribed by the Employer or under the applicable law for the safety of the equipment and plant or for the safety of personnel or the Contractor does not prevent hazardous conditions which cause injury to his own employees or employees of other Contractors or Employer‟s employees or any other person who are at Site or adjacent thereto, then the Contractor shall be responsible for payment of a sum as indicated below to be deposited with the Employer, which will be passed on by the Employer to such person or next to kith and kin of the deceased: a. Fatal injury or accident causing death : Rs. 15,00,000/- per person b. Major injuries or accident causing 25% or more permanent disablement : Rs. 5,00,000/- per person | We follow adequate safety measures and rules during project execution. Further, we have a master insurances policies covering our employees including third party employeed by us. However employer's employees are not covered under the policy. Accordingly, we request you to take into consideration this aspect and delete this clause. | Provisions of Bidding documents remain unchanged. |
|  | GCC 18.3.3.25, Vol-I of Bidding documents | Notwithstanding above, the Contractor shall also be responsible for payment of sum as indicated below additionally which shall be deposited in Safety Corpus Fund pursuant to GCC Sub-Clause 18.3.3.26 a. Upon 1st Fatal Accident due to negligence by the Contractor Rs. 50,00,000/- b. Upon 2nd Fatal Accident due to negligence by the Contractor Rs. 75,00,000/- c. Upon 3rd Fatal Accident due to negligence by the Contractor Rs. 1,00,00,000/- d. Re-occurrence of Fatal Accident even after 3rd Fatal Accident due to negligence by the Contractor Rs. 1,00,00,000/- per fatal accident | We will be taking required insurances for our employees as well as third party employees and thus they are covered under the policy in case of any emergencies. Accordingly this clause should not be applicable and we request Powergrid to delete this clause. | Provisions of Bidding documents remain unchanged. |
|  | GCC 18.3.3.26, Vol-I of Bidding documents | The amount paid/ recovered from the Contractor on account of noncompliance to Safety measures shall be deposited in the „Safety Corpus Fund‟, if not specified otherwise, established by the Employer. The „Safety Corpus Fund‟ shall be used for augmentation of Safety measures in construction works, capacity building of workers, development of working conditions of workers like providing tents/ mobile toilets/ caravans, safety tools & plants etc. and undertaking such other activities which will facilitate in reducing the accidents. However, the Contractor shall have no claim in this regard and the Employer shall be sole judge in this regard. | This is not the transmission line project. This project will be a control center project in a controlled environment and hence this clause will not be applicable to us. Further we will be taking required safety precautions and related insurances for our employees including third party insurances, we request Powergrid to delete this clause. | Provisions of Bidding documents remain unchanged. |
|  | GCC 36.2.6, Vol-I of Bidding documents | If the Employer completes the Facilities, the cost of completing the Facilities by the Employer shall be determined. If the sum that the Contractor is entitled to be paid, pursuant to GCC Sub-Clause 36.2.5, plus the reasonable costs incurred by the Employer in completing the Facilities, exceeds the Contract Price or the entire Facilities if entire Facilities have been completed or the price for part of the Facilities if part of the Facilities have been completed, the Contractor shall be liable for such excess. If such excess is greater than the sums due the Contractor under GCC Sub-Clause 36.2.5, the Contractor shall pay the balance to the Employer, and if such excess is less than the sums due the Contractor under GCC Sub-Clause 36.2.5, the Employer shall pay the balance to the Contractor. For facilitating such payment the Employer shall encash the Bank Guarantees of the Contractor available with the Employer and retain such other payments due to the Contractor under the Contract in question or any other Contract that the Employer may have with the Contractor. The Employer and the Contractor shall agree, in writing, on the computation described above and the manner in which any sums shall be paid. | In the 2nd last para under sub clause no. 36.2.6, We request Powergrid to delete the below lines. : For facilitating such payment the Employer shall encash the Bank Guarantees of the Contractor available with the Employer and retain such other payments due to the Contractor under the Contract in question or any other Contract that the Employer may have with the Contractor. We request Powergrid to do the adjustment of dues for this contract from the same contract and not with any other contract. | Provisions of Bidding documents remain unchanged. |
|  | 1.1, Appendix-I Terms of Payment, Section-VI, Vol-I of Bidding documents | Terms of payment: A. Interest Bearing Advance (Optional*): Ten percent (10%) | We request Powergrid to kindly provide interest free advance | Provisions of Bidding documents remain unchanged. |
|  | B.1, Appendix-I Terms of Payment, Section-VI, Vol-I of Bidding documents | If Advance is not opted: For SW : 30% pro-rata after FAT, 55% pro-rata after Field Test , 15% against Operational acceptance For HW : 70% pro-rata after shipment, 15% pro-rata on receipt of equipment at site (incl. spares) , 15% against Operational acceptance | If Advance is not opted, we request Powergrid to accept the below Terms of Payment : For SW : 65% pro-rata after FAT, 30% pro-rata after Field Test , 5% against Operational acceptance For HW : 75% pro-rata after shipment, 20% pro-rata on receipt of equipment at site (incl. spares) , 5% against Operational acceptance | Provisions of Bidding documents remain unchanged. |
|  | Bid Security Form, Section – VI, Vol-I of bidding documents | BID SECURITY FORM (Not Applicable) | Although the form is given in the sample forms, it is mentioned as Not Applicable. Thus, we understand that EMD in the form of Bid security is not applicable to this tender. Kindly confirm. | Bidders are requested to refer ITB Clause 24.1 which is amply clear |
|  | Article 4. Appendices, Section – VI: Samples Forms and Procedures, Vol-I of bidding documents | As per Section VI, page no. 22 it is mentioned about Integrity Pact as "[^ to be appended at the Stage of Contract Award.]. | Please clarify when to submit the Integrity Pact . Whether at the stage of bid or at the time of award of contract ? | Bidders are requested to refer ITB Clause 9.3(l) which is amply clear |
|  | ITB 19.2, Vol-I of Bidding documents | 19.2 Bidders are not allowed to form joint venture(s) or consortium (consortia) with other bidders, nor change the partner or structure of the joint venture or consortium if the Bidder in the First Stage was a joint venture or consortium. | Kindly Confirm whether the consortium of 2 or more firms is allowed for participation in this tender | Provisions of Bidding documents are amply clear |
|  | ITB 9.3 (b), Vol-I of Bidding documents | For this package bids from joint venture is not permitted and accordingly Form:14 & Form:15 are not applicable. Further, other references of Joint Venture in the Bidding Documents including references in Section-VI: Sample Forms and Procedures are not applicable. |  |  |
|  | GCC 22.8.1, Vol-I of Bidding documents | 22.8.1 At the end of the Defect Liability Period, the Contractor's Liability ceases except for latent defects. The Contractor's liability for latent defects warranty shall be limited to period of ten (10) years from the end of Defect Liability Period. For the purpose of this clause, the latent defects shall be the defects inherently lying within the material or arising out of design deficiency, which do not manifest themselves during the Defect Liability Period defined in this GCC Clause 22, but later. | Referring to the previous contracts of similar nature, The Contractor's liability for latent defects warranty shall be limited to period of three (3) years from the end of Defect Liability Period. Request you modify the clause accordingly | Refer Amendment No-II |
|  | GCC 22.8.1, Vol-I of Bidding documents | 22.8 If the Facilities or any part thereof cannot be used by reason of such defect and/or making good of such defect, the Defect Liability Period of the Facilities or such part, as the case may be, shall be extended by a period equal to the period during which the Facilities or such part cannot be used by the Employer because of any of the aforesaid reasons. Upon correction of the defects in the Facilities or any part thereof by repair/replacement, such repair/replacement shall have the Defect Liability Period extended by a period mentioned in GCC Sub-Clause 22.2 from the time of such replacement/repair of the facilities or any part thereof. | We will replace/ repair the part / facility as the case may be however re-warranty and extension of DLP on the replaced part/ facility is not acceptable. Request you to kindly modify the clause accordingly. | Provisions of bidding documents remain unchanged |