| Sl. No | Clause Ref. No. | Existing provision | Amended as |
| --- | --- | --- | --- |
| Volume-I of the bidding documents |  |  |  |
|  | Appendix-1 (Terms and Procedures of Payment), Sample Forms and Procedures, Section-VI | Appendix-1 TERMS AND PROCEDURES OF PAYMENT In accordance with the provisions of GCC Clause 8 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules. Payments will be made in the currencies quoted by the Bidder unless otherwise agreed between the parties. The Contractor may make applications for payment in respect of part deliveries as work proceeds. 1. TERMS OF PAYMENT In addition to the Conditions stipulated under GCC Clause 8, the following terms & Conditions will apply. - Supply Portion …………………………………… B Progressive Payment …………………………………… B.1 Fifty percent (50%)^ of the Ex-Works price component … … … … … … … … … …………………. B.2 Twenty percent (20%) of the Ex-works price of Main Equipment/ materials … … … … … … … … … … … … … … … 2. PAYMENT PROCEDURES 2.1 Method of Payment … …. …. ….. … …. …. …. 2.2 Bill Tracking System … …. …. ….. … …. …. …. | Appendix-1 TERMS AND PROCEDURES OF PAYMENT In accordance with the provisions of GCC Clause 8 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules. Payments will be made in the currencies quoted by the Bidder unless otherwise agreed between the parties. The Contractor may make applications for payment in respect of part deliveries as work proceeds. 1. TERMS OF PAYMENT In addition to the Conditions stipulated under GCC Clause 8, the following terms & Conditions will apply. - Supply Portion ……………………………………. B Progressive Payment # …………………………………… B.1 Fifty percent (50%)^ of the Ex-Works price component … … … … … … … … … …………………. B.2 Twenty percent (20%) of the Ex-works price of Main Equipment/ materials … … … … … … … … … … … … … … … # Percentage of Progressive Payment shall be suitably adjusted in case of unbalanced/ front loaded bid as per the methodology brought-out at sl. No. 2.3 below. … …. …. ….. … …. …. …. 2. PAYMENT PROCEDURES 2.1 Method of Payment … …. …. ….. … …. …. …. 2.2 Bill Tracking System … …. …. ….. … …. …. …. 2.3 PAYMENT PROCEDURES IN CASE OF UNBALANCED / FRONT LOADED BID a. A bid shall be considered front loaded or unbalanced, if the percentage of Services component (Installation, civil works and F&I) to Total Contract Price (Supply component + Services component) quoted by the bidder is less than 20%. b. In the event of award on the bidder who have submitted unbalanced/front loaded bid, the percentage of Progressive payment against Supply of Goods portion (refer sl. No. 1.1 above) shall be deferred by the percentage by which the percentage of the Services price components in the bid less than the percentage specified at 2.3 a above in the bidding documents. No interest shall be payable on the deferred amount. The aforesaid deferred amount shall be paid on pro-rata basis upon completion of installation of the respective item and its certification by the Project Manager. No interest shall be payable on the deferred amount. Price Variation and Quantity variation shall continue to be governed by the unit price quoted by the bidder. |
|  | ITB 9.3(c), Section-II: ITB, Vol.-I of the Bidding Documents | Attachment 3: Bidder’s Eligibility and Qualifications (Uploading of Scanned Copies of documentary evidence in support of Bidder’s qualification. In case of Joint Venture bid, submission of Hard Copy in ‘Original’ of the JV Agreement and POA for JV) ……………… ……………… | Supplementing the ITB clause 9.3(c) with the following in Section-BDS: POWERGRID has develop a data-base of Qualification Requirement (QR) data named as ‘Information on Record’ (hereinafter referred to as the ‘IoR portal’) of different bidders for certain categories of its procurement to minimize the time taken to ascertain QR compliance. Bidders have given viewing rights for their own data on the portal. The link for accessing IoR portal is available at POWERGRID’s website [www.powergrid.in]. In such case, over and above the documents submitted by the bidders in their bids, the above data-base may also be considered. Notwithstanding the above, bidders may please note that the maintenance of any information of any bidder on IoR portal should not be construed that the bidder is considered meeting the Qualification Requirement (QR). The evaluation of the bids inter-alia compliance to QR of the bidders shall be carried out as per provisions of the Bidding Documents. |
|  | Attachment-3 (QR) to First Envelope Bid Form, Vol.-III of the Bidding Documents | Attachment-3 (QR) (Qualifying Requirement Data) …………………… Dear Sir, In support of the Qualification Requirement (QR) for bidders, stipulated in Annexure-A (BDS) of the Section-III (BDS), Volume-I & additional information required as per ITB Clause 9.3(c) of the Bidding Documents, we furnish herewith our QR data/details alongwith other information,………. ………………… | Attachment-3 (QR) (Qualifying Requirement Data) …………………… Dear Sir, In support of the Qualification Requirement (QR) for bidders, stipulated in Annexure-A (BDS) of the Section-III (BDS), Volume-I & additional information required as per ITB Clause 9.3(c) of the Bidding Documents, we furnish herewith our QR data/details alongwith other information,………. ………………… 6.0 In addition to the data/details furnished as above, the information available at ‘Information on Record’ (IoR) portal of POWERGRID may also be considered as our submission for purpose of QR compliance. |
|  | Vol.-III of the Bidding Documents | Existing File “01_Attachment-3(QR)” | In view of the Sl. No. 3 above, the existing file “01_Attachment-3(QR)” Stands replaced with “01_Attachment-3(QR)_rev01” |