| S. No. | CLAUSE | EXISTING PROVISION | Amended provision |
| --- | --- | --- | --- |
| 1.0 | Appendix-1 (Terms and Procedures of Payment), Sample Forms and Procedures, Section-VI | Appendix-1 TERMS AND PROCEDURES OF PAYMENT In accordance with the provisions of GCC Clause 8 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules. Payments will be made in the currencies quoted by the Bidder unless otherwise agreed between the parties. The Contractor may make applications for payment in respect of part deliveries as work proceeds. 1. TERMS OF PAYMENT In addition to the Conditions stipulated under GCC Clause 8, the following terms & Conditions will apply. - Supply Portion B Progressive Payment …………………………………… B.1 Fifty Five Percent (55%)** of the Ex-Works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid progressively on submission of documents indicated hereinunder:… … … … … … … … … …………………. B.2 Fifteen Percent (15%) of the Ex-works price of Main Equipment/ materials (including Mandatory Spares) shall be paid on receipt and storage at site … … … … … … … … … … … … … … … 2. PAYMENT PROCEDURES 2.1 Method of Payment … …. …. ….. … …. …. …. 2.2 Bill Tracking System … …. …. ….. … …. …. …. | Appendix-1 TERMS AND PROCEDURES OF PAYMENT In accordance with the provisions of GCC Clause 8 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules. Payments will be made in the currencies quoted by the Bidder unless otherwise agreed between the parties. The Contractor may make applications for payment in respect of part deliveries as work proceeds. 1. TERMS OF PAYMENT In addition to the Conditions stipulated under GCC Clause 8, the following terms & Conditions will apply. - Supply Portion B Progressive Payment# …………………………………… B.1 Fifty Five Percent (55%)** of the Ex-Works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid progressively on submission of documents indicated hereinunder … … … … … … … … … …………………. B.2 Fifteen Percent (15%) of the Ex-works price of Main Equipment/ materials (including Mandatory Spares) shall be paid on receipt and storage at site … … … … … … … … … … … … … … … # Percentage of Progressive Payment shall be suitably adjusted in case of unbalanced/ front loaded bid as per the methodology brought-out at sl. No. 2.3 below. … …. …. ….. … …. …. …. 2. PAYMENT PROCEDURES 2.1 Method of Payment … …. …. ….. … …. …. …. 2.2 Bill Tracking System … …. …. ….. … …. …. …. 2.3 PAYMENT PROCEDURES IN CASE OF UNBALANCED / FRONT LOADED BID - A bid shall be considered front loaded or unbalanced, if the percentage of Services component (Installation, civil works, F&I and Training/AMC, if any) to Total Contract Price (Supply component including Offshore + Services component including AMC Contracts) quoted by the bidder is less than 24.1%. - In the event of award on the bidder who have submitted unbalanced/front loaded bid, the percentage of Progressive payment against Supply of Goods portion (refer sl. No. 1.1 above) shall be deferred by the percentage by which the percentage of the Services price components in the bid less than the percentage specified at 2.3 a above in the bidding documents. No interest shall be payable on the deferred amount. The aforesaid deferred amount shall be paid on pro-rata basis upon completion of installation of the respective item and its certification by the Project Manager. No interest shall be payable on the deferred amount. Price Variation and Quantity variation shall continue to be governed by the unit price quoted by the bidder. |
| 2 | GCC 34.1 | The Time(s) for Completion specified in the SCC shall be extended if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: - any Change in the Facilities as provided in GCC Clause 33 - any occurrence of Force Majeure as provided in GCC Clause 32 - any suspension order given by the Employer under GCC Clause 35 hereof or reduction in the rate of progress pursuant to GCC Sub-Clause 35.2 or - any changes in laws and regulations as provided in GCC Clause 31 or - any other matter specifically mentioned in the Contract by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor. | The Time(s) for Completion specified in the SCC shall be extended if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: - any Change in the Facilities as provided in GCC Clause 33 - any occurrence of Force Majeure as provided in GCC Clause 32 - any suspension order given by the Employer under GCC Clause 35 hereof or reduction in the rate of progress pursuant to GCC Sub-Clause 35.2 or - any changes in laws and regulations as provided in GCC Clause 31 or - any other matter specifically mentioned in the Contract by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor. Notwithstanding above, in the interest of timely project completion, the Employer may, with the consent of Contractor, provide additional Labour to expedite activities related to Foundation, Erection & Stringing. However, in such case, the additional labour deployed shall be under the overall obligation of the Contractor inter-alia including risk & responsibilities thereof and all Contractual provisions shall apply thereto except for GCC Clause 18.1.3(a) and GCC Clause 18.1.3(b). The modality to be adopted for providing such additional labour is as follows: - - The Project Manager, by written notice to the Contractor, may offer to provide additional labour to Contractor for expediting timely completion of the activities related to foundation, erection & stringing. - The Contractor, as soon as possible but not later than 15 days after receiving the Project Manager’s offer as per i) above, may consent to utilise such labour for the Facilities. - The offer and acceptance as above shall be in writing. - The expenditure incurred by the Employer for providing such additional Labour shall be recovered from the Contractor from their monthly running bills. However, the recovery amount in such case shall be limited to the value worked out as under: Activity; Tentative rate of the activity. Foundation; Excavation: Rs 47 (per Cu m)​ Concreting: Rs 1,442 (per Cu m ) ​ Reinforcement Steel -Rs. 18,195/- per MT. Tower Erection; Rs 4,127 (per MT)​. Stringing; Rs 82,702/-Per Bay). - Such expenditure incurred on providing additional labor shall however not be construed as Facilitation in line with GCC Clause 36B hereof. - If the Contractor is not satisfied with the workmanship of the additional Labour provided as per above, he shall by notice to the Project Manager, ask for partial/full replacement of the deployed labour. - Upon receipt of Contractor’s notice as per vi) above, the Project Manager shall as soon as possible, provide replacement of labour to the Contractor. |
| 3. | ITB 9.3(ee), Section-II: ITB, Vol.-I of the Bidding Documents | - | Add new clause ITB 9.3(ee) in Section: BDS: (ag) Attachment-30: Declaration by the bidder for Acknowledgement and Acceptance of ‘Supplier Code of Conduct’ The ‘Supplier Code of Conduct’. is attached as Appendix-III to the Special Conditions of Contract. |
| 4. | ITB 21.1, Section-III: BDS, Vol.-I of the Bidding Documents | Replacing first Para of ITB clause 21.1 with the following: During bid evaluation, the Employer may, at its discretion, ask the Bidder for a clarification of its bid. In case of erroneous/non submission of documents related to/identified in ITB Sub-Clause 9.3 (b), (o), (s), (t), (u), (v), (w), (x), (y), (z), (aa), (bb), (cc) and (dd) or Deed of Joint Undertaking pursuant to ITB Sub-Clause 9.3 (c) & (e) or the complete annual reports together with Audited statement of accounts pursuant to ITB Sub-Clause 9.3 (c), Online Payment Acknowledgement towards the cost of Bidding Documents pursuant to ITB 5.4, documentary evidence with regard to registration with designated Authority of GoI under the Public Procurement Policy for MSEs pursuant ITB 5.5, documentary evidence with regard to MSE owned by SC/ST entrepreneurs or women in line with Public Procurement Policy for MSEs pursuant to ITB 9.3(p), required to be submitted by the Bidder as per the provisions of the Bidding Documents, the Employer may give the Bidder not more than 7 working days notice to rectify/furnish such documents, failing which the bid shall be rejected. The request for clarification and the response shall be in writing, and no change in the price or substance of the bid shall be sought, offered or permitted. | Replacing first Para of ITB clause 21.1 with the following: During bid evaluation, the Employer may, at its discretion, ask the Bidder for a clarification of its bid. In case of erroneous/non submission of documents related to/identified in ITB Sub-Clause 9.3 (b), (o), (s), (t), (u), (v), (w), (x), (y), (z), (aa), (bb), (cc), (dd) and (ee) or Deed of Joint Undertaking pursuant to ITB Sub-Clause 9.3 (c) & (e) or the complete annual reports together with Audited statement of accounts pursuant to ITB Sub-Clause 9.3 (c), Online Payment Acknowledgement towards the cost of Bidding Documents pursuant to ITB 5.4, documentary evidence with regard to registration with designated Authority of GoI under the Public Procurement Policy for MSEs pursuant ITB 5.5, documentary evidence with regard to MSE owned by SC/ST entrepreneurs or women in line with Public Procurement Policy for MSEs pursuant to ITB 9.3(p), required to be submitted by the Bidder as per the provisions of the Bidding Documents, the Employer may give the Bidder not more than 7 working days notice to rectify/furnish such documents, failing which the bid shall be rejected. The request for clarification and the response shall be in writing, and no change in the price or substance of the bid shall be sought, offered or permitted. |
| 5. | Cl. 2.0 of Bid Form (1st Envelope), Vol-III of the Bidding Documents | Attachments to the Bid Form (First Envelope): ……………. ……………. ……………. | Attachments to the Bid Form (First Envelope): ……………. ……………. (dd) Attachment-32: Declaration by the bidder for Acknowledgement and Acceptance of Supplier Code of Conduct |
| 6. | The file ‘First_Envelope_and_Bid_Forms’ stands replaced with the revised excel file for First Envelope and Bid forms, i.e., ‘First_Envelope_and_Bid_Forms_rev1’. Note: While submitting/ uploading the Price Bid on e-tendering portal, the bidder is required to change the file names as ‘First_Envelope_and_Bid_Forms’. |  |  |