

	Amendment No 01 dated 10/11/2026 to IFB for Transmission Line Package TL05 for 765 kV D/C line from 765 kV AIS Alkud-II (Jath) to 765 kV AIS Kandalgaon (proposed) (Part-III) associated with “Intra-State Transmission System for Establishment of 765/400/220 KV AIS Alkud II/Jath (Dist.: Sangli)” through Tariff Based Competitive Bidding (TBCB) route; Spec. No. CC/T/W-TW/DOM/A06/26/14723



	Sl.
No.
	Clause Ref. No.
	Existing provision
	Amended as

	INVITATION FOR BIDS (IFB), SECTION-I, VOLUME-I 

	1. 
	IFB 3.2
	The completion period for the subject Package(s) shall be 21 (Twenty-One) months as specified in ITB Sub-Clause 24.1(c).
	The completion period for the subject Package(s) shall be 33 (Thirty-Three) months as specified in ITB Sub-Clause 24.1(c).
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