## Sheet3
Technical Specifications for the work of Replacment of Defective Polymer insulators with Polymer Long Rod Insulators in 765 KV S/C Moga Meerut Tr. Lines.
Sl. No. | Description
1 | SCOPE OF WORK
1.(I) | The scope of work briefly covers for " Replacement of defective Polymer insulators in 765 KV S/C Meerut Moga Tr. Line at various locations falling in states of Uttar Pradesh, Haryana and Punjab under jurisdiction of Meerut, Panipat , Malerkotla and Moga Groups respectively. The scope of work includes mobilization and demobilization of skilled & experienced manpower at site including their boarding, lodging, arrangement of required T&P, Safety gears, Transportation of Polymer insulators from store situated at Moga, Malerkotla, Panipat & Meerut & handing over of dismentled Polymer insulators from various sites to respective POWERGRID Stores (or as per the instructions of Engineering Incharge ). The contractor shall ensure the proper handling of Polymer insulators to avoid any damage to the material and other property at site. In the event of damages , recovery shall be made from the party at the rate of 1.5 times of the actual current cost of the damaged item.
1.(II) | All the items which are incidental and necessary for successful completion of the works,but not exclusively mentioned , shall be deemed to be included in the scope of the work.
I(iii) | Procurement of Erection All Risk Insurance, Workman Compensation insurance, insurance of owner supplied material (Jointly in the name of POWERGRID & Contractor) on behalf of POWERGRID, third party insurance or any other insurances pertinent to the work, shall be the responsibility of the Contractor with no additional cost to the POWERGRID.
1(iv) | The work of replacement of defective Polymer insulator in various locations of 765 KV S/C Moga Meerut Tr. Line falling in jurisdiction of Uttar Pradesh, Haryana and Punjab (As per the BOQ) shall be required to be completed in Maximum 10 shut down days ( from 09.00 Hrs to 1700 Hrs on daily basis ). The shut down shall be arranged by POWERGRID. However, in the eventuality of delay in consective shut down due to grid constraints/system requirements, no idle charges is payable to the Party. The contractor shall deploy sufficient manpower & other resources along with supervisory staff so as to complete the entire work within 10 shut down days.
I(v) | The T&P to be used in the work, shall be properly tested by a competent person and the testing certificate in this respect to be submitted before start of the work.
I (vi) | There may be +/- 25% variation in the work as indicated in BOQ.
2 | In case if composite insulator is damaged during the execution of work, 1.5 times of actual cost of the Polymer insulator shall be recovered from the contractor. The additional quantity of Polymer insulator required to complete the work may be issued from any POWERGRID Store situated in NR2, as per the availability of the Polymer insulator. The contractor shall have to make arrangements for transportation of such insulators from the store to the respective sites with no additional cost to POWERGRID to get the work completed at site with in scheduled shut down period.
3 | Wastage/Breaking
I.) | Only 5% wastage of quantity of dismentled insulators shall be allowed. Recovery shall be made from the bills for damaged insulators exceeding 5% of dismentled quantity.
4 | Installation & Execution
I.) | Gang mobilization in requisite manner & execution of the work in the shut down period is the essence of the contract. If the period of shut down has to be cut short or changed due to any reason, the work shall have to be executed according to the new time schedule provided to the contractor, for which deployment of additional gangs and T&P etc. shall be arranged by the contractor without any additional cost to the POWERGRID.
II.) | The contractor shall have to mobilize the gangs at a short notice i.e. (04-05 days notice). It is the resposibility of the contractor to keep himself in contact with Engineer-In-charge regarding availability of shutdown/date of execution of work. The contractor shall engage adequate number of gangs so as to complete the entire work within the alloted shut down period.
III.) | The contractor shall ensure that while executing the said work, no damage/tampering is done to the POWERGRID's property like conductor and Hardware fittings etc.
IV.) | The contractor shall take proper care so as not to damage any standing crop while carrying out the work. In case some locations are such that work cannot be executed without damaging the standing crops, efforts should be made to cause minimum damages to the crops.
5 | Co- ordination:
I.) | The contractor has to remain in constant touch with the Engineer-in-charge regarding availability of required outages and to prepare an advance schedule thereof.
II.) | The contrator shall have to establish proper co-ordination for the assigned work with POWERGRID and other agencies including farmers.
6 | PTW
I.) | The contractor shall have to obtain Permit to work (PTW) on day to day basis which will be issued by POWERGRID official for specific time duration to the authorized Engineer approved by Engineer in charge
II.) | Failure to return the PTW within stipulated time period will be viewed seriously. All care shall be taken to return the Permit to Work on time.
7 | Any damages caused to POWERGRID's property such as conductors, Hardware fitting, Tower Parts etc. will have to be make good by replacing damaged items by the contractor with no additional cost to POWERGRID, otherwise the cost will be recovered as per the assessment by POWERGRID.
8 | It may be noted that all the material, T&P etc. required for the work are to be arranged by the contractor at his own cost. POWERGRID shall in no way be held liable for any loss or damage to such material. The cost of Storage cum Erection insurance by the contractor shall be deemed to have been included in the unit rate quoted by the contractor. POWERGRID shall inform the value of "Owner supplied Material" to the contractor after placement of award.
9 | Safety
I.) | All safety rules as per the guideline issued by POWERGRID for working in Tr. Lines ,IE Rules & extant rules applicable as per Law , are to be observed by the contractor.
II.) | All safety equipment i.e. Safety Belts, Safety Helmets, Safety shoes, Hand Gloves, Vertical Fall arrestors etc. required for carrying out the work in the Tr. Line are to be arranged by contractor
III.) | The contractor shall ensure the use of safety apparatus by all labours/supervision staff during the execution of work. It is the responsibilty of the contractor to execute the entire job in a safe manner to avoid any eventuality of accidents.

## Sheet1
LIST OF ENGINEER-IN-CHARGES
Sl. No. | Name of Transmission Line | Section | Store Address
1 | 765 KV s/c Moga Meerut Line (Moga Portion) | 736 to 922 | Power Grid Coporation of India Limited, 800/400/220 KV Substation, Urga Nagar, Kotkapura Road, Moga -142001 (Pb.)
2 | 765 KV s/c Moga Meerut Line (Malerkotla Portion) | 546 to 735 | Power Grid Coporation of India Limited, 400/220 KV Substation,Ludhiana Road, Malerkotla -148023 (Pb.)
3 | 765 KV s/c Moga Meerut Line (Panipat Portion) | 113 to 545 | Power Grid Coporation of India Limited, 400 KV BBMB Substation, Sewah, Panipat (Haryana)- 132108
4 | 765 KV s/c Moga Meerut Line (Meerut Portion) | 001 to 113 | Power Grid Corporation of India Ltd 765/400/220KV Substation, Meerut (UP)