| Sl. No. | Clause Ref. No. | Existing provision | Amended as |  |
| --- | --- | --- | --- | --- |
|  | Appendix-1 (Terms and Procedures of Payment), Sample Forms and Procedures, Section-VI | - TERMS OF PAYMENT ------------------------ B. Progressive Payment ---------------------- --------------------- | - TERMS OF PAYMENT ------------------------ B. Progressive Payment # ---------------------- --------------------- # Percentage of Progressive Payment shall be suitably adjusted in case of unbalanced/ front loaded bid as per the methodology brought-out at sl. No. 2.3 below |
|  | Appendix-1 (Terms and Procedures of Payment), Sample Forms and Procedures, Section-VI | NIL | 2.3 PAYMENT PROCEDURES IN CASE OF UNBALANCED / FRONT LOADED BID - A bid shall be considered front loaded or unbalanced, if the percentage of Services component (Installation) to Total Contract Price (Supply component + Services component) quoted by the bidder is less than 16.59 %. - In the event of award on the bidder who have submitted unbalanced/front loaded bid, the percentage of Progressive payment against Supply of Goods portion (refer sl. No. 1.1 above) shall be deferred by the percentage by which the percentage of the Services price components in the bid less than the percentage specified at 2.3 a above in the bidding documents. No interest shall be payable on the deferred amount. The aforesaid deferred amount shall be paid on pro-rata basis upon completion of installation of the respective item and its certification by the Project Manager. No interest shall be payable on the deferred amount. Price Variation and Quantity variation shall continue to be governed by the unit price quoted by the bidder. |