| S N | Clause | Provision of Bidding Documents | Bidder’s Query | POWERGRID's Reply |
| --- | --- | --- | --- | --- |
|  | GCC 1.1(e) & 1.1(ee) Section V- SCC Vol-I of Bidding Documents | The Time for Completion shall be as under : Description; Duration in Months from the date of Notification of Award. Establishment of State Transmission Asset Management Centre (STAMC) for Remote Control & Monitoring of OPTCL Grid Substations under Consultancy Services to OPTCL; Spec. No.: CC/NT/W-SCADA/DOM/A00/23/08228; 18 (Eighteen Months). | Considering the non readiness of the sites involved in the project, it would be difficult to complete the project with 18 months. Request POWERGRID to increase the timeline to atleast 24 months, provided the project sites become ready by then. | There shall be no change in the implementation schedule and Provision of bidding document shall remain same. |
|  | First Paragraph of GCC 9.3.1 Section V- SCC Vol-I of Bidding Documents | The Contractor shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten percent (10%) of the Contract Price (including Maintenance charges for 01 year during Defect Liability Period and AMC charges for 06 years after Defect Liability Period), with a validity upto ninety (90) days beyond the Defect liability Period. | ## Request POWERGRID to change the percentage to 3% in line with other similar utility contract requirements. | Provision of bidding document shall remain unchanged. |
|  | Appendix-1 to Contract Agreement, Section – VI, Vol-I of Bidding Documents | D. Final Payment ……………………… However, in case of delay in testing and commissioning & issuance of taking over certificate by Employer beyond six (6) months from the date of receipt of equipment at site, the last 15% of Ex-Works price of respective equipment shall be paid after issuance of a certificate by Employer’s representative that the equipment have been received in good condition and on submission of a bank guarantee of equivalent amount, which shall be kept valid initially for a period of twelve (12) months or until three (3) months after the expected date of commissioning (in case it is possible to anticipate the same), whichever is earlier, provided all other conditions as per para above are complied with by the contractor. If the commissioning does not take place within the validity period of BG, the validity of BG shall be extended from time to time. The bank guarantee shall, however, be released within one month of successful commissioning of the respective equipment by the Employer. | As per this clause, despite of delay due to employer, contractor has to pay Bank Guarantee of equivalent amount to receive the last milestone payment. PGCIL would already be holding PBG, and contractor finances would already be affected due to delay as per this clause, hence it is requested to delete the provision of submission of BG of equivalent amount to retrieve 15% final payment if delay is due to employer. | Provision of bidding document shall remain unchanged. |
|  |  |  | We request to reduce the retention payment(Final Payment) from 15% to 5%, and add corresponding payment milestone during design engineering stage. | Provision of bidding document shall remain unchanged. |
|  | General Query |  | We request PGCIL to allow price variation of commodity & labor during AMC phase. Bidder can quote the indices as part of the technical proposal which will be applicable or PowerGrid can suggest from their side. | Bidders are requested to refer Appendix – 2 ‘PRICE ADJUSTMENT’ to Contract Agreement, Section – VI, Vol-I of Bidding Documents, which is amply clear in this regard. |
|  | General Query | Storage at Site | We understand the material can be stored at PGCIL premises/installation site after dispatch. Please confirm. | Bidder to quote as per the provisions of the Bidding Documents. |
|  | Cl 21 Completion Time Guarantee sub clause no 21.2; GCC/SCC | 21. Completion Time Guarantee 21.1 ……………………… 21.2 If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to 0.05% (zero point zero five percent) of the Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each day which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed). …………..………………….. | We request that in the event of delay, Liquidated damages shall be the sole & exclusive remedy. Please confirm | Provision of bidding document shall remain unchanged. |
|  | Cl 35 ‘Suspension’, GCC, Vol-I of the Bidding Documents | 35. Suspension 35.1 The Employer may request the Project Manager, by notice to the Contractor, to order the Contractor to suspend performance of any or all of its obligations under the Contract. Such notice shall specify the obligation of which performance is to be suspended, the effective date of the suspension and the reasons therefor. The Contractor shall thereupon suspend performance of such obligation (except those obligations necessary for the care or preservation of the Facilities) until ordered in writing to resume such performance by the Project Manager. …………….……………………….. | Contractor shall be entitled for any and/or all cost incurred due to Suspension by Employer. Contractor should be entitled to suspend the works in following: 1. Payment is delayed for more than 45 days from date of Invoice. 2. Input form Engineer is delayed >30 days | Provision of bidding document shall remain unchanged. |
|  | Cl 36 ‘Termination’, GCC, Vol-I of the Bidding Documents | 36. Termination 36.1 Termination for Employer‟s Convenience 36.1.1 The Employer may at any time terminate the Contract for any reason by giving the Contractor a notice of termination that refers to this GCC Sub-Clause 36.1. ………………… ……………………………….. 36.2 Termination for Contractor‟s Default 36.2.1 The Employer, without prejudice to any other rights or remedies it may possess, may terminate the Contract forthwith in the following circumstances by giving a notice of termination and its reasons therefor to the Contractor, referring to this GCC Sub-Clause 36.2: …………….. …………………………………. | In the event of Termination by Customer for the reason not attributable to contractor, all direct & indirect cost shall be considered for payment to Contractor. Also Contractor shall be entitled to Terminate the Contract in following scenarios: 1. Payment is delayed for more than 60 days from date of Invoice. 2. Input form Engineer is delayed >60 days | Provision of bidding document shall remain unchanged. |
|  | Cl 32 ‘Force Majeure’, GCC, Vol-I of the Bidding Documents | 32. Force Majeure 32.1 “Force Majeure” shall mean any event beyond the reasonable control of the Employer or of the Contractor, as the case may be, and which is unavoidable notwithstanding the reasonable care of the party affected, and shall include, without limitation, the following: (a) war, hostilities or warlike operations (whether war be declared or not), invasion, act of foreign enemy and civil war, (b) rebellion, revolution, insurrection, mutiny, usurpation of government, conspiracy, riot and civil commotion, (c) earthquake, landslide, volcanic activity, flood or cyclone, or other inclement weather condition, nuclear and pressure waves or other natural or physical disaster, | Please include Pandemic in the list of events | Provision of bidding document shall remain unchanged. |
|  | Appendix-1 to Contract Agreement, Section – VI, Vol-I of Bidding Documents | Terms of Payment | In case of payments are delayed beyond 30 days from the date of invoice, an interest @ 12% p.a. shall be levied on the pending invoices value. Please confirm | Provision of bidding document shall remain unchanged. |
|  | Clause 2.1 & 38.1 of GCC | 2.1 Contract 2.1.1 The Contracts to be entered into with the successful Bidder shall be as under: - First Contract (Supply of Goods): For Ex works supply of all equipments and materials including mandatory spares and Type Test to be conducted (whether in India or abroad) (Supply of Goods Contract) - Second Contract (Supply of Services): For providing all services i.e. inland transportation for delivery at site, In-transit insurance, unloading, handling at site, installation, Testing and Commissioning including performance testing in respect of all the equipments supplied under the "First Contract", Training to be imparted (whether in India or abroad) and any other services specified in the Contract Documents (Supply of Services Contract). - Third Contract (Supply of Maintenance Services): ‘Third Contract’ for Comprehensive maintenance services for Seven years (One year Defect Liability Period and Six years after the completion of Defect Liability Period) for the equipments and services delivered under ‘First Contract’ and ‘Second Contract’. All the three contracts will contain a cross fall breach clause specifying that breach of one will constitute breach of the others. For all purposes, 'Employer' & 'Owner' under the third Contract shall mean Odisha Power Transmission Corporation Limited (OPTCL). First and Second contracts shall be signed between POWERGRID (on behalf of the Owner) and Contractor. Before commencement of AMC, Contractor shall enter Third contract directly with the Owner for Comprehensive maintenance services. …………………………………………… 38. Settlement of Disputes 38.1 POWERGRID is working as a Consultant on behalf of OPTCL. The cost of any litigation/arbitration and any liablity arising out of the award thereof, if any, shall be borne by the Owner. At no occasion POWERGRID shall be held liable under this contract. No case/arbitration shall be initiated against POWERGRID by the bidder/contractor, and also POWERGRID shall not be made a party by the bidder/contractor in the arbitration/court proceedings as POWERGRID in acting as an “Agent” or “Consultant”on behalf of OPTCL. ………………………………. | We understand that in case of any dispute under Supply & Services Contract (1st and 2nd Contract), dispute resolution shall commence between contractor & OPTCL (Owner) while Contract is signed between contractor & PowerGrid (Employer). Please clarify that the 1st and 2nd Contract is signed between Contractor and OPTCL(Owner) and PGCIL (Consultant/Agent/ Employer) only. | Bidders are requested to refer Cl. 2.1 & 38.1 of GCC in SCC, which are amply clear in this regard. |
|  | Cl 21 Completion Time Guarantee sub clause no 21.2; GCC/SCC | 21. Completion Time Guarantee 21.1 ……………………… 21.2 If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to 0.05% (zero point zero five percent) of the Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each day which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed). …………..………………….. | Liquidated damages shall be the sole remedy for any kind of loss/damage. We request you to kindly remove "The parties agree that the sum specified above is not a penalty but a genuine pre-estimate of the loss/damage which will be suffered by the Employer for default on the part of the Contractor and said amount will be payable without proof of actual loss or damage caused by such default. " | Provision of bidding document shall remain unchanged. |
|  | Cl 36 ‘Termination’, GCC, Vol-I of the Bidding Documents | 36. Termination 36.1 Termination for Employer‟s Convenience 36.1.1 The Employer may at any time terminate the Contract for any reason by giving the Contractor a notice of termination that refers to this GCC Sub-Clause 36.1. ………………… ……………………………….. 36.2 Termination for Contractor‟s Default 36.2.1 The Employer, without prejudice to any other rights or remedies it may possess, may terminate the Contract forthwith in the following circumstances by giving a notice of termination and its reasons therefor to the Contractor, referring to this GCC Sub-Clause 36.2: …………….. …………………………………. | Termination by contractor is not mentioned in the contract condition. Request you to kindly add it in the contract. Contractor shall be entitled for any and/or all cost incurred due to Termination by Employer. Contractor should be entitled to suspend the works in following: 1. Payment is delayed for more than 45 days from date of Invoice. 2. Input form Engineer is delayed >30 days | Provision of bidding document shall remain unchanged. |
|  | Preamble, INSTRUCTION TO BIDDERS (ITB) | …………………………… However, it shall be noted that no other party, including the Bidder/Contractor, shall derive any right from this 'Works & Procurement Policy and Procedure' documents or have any claim on the Employer on the basis of the same. …………………………….. | We request you to kindly ammend and remove bidder/contractor from limitation. Since, it is regarding the work, procurement policy which should be applicable for bidder/contractor and PGCIL. | Provision of bidding document shall remain unchanged. |