| Sl. No. | Clause ref. | Existing Provision of the Bidding Document | Query asked by the bidders | POWERGRID’s Clarification |
| --- | --- | --- | --- | --- |
|  | Clause No 1.1. (j) Vol‐1 ‐ Sec IV ‐GCC | Effective Date” means the date of Notification of Award from which the Time for Completion shall be determined. | Whether all input data from the Employer shall be provided prior to issuance of Notification of Award. In absence of all input data by the Employer, the Contract shall be based on the assumption of the Contractor. In case of any change on the above, the same shall be subject to mutual agreement between parties. | Provisions of bidding document are amply clear. |
|  | Clause No 1.1. (v) Vol‐1 ‐ Sec IV ‐GCC | The time for completion of Contract | Whether the deemed completion shall be construed if the Contractor has not received issuance of the certificate within 7 days of completion or if the employer not provided any written comments within 7 days or the Employer /Owner started its commercial use or otherwise. | Refer Amendment-1 |
|  | Clause No 4 Vol‐1 ‐ Sec IV ‐GCC | The time for Commencement and Completion | Whether the work schedules shall be subject to Liquidated Damages? Whether the work schedules shall commence on the Effective Date? | For Liquidated damage, Refer CL 9 of GCC. Work Schedule shall commence from the date of NOA. Refer Cl 4 of GCC |
|  | Clause No 7.3 Vol‐1 ‐ Sec IV ‐GCC | Review of the work performed by the contractor either by Employer or through another consultant separately appointed by Owner and ask for any clarification and changes/modifications to the work performed by the contractor. Such changes shall be mutually discussed and agreed between the Owner and the contractor and the same shall be incorporated by the contractor in his work without any cost to the Employer and without any dilution of the responsibility of the contractor. | Please find the observations as below ‐ The consultant shall not be a competitor to the Bidder. The consultant needs to be bound by NDA or other suitable mechanisam to prevent the interest and technology details of Bidder. | POWERGRID will take due diligence during engagement of consultant, if any. |
|  | Clause 7.1 Vol‐1 ‐ Sec IV ‐GCC | Owner reserves the right for the following: ‐ - Rejection of any or all offers/Reports without assigning any reason whatsoever. - Rejection of any offer/Reports with incomplete scope of works or which is an incomplete offer/Reports in the opinion of the Employer. - Review of the work performed by the contractor either by Employer or through another consultant separately appointed by Owner and ask for any clarification and changes/modifications to the work performed by the contractor. Such changes shall be mutually discussed and agreed between the Owner and the contractor and the same shall be incorporated by the contractor in his work without any cost to the Employer and without any dilution of the responsibility of the contractor. Seek changes in the contractor personnel deployed for the assignment on grounds of quality of work, timely completion or other reasons. Such changes shall be mutually discussed and agreed between the Owner and the contractor without any cost to the Owner and without any dilution of the responsibility of the contractor. Further, the replaced personnel shall have similar or higher competency level and designation. | Whether the Contractor is entitled to the cost and the expenses incurred towards any or all offers/Reports, if the Contractor is not in default? Whether Rejection of any or all offers/Reports shall be provided only after assigning reason of default? | Provisions of bidding document shall prevail. Refer Amendment-1 |
|  | Clause 9.2 Vol‐1 ‐ Sec IV ‐GCC | 9.2. If the Contractor fails to comply with the Time for Completion in accordance with Clause 9.1 above for the entire scope of work as per Technical specification, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to 0.05% (zero point zero five percent) of the Contract Price plus GST payable thereon for the entire scope of work, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each day which shall elapse between the relevant Time for Completion and the date stated in acceptance of final report of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price plus GST payable thereon for the entire scope of work, (or a part for which a separate time for completion is agreed). | As per Appendix‐5 (Sec VI) ‐Draft Contract, GUARANTEES, LIQUIDATED DAMAGES FOR NON – PERFORMANCE are specified as Not Applicable. Hence this clause may be deleted or suitable modifications are required in the draft contract. | Please refer Amendment – 1 Provisions of bidding document shall prevail. |
|  | Cl 9.4 Vol‐1 ‐ Sec IV ‐GCC | Contractor shall indemnify and hold harmless POWERGRID against any and all claims, demands, and/or judgements of any nature brought against POWERGRID arising out of the services by Contractor and it's staff under this Agreement. The obligation under this paragraph shall survive the termination of this Agreement. | It is proposed to delete this provision. | Provision of bidding documents will remain unchanged. |
|  | Clause 10.1 Vol‐1 ‐ Sec IV ‐GCC | Performance Securities 10.1.1. The Contractor shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Three percent (3%) of the Contract Price, with a validity upto ninety (90) days beyond the completion Period as per contract agreement. The same shall be extended by the Contractor time to time till ninety (90) days beyond the extended completion Period, as may be required under the Contract. | No specific or definite date is specified under these provisions towards the release of Performance Securities. Hence following text is proposed as new clause ‐ "The Performance Securities submitted under the Contract shall be released upon 4 months from Effective Date or the Completion of the Work, which ever is later." | Provisions of bidding document are amply clear. Bidder may also refer Amendment – 1 |
|  | Clause 10.2 (b) Vol‐1 ‐ Sec IV ‐GCC | Alternatively, if the Contractor fails to extend the validity of the performance security, an amount @prevailing SBI Card Rate applicable for Inland Bank Guarantee +2% per annum on the performance security amount corresponding to the Facilities or any relevant part thereof covered under the said performance security, for the period of delay shall be paid by the Contractor to the Employer. The Employer may, without prejudice to any other method of recovery, deduct the amount worked out as above from any monies due or to become due to the Contractor under the Contract. | Option ‐1 Alternatively, if the Contractor fails to extend the validity of the performance security for delays solely attributable to Contractor, an amount @prevailing SBI Card Rate applicable for Inland Bank Guarantee +2% per annum on the performance security amount corresponding to the Facilities or any relevant part thereof covered under the said performance security, for the period of delay shall be paid by the Contractor to the Employer. The Employer may, without prejudice to any other method of recovery, deduct the amount worked out as above from any monies due or to become due to the Contractor under the Contract. Further, if the Contractor is required to extend the validity of the performance security for reasons attributable to the Employer, the Employer shall reimburse the performance security extension charges at actuals. Option‐2 ‐ Deletion of this clause. | Provisions of bidding document shall remain unchanged. |
|  | Clause 10.4 Vol‐1 ‐ Sec IV ‐GCC | The Employer shall be sole judge in above regard. | The same may be deleted | Provisions of bidding document shall remain unchanged. |
|  | Cl 12.1 Vol‐1 ‐ Sec IV ‐GCC | 12.1. The copyright in all the drawings, documents and other materials containing data and information for design(s) which have been developed by the Contractor or by any third party under the Contract shall remain vested in the Employer for the material and in the manner as detailed in the Technical Specification, The Employer shall however be free to reproduce all drawings, documents and other material furnished to the Employer for the purpose of the Contract including, if required. | Whether the copyright in all the drawings, documents and other materials containing data and information for design(s) which have been developed by the Contractor or by any third party under the Contract shall remain vested in the Contractor or by third party, being the original copyrights owner, for the material and in the manner as detailed in the Technical Specification, The Employer shall however be free to use all drawings, documents and other material furnished to the Employer for the purpose of the Contract including, if required. Please confirm that there will be no transfer of owership of IPRs, vested with the documents prepared by the Contractor. (GCC 17) | Refer Amendment - 1 |
|  | Cl 13.1 Vol‐1 ‐ Sec IV ‐GCC | The Employer and the Contractor shall keep confidential and shall not, without the written consent of the other party hereto, divulge to any third party any documents, data or other information furnished directly or indirectly by the other party hereto in connection with the Contract, whether such information has been furnished prior to, during or following termination of the Contract. | The Employer (including its consultant or other parties employed by the Employer) and the Contractor shall keep confidential and shall not, without the written consent of the other party hereto, divulge to any third party any documents, data or other information furnished directly or indirectly by the other party hereto in connection with the Contract, whether such information has been furnished prior to, during or following termination of the Contract. | Refer Amendment - 1 |
|  | Cl 13.2 Vol‐1 ‐ Sec IV ‐GCC | The Contractor shall not use such documents, data and other information received from the Employer for any purpose other than such work and services as are required for the performance of the Contract. | The Contractor Parties shall not use such documents, data and other information received from the other Party Employer for any purpose other than such work and services as are required for the performance of the Contract. | Refer Amendment - 1 |
|  | Cl. 14 Vol‐1 ‐ Sec IV ‐GCC | The contractor shall not assign or sub‐contract any portion of this work without the prior written consent of POWERGRID. | Whether prior writtent consent is also required to assignment or subcontracting to Group Company, or entity who has provided with the Deed of Joint Undertaking? | Provisions of bidding document are amply clear. |
|  | CL 20 Vol‐1 ‐ Sec IV ‐GCC | Force Majeure | Please confirm the below Note will be part of Force Majeure: "The Parties are aware of the current worldwide outbreak of a Coronavirus (commonly known as COVID‐19) or any mutation of such virus which is or may impact normal business and execution of this Contract. Contractor shall be entitled to cost compensation, time extension, or other reasonably required contract adjustments, if any consequences whether directly or indirectly resulting out of, or in connection with the coronavirus outbreak, lead to delays in delivery of goods or provision of services or otherwise affect Contractor's contractual obligations or duties. Contractor hereby reserves the right to amend the delivery, the price, the scope and the other terms and conditions of contract set out in this offer due to the current epidemic of novel coronavirus outbreak. Notwithstanding anything to the contrary, the forgoing paragraph is deemed to be incorporated into any subsequent concluded contract. The Parties acknowledge and include the following events under Force Majeure (a) the continuing conflict between Russia, Ukraine, and other counties which began on or around 24 February 2022, and any economic and other sanctions imposed which may arise out of or in connection therewith (b) a continuing global shortage in the supply of microchips and products containing microchips exists, which is or may impact normal business and execution of this Contract. " | Provisions of bidding document are amply clear. Bidder may also refer Amendment – 1 |
|  | Cl 21.1 Vol‐1 ‐ Sec IV ‐GCC | New Clause | Add the following as new Clause ‐ (f) Any delay to Work for reason not attributable to Contractor and/or for any reason specified under the conditions of Contract. | Provisions of bidding document are amply clear. Bidder may also refer Amendment – 1 |
|  | Cl 21.4 Vol‐1 ‐ Sec IV ‐GCC | New Clause | In the event of extension of Time for Completion for reasons not attributable to the Contractor, the Contractor shall have the right to compensation for additional costs resulting from extension of Time for Completion. | Provisions of bidding document shall prevail |
|  | Cl 24.1 Vol‐1 ‐ Sec IV ‐GCC | Termination for Default | It is proposed to add the following towards the end ‐ The services that are completed and ready as on notice of termination shall be accepted and payable by the Owner at the contract terms and prices. If payment of the invoice is delayed, or the Employer disrupts or breaches its obligations under the Contract, the Contractor shall have the right of terminate the Contract, if the Employer does not cure its failure within 30 days after receipt of the default notice from the Employer. | Bidding condition shall remain unchanged. |
|  | CL 25 Vol‐1 ‐ Sec IV ‐GCC | Suspension of the obligation | It is proposed to add the following ‐ If the suspension period on account of Force Majeure exceeds 60 days in aggregate, then, the Contract shall stand terminated. However, the Employer shall release payments as per the Contract terms for the services rendered up to date of notice of Force Majeure. If the suspension period on account of Force Majeure is less than 60 days in aggregate, then the Contractor shall be entitled for Extension of Time without any imposition of Liquidated Damages for a duration equivalent to the suspension period. If the Employer suspends the Contract for any reasons other than Force Majeure, the Contractor shall be entitled for Extension of Time without imposition of Liquidated Damages for a duration equivalent to the suspension period (including additional time for re‐commencement etc.) and additional compensation thereto. If payment of the invoice is delayed, or the Employer disrupts or breaches its obligations under the Contract, the Contractor shall have right of suspension, time extension and cost compensation resulting from such delay, suspension or disruption. | Provisions of bidding document are amply clear. Bidder may also refer Amendment – 1 |
|  |  | New Clause | Limitation of Liability. (a) The total cumulative liability of the Contractor, its officers, employees and affiliates to the Employer with respect to Work performed or to be performed pursuant to this Agreement whether in contract, warranty, indemnity, contribution, tort (including negligence, whether active, passive or any other kind) or otherwise, shall not exceed 100% of gross compensation received by the Contractor under the applicable Purchase Order/Agreement. b) The Contractor shall not be liable to the Employer for any special, consequential, indirect, incidental or penal losses or damages whether in contract, warranty, tort, negligence, strict liability or otherwise, including but not limited to loss of profits or revenue, or other losses, damages or claims related to the unavailability of facilities or equipment, shutdowns or service interruptions, loss of use, profits or revenue, inventory or use charges or cost of capital, or claims of customers of Invenergy or other third parties for any damages. | Refer Amendment - 1 |
|  | Cl No: 8.1 & 8.2 Section‐I (Vol‐1), IFB | 8.1 Soft Copy Part of the Proposals must be uploaded under Single Stage Two Envelope Proposal procedure on the portal at or before 11:00 hours on 19/09/2022. The e‐Procurement system would not allow any late submission of Proposals through the portal after due date & time as specified. | We kindly request the Owner to extend the Bid submission date till 7th October 2022. | Bid submission date has been extended which is currently up to 31.10.2022. |
|  | Cl. No: 2.5 Section‐II (Vol‐1), ITB | 2.5.A Bidder shall not have a conflict of interest. All Bidders found to have a conflict of interest shall be disqualified. A Bidder may be considered to have a conflict of interest with one or more parties in this bidding process, if: ….................... ...................... f.a Bidder or any of its affiliates participated as a consultant in the preparation of the design or technical specifications of the Plant and Installation Services that are the subject of the bid; or ....................... ....................... | Kindly requesting you to delete the referred clause. | Bidding Conditions shall prevail. Bidder may also Refer Amendment-1 |
|  | Cl. No: 6.2 Section‐II (Vol‐1), ITB | The Bidder is advised to visit and examine the site (s) of the subject proposal and its surroundings and obtain for itself on its own responsibility and cost all information that may be necessary for preparing the bid and entering into a contract. The costs of visiting the site shall be at the Bidder’s own expense. | This requirement cannot be fulfilled by the Bidder at this stage since the site details / land layouts are not provided in the tender. | Provisions of bidding document are amply clear. |
|  | Cl. No: 9 Section‐II (Vol‐1), ITB | I Hard Copy Part …............................ iv.B idders shall also submit Joint Deed of Undertaking by the PARENT/ PRINCIPAL/GROUP COMPANY along with the bidder, duly signed and stamped on each page in original, if applicable as per Annexure‐ A (BDS); ................................ | We request Owner to delete this Joint Deed of Undertaking requirement. Bidder requests Owner to consider Comfort Letter instead of this JDU. | Provisions of bidding document shall remain unchanged. |
|  | Cl. No: 13.1 Section‐II (Vol‐1), ITB | Bids shall remain valid for the period of six months after the date of opening of Techno ‐ Commercial Part i.e. First Envelope, prescribed by the Employer. A bid valid for a shorter period shall be rejected by the Employer as being non‐responsive. | We request Owner to consider bid validity period of 3 months instead of 6 months. | Provisions of bidding document shall remain unchanged. |
|  | Cl. No: 20.7 Section‐II (Vol‐1), ITB | 20.7.Bids containing deviations from critical provisions relating to GCC Clauses 28 (Governing Law), 5 (Contractor’s Responsibilities), 8.4 (Terms of Payment), 10.1 (Performance Security), 11 (Taxes and duties), 9.3 (Defect Liability), 18 (Patent Indemnity), 22.1 (Settlement of Disputes), 23 (Arbitration) will be considered as non‐responsive and Appendix 2 to the Form of Contract Agreement (Price Adjustment) will be considered as non‐ responsive. | Refered Cl. No: 9.3 is not matching. Need to be corrected. | Refer Amendment -1 |
|  | Cl. No: 13 Section‐III (Vol‐1), BDS | Bidder, in case of Indian bidder also means bidder himself or his parent/principal or Group company who participates in the bidding for the main HVDC VSC. | Kindly clarify. | Provisions of bidding document are amply clear |
|  | Cl. No: 1.1 Section‐IV (Vol‐1), GCC Cl. No: 9.4 Section‐IV (Vol‐1), GCC Sl. No: 5 GCC Cl 9 Section‐V (Vol‐1), SCC | (i)“ Defect Liability Period” means the period of validity of the warranties given by the Contractor commencing at Completion of the work during which the Contractor is responsible for rectification of work. 9.4.Liability of the Contractor Any mistake or inadequacy appear in the documents submitted by the Contractor, the Contractor shall perform at its own initiative and no extra cost to POWERGRID, all such services as shall be necessary to remedy the said mistake or inadequacy. The Contractor shall be further liable for the consequences resulting from errors and commissions due to negligence or from inadequacy on its part or on the part of its employees or associates or experts to the extent of the fees actually received by the Contractor. GCC Cl 9 Supplementing Sub‐Clause: The Liability Period shall be 03 months from the date of submission of final report and acceptance of the same. | Please clarify the Defect Liability Period for the scope of the work? | Please Refer Amendment-1 |
|  | Cl. No: 1.1 Section‐IV (Vol‐1), GCC | (v)The Time of completion of Contract: Unless otherwise terminated under the provisions of any other relevant clause of the document, contract shall be deemed to have been completed after issuance of the certification from Officer in Charge, that there is no demand outstanding against the contractor and all liabilities under the contract have been satisfactorily fulfilled by the contractor. | We request you to amend the clause as below: (v)T he Time of completion of Contract: Unless otherwise terminated under the provisions of any other relevant clause of the document, contract shall be deemed to have been completed upon submission of all deliverables mentioned in the technical specification after issuance of the certification from Officer in Charge, that there is no demand outstanding against the contractor and all liabilities under the contract have been satisfactorily fulfilled by the contractor. | Provisions of bidding document shall prevail |
|  | Cl. No: 7.1 Section‐IV (Vol‐1), GCC | Rejection of any or all offers/Reports without assigning any reason whatsoever. | We request Owner to delete this clause. | Please Refer Amendment-1 |
|  | Cl. No: 7.2 Section‐IV (Vol‐1), GCC | Rejection of any offer/Reports with incomplete scope of works or which is an incomplete offer/Reports in the opinion of the Employer. | Rejection of any offer/Reports with incomplete scope of works or which is an incomplete offer/Reports in the opinion of the Employer. | Please Refer Amendment-1 |
|  | Cl. No: 7.3 Section‐IV (Vol‐1), GCC | Review of the work performed by the contractor either by Employer or through another consultant separately appointed by Owner and ask for any clarification and changes/modifications to the work performed by the contractor. Such changes shall be mutually discussed and agreed between the Owner and the contractor and the same shall be incorporated by the contractor in his work without any cost to the Employer and without any dilution of the responsibility of the contractor. | We request to amend the caluse as follows: "Review of the work performed by the contractor either by Employer or through another consultant separately appointed by Owner and ask for any clarification and changes/modifications to the work performed by the contractor. Such changes shall be mutually discussed and agreed between the Owner and the contractor and the same shall be incorporated by the contractor in his work without any cost to the Employer and without any dilution of the responsibility of the contractor." | Please refer Sr. no. 26. Of Clarification-1 (Technical) dated 31/10/2022. |
|  | Cl. No: 11.7 Section‐IV (Vol‐1), GCC | The Contractor shall be liable to take /maintain all necessary insurances at its own cost. | We request Owner to delete this clause since insurance requirements are not applicable as per Appendix‐3 | As per Employer’s understanding, no insurance is required for the FEED Study. However, bidder must confirm their position in relation to the insurance requirement. In case any insurance is required for properly executing and completing the scope of work, the same must be included in bid. No compensation on this ground shall be admissible later on. |
|  | Appendix‐3 Section‐VI (Vol‐1), Sample Forms and Procedures | INSURANCE REQUIREMENTS ‐ NOT APPLICABLE | We request Owner to delete this clause since insurance requirements are not applicable as per Appendix‐3 | Provisions of bidding document shall remain unchanged. |
|  | Cl. No: 25 Section‐IV (Vol‐1), GCC | 25.SUSPENSION OF THE OBLIGATION The obligations stipulated in the Bidding documents can only be suspended in the case of any particular item of work, in the event of Force Majeure as defined in Clause No. 15 herein or as a result of an agreement between the parties. In the event of Force Majeure, neither of the Parties may be considered in default of its obligations under the terms of the Bidding documents. | The refered clause number is not matching. Please correct the same. | Please Refer Amendment -1 |
|  | Cl. No: 26 Section‐IV (Vol‐1), GCC | 26.ABANDONMENT OF WORK If any work included in the scope of the Bidding documents to be done by the contractor is abandoned or suspended for any cause or reasons which cannot be attributed to the contractor, payment shall be made on a pro‐ rate basis for the work actually done and reported by him. | Kindly clarify how value for the pro‐rata payments will be decided. It would be helpful if you can provide a sample calculation. | Please Refer Amendment -1 |
|  | Sl. No: 2 / GCC Cl 4 Section‐V (Vol‐1), SCC |  | Kindly requesting the Owner to consider Eight (8) months instead of 4 months. | Provisions of bidding document are amply clear |
|  | Appendix ‐ 4 TIME SCHEDULE Section‐VI (Vol‐1), Sample Forms and Procedures |  | Kindly requesting the Owner to consider Eight (8) months instead of 4 months. | Provisions of bidding document are amply clear |
|  | Sl. No: 5 GCC Cl 9 Section‐V (Vol‐1), SCC | GCC Cl 9 Supplementing Sub‐Clause: The Liability Period shall be 03 months from the date of submission of final report and acceptance of the same. | The Liability Period shall be 03 months from the date of submission of final report and acceptance of the same. | Provisions of bidding document shall prevail. Bidder may also Refer Amendment-1. |
|  | Vol‐1, FORM OF JOINT DEED OF UNDERTAKING | IN WITNESS WHEREOF the Parent/Principal/Group Company, and the Bidder/Contractor/Manufacturer have through their Authorised Representatives executed these presents and affixed Common seals of their respective Companies, on the day, month and year first above mentioned. AND (For Manufacturer) (Signature of the authorized representative) | Manufacturer is not applicable for this tender. Kindly requesting you delete same. | Provisions of bidding document are amply clear. |
|  | ATTACHMENT‐5 Vol‐3, First Envelope and Bid Forms | We hereby declare that the following Work Completion Schedule shall be followed by us in furnishing and installation of the subject Package i.e., FEED – 1 STUDY of Front End Engineering and design (FEED) study for ± 350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park. for the period commencing from the effective date of Contract to us | We hereby declare that the following Work Completion Schedule shall be followed by us in furnishing and installation of for the subject Package i.e., FEED – 1 STUDY of Front End Engineering and design (FEED) study for ± 350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park. for the period commencing from the effective date of ontract to us | Revised First Envelope and Bid Forms provided. Refer Amendment -1 |
|  | Cl. No: 1.0 Vol‐3, First Envelope and Bid Forms, ATTACHMENT‐9 Additional Information | A certificate from their Banker(s) (as per prescribed formats in Form 16, Section‐VI: Sample Forms and Procedures) indicating various fund based/non fund based limits sanctioned to the Bidder and the extent of utilization as on date. Such certificate should have been issued not earlier than three months prior to the date of bid opening. Wherever necessary the Employer may make queries with the Bidders’ Bankers. | We understand that Form 16 refered here is same as "FORMAT FOR EVIDENCE OF ACCESS TO OR AVAILABILITY OF CREDIT/FACILITIES" provided in Section‐VI: Sample Forms and Procedures. Please confirm. | Revised First Envelope and Bid Forms provided. Refer Amendment -1 |
|  | Cl. No: 2.0 (c) Vol‐3, First Envelope and Bid Forms, BID FORM (First Envelope) | …........................... Further the required deed of Joint Undertaking signed by us and PRINCIPAL as per your format. | …........................... Further the required deed of Joint Undertaking signed by us and PARENT/PRINCIPAL/GROUP COMPANY as per your format. | Revised First Envelope and Bid Forms provided. Refer Amendment -1 |
|  | Cl. No: 4 Vol‐3, Attachment‐12, Declaration of Key Managerial Person and Power of Attorney holder | We understand that any false declaration and/or misrepresentation of facts and/or furnishing of false/forged documents /information may lead to our debarment from participation in Employer tenders and that our Bid Security/ Contract Performance Guarantee may be forfeited besides other actions as deemed to be appropriate as per the provisions of the Bidding Document/Integrity Pact/Employer’s policy. | Bid Security is not applicable. We understand that Bidder shall submit only the Bid‐Securing Declaration. Please confirm. | Bidder’s Understanding is correct. |
|  | Schedule‐1 Vol‐3, Price_schedule | Township for 132/33 kV Silapathar (new) Civil Works | Item description is not matching with the scope of work. Please correct the same. | Revised Price Schedule provided. Refer Amendment -1 |
|  | Section‐VI (Vol‐1), Sample Forms and Procedures Appendix ‐ 1 TERMS AND PROCEDURES OF PAYMENT | 60% of total of FEED‐1 Study Payment shall be released after submission of duly signed FEED‐1 report as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 30% of FEED‐1 Study payments shall be released after clarification by Bidder and acceptance of respective report by POWERGRID. Final 10% of FEED‐1 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. | 20% as Advance Payment 50% of total of FEED‐1 Study Payment shall be released based on agreed delivery milestone and after submission of duly signed FEED‐1 respective reports as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 20% of FEED‐1 Study payments shall be released after clarification by Bidder and acceptance of respective report by POWERGRID. Final 10% Payment to be released after expiry of Liability Period of 3 months from date of submission of final report and acceptance (SCC GCC CL 9). of FEED‐ 1 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from5 GW renewable energy park) by the bidder or its parent/principal or group company. | Provisions of bidding document shall remain unchanged. |
|  | Section‐VI (Vol‐1), Sample Forms and Procedures Appendix ‐ 1 TERMS AND PROCEDURES OF PAYMENT | Clause numbers: 1.1, 1.2, 7.1, 7.2, 7.3, 7.4, 7.5 | Clause numbers are not in correct order. Please correct the same. | Please Refer Amendment -1 |
|  | Sl No 9 (e ) Section III (Vol I)_BDS | POWERGRID’s right to associate itself in the FEED study | Please clarify the details of the association like no of man‐days, stage of involvement, other modalities. Bidder's scope excludes any kind of boarding, lodging, travel and any other associated expenses related to this association. | The details and extent of the association of Employer/owner during the FEED Studies will be subject of discussion during Post Bid Discussion. The cost involved on account of boarding, lodging, travel etc of POWERGRID Employee will be borne by Employer/owner. |
|  | Clause No ‐ 9.2 Section‐IV, GCC | If the Contractor fails to comply with the Time for Completion in accordance with Clause 9.1 above for the entire scope of work as per Technical specification, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to 0.05% (zero point zero five percent) of the Contract Price plus GST payable thereon for the entire scope of work, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each day which shall elapse between the relevant Time for Completion and the date stated in acceptance of final report of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price plus GST payable thereon for the entire scope of work, (or a part for which a separate time for completion is agreed). | Circular No ‐ 178/10/2022 ‐ GST dated ‐ 03.08.2022 has clarified that GST is not applicable on the Liquidated damages, Penalty imposed on violation of Law, late payment Fee, etc. Kindly confirm that in case of said scenarios covered under the said Circular, GST is not applicable. | Please Refer Amendment -1 |
| - 1 | Section I IFB 3.0 | FEED – 1 STUDY of Front End Engineering and design (FEED) study for ± 350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park. | As per Vol‐II, Chapter‐2, 1st para Bidder understands that the Pang pooling station (Leh) would be connected to 13 GW renewable energy park (9 GWp solar, 4 GWp wind) with 12 GWhp BESS. However, the name of the package here and elsewhere in the tender documents (including for future FEED‐2 study and main HVDC VSC package) mentions 5 GW renewable energy park. Please check and correct the tender documents appropriately. | Technical specification shall prevail. |
|  | Section I IFB 2.5 | The Bid for FEED‐2 study shall be invited in due course and the Bid for main HVDC VSC Package ….. shall be invited from eligible bidders after completion of FEED‐1 and FEED‐2 studies. | Bidder acknowledges and appreciates this information from Owner. However, it shall be noted that the terms & conditions, etc. agreed for FEED‐1 Study contract shall not be deemed to be binding or to set a precedent / obligation for the future tenders / contracts e.g. FEED‐2 Study and main HVDC VSC package. | Bidding Conditions shall prevail. |
|  | Section II ITB 2.4 (4) Section IV GCC 14 | *For the purpose of working out 50% of the Contract, following shall be taken into account: (a) Scope of the contract which is permissible to be sub‐contracted as per bidding documents, shall be excluded. The contractor shall not assign or sub‐contract any portion of this work without the prior written consent of POWERGRID. | Considering the requirements of ITB 2.1 and Annexure‐A (BDS), and the scope of work (FEED Study ‐ 1) of this tender, the Bidder requests the following amendment: "In case the bidder is an Indian entity (as per Cl. 2.1.2 of Annexure‐A (BDS), then the bidder/contractor shall be permitted to sub‐contract major portion of this work (more than 50%) to the Parent / Principal / Group Company of the bidder that meets the qualifying requirements as per Cl. 2.1.1 of Annexure‐A (BDS)" | Provisions of bidding document are amply clear. |
|  | Section II ITB 2.5 | A Bidder shall not have a conflict of interest. All Bidders found to have a conflict of interest shall be disqualified. … (f) A Bidder or any of its affiliates participated as a consultant in the preparation of the design or technical specifications of the Plant and Installation Services that are the subject of the bid. | Bidder draws Owner's attention to Section‐I, IFB 2.2 to 2.5 wherein it is mentioned that Owner intends to invite tenders for FEED‐2 Study and the Main HVDC VSC package in due course. In case the Bidder participates in FEED‐1 (or FEED‐2 Study), then this should not be interpreted as conflict of interest in case the Bidder participates in the future tenders for FEED‐2 Study / Main HVDC VSC package. Owner is requested to confirm and include this provision in the tender documents for FEED‐1 Study. | Please Refer Amendment -1 |
|  | Section II ITB 5.1 (3) | Volume‐III: Bid Form, Price Schedules & Technical Data Sheets | No "Technical Data Sheets" were found in Volume‐III. We understand that this refers to the Technical Bid to be submitted by the Bidder with First Envelope. | Please Refer Amendment -1 |
|  | Section II ITB 6.2 | The Bidder is advised to visit and examine the site (s) of the subject proposal and its surroundings and obtain for itself on its own responsibility and cost all information that may be necessary for preparing the bid and entering into a contract. The costs of visiting the site shall be at the Bidder’s own expense. | In accordance with Section‐I, IFB 2.4 the scope of this tender is limited to the 1st part of the Front‐End Engineering and Design Study i.e. FEED‐1 Study. Therefore, the requirements mentioned under ITB 6.2 are not relevant, and will not be considered in the Bidder's scope & costing. Owner is requested to confirm this understanding. Alternatively, Owner is requested to state the specific FEED‐1 Study tasks / deliverables (refer Vol‐II) under which such site visit is envisaged during the bidding and/or execution phase. | Please Refer Amendment-1 |
|  | Section II ITB 6.2 | POWERGRID will issue clarifications/amendment through E‐Portal. These shall form integral part of the Bidding Documents and accompany the Bidder’s proposal. | Please clarify the underlined text. | Please Refer Amendment -1 |
|  | Section II, ITB 6.3 Section III, BDS 5 | The Bidder’s designated representatives are invited to attend a pre‐bid meeting, which will take place through Video Conferencing. The Schedule of meeting and web link to join the meeting shall be as mentioned in Section III BDS. | Apart from the initial pre‐bid meeting on 6th September 2022 [as per ITB 6.4 (BDS 5)], Bidder is of the opinion that that additional pre‐bid meetings / one‐to‐one meetings between Owner & individual Bidder may be necessary to ensure mutual clarity of the bidding documents prior to submission of the single stage bid. Hence, Owner is requested to permit these additional meetings during the course of the bidding documents clarification process. The results of these pre‐ bid meetings / one‐on‐one meetings between Powergrid and the Bidder(s) may be recorded; and issued to all Bidders in the form of Common Amendments and Clarifications in accordance with relevant provisions of ITB. | Noted |
|  | Section II ITB 6.4 | After receipt of such interpretations and clarifications, the Bidder may submit his offer but within the time and date as specified in the documents. | Depending on the nature, quantum & timing of the intepretations & clarifications, and other influencing factors it may be necessary for the deadline for submission of bid to be extended in accordance with ITB 7.3. | Bid submission date has been extended which is currently up to 31.10.2022. |
|  | Section II ITB 11.2 | The bid Prices quoted by the Bidder shall be Fixed during the performance of the contract and not subject to variation on any account | The Bidder understands that bid prices shall not be subject to variation on account of price indices and such factors. However, the bid prices shall be subject to variation during the course of execution in case of additional scope or work or task, new requirements, changes, repetition of work, extension of time, etc. for reasons not attributable to the bidder/contractor, etc. | Please Refer Amendment -1 |
|  | Section II ITB 11.3 | The quoted prices shall be deemed to cover for the full scope as aforesaid, including travel and other out of pocket expenses, overhead and profits. The bid price shall include all man‐day charges including deputation, equipment charges, administrative charges and any other incidental charges (directly or indirectly), for successful completion of the work. | `1. No international travels to India are foreseen and hence costs for the same will not be included in the bid price. Participation of experts/ personnel located outside of India during meetings and discussions with Owner will be carried out virtually e.g. via Microsoft Teams meeting or similar online platforms. Kindly confirm this understanding. 2. In case it is required for our international experts / personnel to travel or be deputed to India or outside of home country due to Owner's request e.g. for participating in meetings, etc. the costs for the same shall be paid by the Owner as per unit rates defined in the contract. The Owner is requested to include a price schedule for "Optional Items" that may be ordered on unit rate basis. Considering the nature of work, this would be an efficient way to optimise the overall cost as well result in smooth execution of the FEED‐1 study. | 1& 2: The FEED Study is to be carried out by the bidder in association with their Parent/Principal/Group Company. All necessary support & arrangement between bidder and their Principal/Parent/Group Company is covered under the scope of the Contract. |
|  |  |  | 3. No equipment supply to Owner is foreseen under the contract. Kindly confirm this understanding. | 3. Bidder’s understanding is correct. |
|  | Section II ITB 13.1 | Bids shall remain valid for the period of six months after the date of opening of Techno ‐ Commercial Part i.e. First Envelope, prescribed by the Employer. | Considering the nature of work, Bidder requests for a validity period of three (3) months after the date of opening of First Envelope. | Provisions of bidding document shall remain unchanged. |
|  | Section II ITB 21.9 Section IV GCC 11.3 | If there is difference in HSN/SAC classification and corresponding rate of GST of an item as confirmed/deemed confirmed by the bidder in its bid and HSN/SAC and corresponding rate of GST as interpreted under any interpretation/ judgment/ Notification/ Circular issued under the GST law before or after the award of contract, GST reimbursable to the bidder/Contractor shall be lower of the GST applicable at the rate as confirmed/deemed confirmed in the bid or actual GST paid/payable by the bidder for that item. | Bidder understands that in case the change in HSN/SAC classification and corresponding rate of GST are as result of change in laws & regulations in accordance with GCC 19, then GST reimbursable to the bidder/Contractor shall be higher of the GST applicable at the rate as confirmed/deemed confirmed in the bid or actual GST paid/payable by the bidder for that item. | Provisions of bidding document shall remain unchanged. |
|  | Section II ITB 27 BDS 13 | The award prices of FEED Studies along with taxes and duties for respective bidder will be added in the evaluation of price bid for the main HVDC VSC Package, if the bidder participates in the bidding for the main HVDC VSC Package Package.... Bidder, in case of Indian bidder also means bidder himself or his parent/principal or Group company who participates in the bidding for the main HVDC VSC. | As per the Bidder's understanding, the FEED Studies comprising of FEED‐1 Study (Owner's present tender) and FEED‐2 Study (tender to be issued by Owner in due course after completion of FEED‐1 Study) is intended to facilitate the tendering of the main HVDC VSC package considering its unique and unprecedented technical challenges & complexities. Therefore, the award prices of the FEED Studies cannot be equated / compared with conventional bid evaluation parameters e.g. losses, domestic content, etc. that have been used in Owner's earlier HVDC bid package evaluations. Hence, the Owner is requested to delete this clause entirely. Alternatively, since the Owner intends to issue the tenders for FEED‐2 Study and main HVDC VSC package in due course, atleast the following modification to the clause is requested: The award prices of FEED Studies along with taxes and duties for respective bidder may be added as per suitable evaluation methodology (to be defined by the Owner later, i.e. at the time of the main HVDC VSC package bidding) in the evaluation of price bid for the main HVDC VSC Package, if the bidder participates in the bidding for the main HVDC VSC Package Package.... | Provisions of bidding document shall remain unchanged. |
|  | Section IV GCC 1.1 (f) GCC 1.1 (i) | “Contractor’s Equipment” means all plant, facilities, equipment, machinery, tools, apparatus, appliances or things of every kind required in or for installation, completion and maintenance of Facilities that are to be provided by the Contractor, but does not include Plant and Equipment, or other things intended to form or forming part of the Facilities. "Defect Liability Period” means the period of validity of the warranties given by the Contractor commencing at Completion of the work during which the Contractor is responsible for rectification of work. | No hardware or software or licenses will be delivered as per the defined scope of FEED‐1 Study. Hence, Bidder requests deletion of these terms, as these are not relevant for this package. | Please Refer Amendment -1 |
|  | Section IV GCC 1.1 (t) | ‘Technical Specialist’ shall mean the Firm/Agency/Bidder whose proposal has been accepted by the Employer for the Award of the work and shall include his legal representatives, successors and permitted assignee. | Bidder could not find the term 'Technical Specialist' anywhere in the GCC / SCC. Hence, Bidder requests deletion of this clause, as the term "Contractor" is already defined at GCC 1.1 (e). | Please Refer Amendment - 1 |
|  | Section IV GCC 1.1 (u) | Work’ or ‘Study’ or ‘Assessment’ or ‘Services’ shall mean the complete study/work as specified in the scope of work as per bidding documents and technical specification. | Bidder could not find the term 'Assessment' anywhere in the GCC / SCC. Bidder understands that this is a typo error, and should be replaced by "Assignment". Please amend the definition accordingly. | Please Refer Amendment - 1 |
|  | Section IV GCC 1.1 (v) | The Time of completion of Contract: Unless otherwise terminated under the provisions of any other relevant clause of the document, contract shall be deemed to have been completed after issuance of the certification from Officer in Charge, that there is no demand outstanding against the contractor and all liabilities under the contract have been satisfactorily fulfilled by the contractor. | Bidder requests modification in the clause as below: The Time of completion of Contract: Unless otherwise terminated under the provisions of any other relevant clause of the document, contract shall be deemed to have been completed after issuance of the certification from Officer in Charge in accordance with GCC 7 (SCC no. 4), that there is no demand outstanding against the contractor and all liabilities under the contract have been satisfactorily fulfilled by the contractor. | Provisions of Bidding documents shall prevail. |
|  | Section IV GCC 4 Section V SCC 2 Section VI Form 5 ‐ Appendix 4 | Time for Completion Time for Completion | Considering the highly specialized nature of work and quantum of studies involved, completion time of 4 months cannot be confirmed. Bidder requests for Time of Completion of 9 (Nine) Months, and inclusion of following clause: "The Owner will ensure that it fulfils its obligations regarding timely provision of required inputs / data / approvals, etc. to achieve the above. Refer Appendix‐3A to the Contract Agreement regarding Owner's Obligations." | Provisions of Bidding documents shall prevail. |
|  | Section IV GCC 5 | Contractor’s responsibility shall be as mentioned in Volume – II Technical specification of the bidding documents. | Bidder has provided initial preliminary set of comments to Vol‐II in separate Annexure. Bidder requests Owner to extend the deadline for submission of comments mentioned in ITB 6 by atleast one (1) week. Owner is requested to refer Bidder's email dated 31 August, 2022 in this regard. | Agreed |
|  | Section IV GCC 7 Section V SCC sr. no. 3 | Owner/Employer reserves the right to participate in the Feed Study being carried out by the contractor (s) as and when required or is necessary. | - Owner's right to participate in the FEED‐1 Study is understood to mean fulfilment of Owner's obligations as per GCC 6 (see Bidder's pre‐ bid comment in this regard) i.e. ‐ Providing required inputs, network data, etc. for the FEED‐1 Study to be carried out by the Contractor, ‐ Approval of assumptions used by the Contractor before start of the different studies, ‐ Review and approval of the study results, in accordance with the technical specifications and prevailing standards / regulations. Owner is requested to confirm Bidder's understanding. | - Condition of Bidding Documents are clear. Bidder is also requested to refer Amendment-1. |
|  |  |  | - Bidder wishes to clarify that no training to Owner's personnel or visit of Owner's personnel to Bidder's offices (or their collaborator's offices) is foreseen as part of the FEED‐1 Study. Owner is requested to confirm Bidder's understanding. | 2. Training is not envisaged in the subject package; however other provisions of Bidding documents shall prevail. |
|  | Section IV GCC 6 | Void | Bidder requests to rename this clause as "Owner's Responsibility" and therein include Owner's obligations to ensure smooth and timely completion of the FEED‐1 Study package. Following obligations are proposed for inclusion under this clause: "6. Owner's Responsibility - The Owner will ensure that it fulfils its obligations regarding timely provision of required inputs / data / approvals, etc. to achieve the time for commencement and completion as per GCC 4. - Timeline of Inputs / Data / Approvals to be furnished to successful Bidder / Contractor by Owner: - Inputs and Network Data for FEED‐1 Study including validated PSS/E network files ‐ With the NoA - Confirmation by Owner of assumptions made by Contractor to be used as basis of studies ‐ Within 1 week of submission by Contractor. - Approvals of engineering submission by Contractor ‐ Within 1 week (for critical documents), Within 3 weeks (for other documents) - Other inputs/data as defined in Appendix‐3A to Contract Agreement" Details for d) above will be furnished by the Bidder as part of the Work Completion Schedule, or in next round of pre‐bid clarifications. | Refer Amendment – 1 |
|  | Section IV GCC 7.1 GCC 7.2 | Rejection of any or all offers/Reports without assigning any reason whatsoever. Rejection of any offer/Reports with incomplete scope of works or which is an incomplete offer/Reports in the opinion of the Employer. | - Please clarify what is meant by "Offers" in GCC 7.1 & GCC 7.2. In other words, please define the scope and purpose of the offers to be submitted by the Contractor during the course of execution of FEED‐1 Study. - "Without assigning any reason" (GCC 7.1) and "in the opinion of the Employer" (GCC 7.2) are not acceptable. It is fair to expect that Owner shall provide suitable reasons and justifications, which shall be based on valid technical standards / guidelines, scope / technical specifications (as per Vol‐II), etc. The Contractor shall have the right to respond. The matter shall be discussed and mutually agreed between the Owner and Contractor. | Please Refer Amendment -1 |
|  | Section IV GCC 7.3 | Review of the work performed by the contractor either by Employer or through another consultant separately appointed by Owner and ask for any clarification and changes/modifications to the work performed by the contractor. Such changes shall be mutually discussed and agreed between the Owner and the contractor and the same shall be incorporated by the contractor in his work without any cost to the Employer and without any dilution of the responsibility of the contractor. | The bid prices shall be subject to variation in case the changes/modifications leads to results in additional scope or work or task, new requirements, repetition of work, extension of time, etc. for reasons not attributable to the bidder/contractor, etc. Such changes in bid prices and/or completion time shall be mutually discussed and agreed between the Owner and the Contractor before the Contractor incorporates these changes in the work. | Please refer Sr. no. 26. Of Clarification-1 (Technical) dated 31/10/2022. |
|  | Section IV GCC 8.2 Section VI Form 5 Appendix 2 | The Contract Price shall be FIRM. FIRM PRICE BASIS | The Bidder understands that the Contract Price shall not be subject to variation on account of price indices and such factors. However, the Contract Price shall be subject to variation during the course of execution in case of additional scope or work or task, new requirements, changes, repetition of work, extension of time, etc. for reasons not attributable to the Contractor, etc. | Please Refer Amendment -1 |
|  | Section IV GCC 9.2 Section VI Form 5 ‐ Appendix 2 | If the Contractor fails to comply with the Time for Completion in accordance with Clause 9.1 above for the entire scope of work as per Technical specification, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to 0.05% (zero point zero five percent) of the Contract Price plus GST payable thereon for the entire scope of work, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each day which shall elapse between the relevant Time for Completion and the date stated in acceptance of final report of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price plus GST payable thereon for the entire scope of work, (or a part for which a separate time for completion is agreed). | Please add the below paragraph at end of the clause: "Such payment shall completely satisfy the Contractor’s obligation to attain Completion of Work or the relevant part thereof, as specified in the contract, within the Time for Completion including any extension thereof. The Contractor shall have no further liability whatsoever to the Employer in respect thereof." | Please Refer Amendment -1 |
|  | Section IV GCC 9.4. | Any mistake or inadequacy appear in the documents submitted by the Contractor, the Contractor shall perform at its own initiative and no extra cost to POWERGRID, all such services as shall be necessary to remedy the said mistake or inadequacy. ... Contractor shall indemnify and hold harmless POWERGRID against any and all claims, demands, and/or judgements of any nature brought against POWERGRID arising out of the services by Contractor and it's staff under this Agreement. The obligation under this paragraph shall survive the termination of this Agreement. | Please add the below paragraph at end of the clause: "The Contractor and the Employer shall not be liable to the other party for any indirect or consequential loss or damage, loss of use, loss of production, or loss of profits or interest costs, cost of capital, loss of power, cost of purchased or replacement power, loss of information and data, damages based on the Employer's third party contracts provided that this exclusion shall not apply to any obligation of the Contractor to pay liquidated damages to the Employer." | Refer Amendment - 1 |
|  | Section IV GCC 9.4 | Any mistake or inadequacy appear in the documents submitted by the Contractor, the Contractor shall perform at its own initiative and no extra cost to POWERGRID, all such services as shall be necessary to remedy the said mistake or inadequacy. | The provisions of this clause will not apply in case such mistake of inadequacy is caused for any reason(s) not attributable to the Contractor e.g. wrong input / data provided by the Owner in the tender/contract documents or changes due to Owner during execution, etc. | Refer Amendment - 1 |
|  | Section IV GCC 9.4 | The Contractor shall be further liable for the consequences resulting from errors and commissions due to negligence or from inadequacy on its part or on the part of its employees or associates or experts to the extent of the fees actually received by the Contractor. | Please modify as follows: The Contractor shall be further liable for the consequences resulting from errors and commissions due to negligence or from inadequacy on its part or on the part of its employees or associates or experts to the extent of the fees actually received by the Contractor under this Contract. | Refer Amendment - 1 |
|  | Section IV GCC 9.4 | Contractor shall indemnify and hold harmless POWERGRID against any and all claims, demands, and/or judgements of any nature brought against POWERGRID arising out of the services by Contractor and it's staff under this Agreement. The obligation under this paragraph shall survive the termination of this Agreement. | Please modify as follows: Contractor shall indemnify and hold harmless POWERGRID against any and all claims, demands, and/or judgements of any nature brought against POWERGRID arising out of negligence in the services by Contractor and it's staff under this Agreement, to the extent of the fees actually received by the Contractor under this Contract. The obligation under this paragraph shall survive the termination of this Agreement up to the term stated in GCC 9 (SCC 5). | Refer Amendment - 1 |
|  | Section IV GCC 11.4 | 11.4. The Contractor shall comply with all tax laws in force in India. The Contractor shall indemnify and hold harmless the Employer from and against any and all liabilities, interest, damages, claims, fines, penalties and expenses of whatever nature arising or resulting from the violation of such tax laws by the Contractor or its personnel, including the Subcontractors and their personnel. | Since the scope of the bid / contract is FEED‐1 Study only, Bidder understands that BOCW is not applicable. Please confirm Bidder's understanding. | Bidder’s understanding is correct. |
|  | Section IV GCC 11.5 | In case of Supply of Services, the Contractor shall invoice the Owner using the GSTIN of Owner in the state/UT in which the service or part thereof is to be rendered. | Bidder understands that the Owner's state in which the service (FEED‐ 1 Study) is to be rendered is Haryana. Please confirm this understanding. | Bidder’s understanding is correct. |
|  | Section IV GCC 11.7 Section VI Form 5 ‐ Appendix 3 | The Contractor shall be liable to take /maintain all necessary insurances at its own cost. Not Applicable. | - Considering the scope of work i.e. FEED‐2 Study, no insurances are foreseen to be taken by the Bidder/Contractor and no costs towards the same will be considered in the bid price. - The Owner is requested to specify the necessary insurances to be taken by the Contractor for the FEED‐1 Study package. In case no insurances are specified by Owner, the Bidder will follow Owner's confirmation "Not Applicable" mentioned in Appendix‐3 to Form of Contract Agreement. | As per Employer’s understanding, no insurance is required for the FEED Study. However, bidder must confirm their position in relation to the insurance requirement. In case any insurance is required for properly executing and completing the scope of work, the same must be included in bid. No compensation on this ground shall be admissible later on. |
|  | Section IV GCC 12.1 | The copyright in all the drawings, documents and other materials containing data and information for design(s) which have been developed by the Contractor or by any third party under the Contract shall remain vested in the Employer for the material and in the manner as detailed in the Technical Specification, | Please modify as follows: The copyright in all the drawings, documents and other materials containing data and information for design(s) which have been developed by the Contractor or by any third party under the Contract shall remain vested in the Employer Contractor for the material and in the manner as detailed in the Technical Specification, | Refer Amendment - 1 |
|  | Section IV GCC 12.1 | The Employer shall however be free to reproduce all drawings, documents and other material furnished to the Employer for the purpose of the Contract including, if required. | Please modify as follows: The Employer shall however be free to reproduce all drawings, documents and other material furnished to the Employer for the purpose of the Contract including, if required. | Refer Amendment - 1 |
|  | Section IV GCC 13.2 | The Contractor shall not use such documents, data and other information received from the Employer for any purpose other than such work and services as are required for the performance of the Contract. | Please modify as follows: The Employer and Contractor shall not use such documents, data and other information received from the Employer other party for any purpose other than such work and services as are required for the performance of the Contract. | Refer Amendment - 1 |
|  | Section IV GCC 17 | All documents prepared by the contractor in connection with the services to be provided by the contractor shall be the property of the owner. | Please modify as follows: All documents prepared by the contractor in connection with the services to be provided by the contractor shall be the property of the Contractor owner. | Bidding Condition shall remain unchanged. |
|  | Section IV GCC 17 | The contractor shall not prepare articles or photographs for publication or speeches about the work and/or plant, contracts and installation in which POWERGRID has an interest without prior written consent of POWERGRID | Please modify as follows: The contractor shall not prepare articles or photographs for publication or speeches about the work and/or plant, under this contracts and installation in which POWERGRID has an interest without prior written consent of POWERGRID, provided that such information is not already available in public domain. The successful bidder / contractor may cite this contract / work in their reference list and similar marketing announcements or publications. | Bidding Condition shall remain unchanged. |
|  | Section IV GCC 19 | If, after the date seven (07) days prior to the date of Bid Opening,...... | - Please modify as follows: If, after the date seven (07) twenty‐eight (28) days prior to the date of Bid Opening,...... - Please add at the end of this clause" "The provisions of this clause will also apply to changes in technical standards, guidelines, regulations, codes. etc." | Provisions of Bidding documents shall remain unchanged. |
|  | Section IV GCC 20 | Force Majeure is hereby defined as such as: - Natural phenomena including but not limited to floods, droughts, earthquakes and epidemics. - Acts of any government, domestic or foreign, including but not limited to war, declared or undeclared, priorities, quarantines, embargoes provided either party such causes. The contractor or the owner shall not be liable for delays. for other causes. | Please modify as follows: "Force Majeure is hereby defined as such as: - Natural phenomena including but not limited to floods, droughts, earthquakes and epidemics, including known pandemics (e.g. Covid‐ 19) whose future is unpredictable. - Acts of any government, domestic or foreign, including but not limited to war, declared or undeclared, priorities, quarantines, embargoes, including known acts (e.g. Russia‐Ukraine war) whose future is unpredictable. - Hostilities, including but not limited to invasion, act of foreign enemy, civil war, rebellion, revolution, insurrection, mutiny, usurpation of government, conspiracy, riot, civil commotion, lockdowns, cyberattacks. provided either party such causes. The contractor or the owner shall not be liable for delays. for other causes. Furthermore, in case of a Force Majeure situation, the Contractor shall get cost relief/compensation in case any additional cost is incurred by him." | Please Refer Amendment-1 |
|  | Section IV GCC 20 | Not Existing | Please add the below paragraph at end of the clause: "Contractor shall not be obligated to fulfill the Contract if such fulfillment is prevented by any impediments arising out of national or international foreign trade or customs requirements or any embargoes or other sanctions. The Parties acknowledge the worldwide outbreak of the COVID‐19 pandemic, which is likely to affect the execution of the contract. The Parties agree that the Contractor shall be entitled to reasonable adjustments of the delivery schedule / milestones / completion time as well as to reimbursement of costs to the extent the delay and the costs are caused directly or indirectly by the outbreak of COVID‐19. The Parties also acknowledge that the outbreak of the military conflict and / or any events related thereto (the “Conflict”) between Ukraine and Russia is likely to negatively affect usual business activities around the globe and /or the execution of the contract in various ways, whether known, unknown, whether foreseeable or unforeseeable. Therefore, the Parties agree that the Contractor shall not be liable for any negative impact or impediment of its performance obligations under or in connection with this contract arising or being aggravated in connection with the Conflict (the “Impact”). Accordingly, the Contractor shall be entitled to an extension of time for execution and / or an adjustment of the contract price and / or other reasonable adjustments to the contract to the extent required to mitigate and / or compensate the above mentioned Impact. | Please Refer Amendment-1. |
|  | Section IV GCC 21.1 | The Time(s) for Completion specified shall be extended if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: a. ... ..... e. ... by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor. | Bidder request for modification to the clause as below: "The Time(s) for Completion specified shall be extended and equitable costs paid to the Contractor if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: a. ... ... e. ... (f) any default or breach of the Contract by the Employer, or any activity, act or omission of the Employer, or employees / representative(s) of Employers, or any other contractors / consultants employed by the Employer, g) Non‐fulfilment of any of its obligationa under the Contract by Owner e.g. delay in providing the inputs / data / approvals etc., by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor. | Provisions of Bidding documents shall prevail. Bidder may also Refer Amendment-1 |
|  | Section IV GCC 21.2 | Except where otherwise specifically provided in the Contract, the Contractor shall submit to the Project Manager a notice of a claim for an extension of the Time for Completion, together with particulars of the event or circumstance justifying such extension as soon as reasonably practicable after the commencement of such event or circumstance. | The Owner has not defined the term "Project Manager" elsewhere in the GCC, hence for sake of uniformity please modify the paragraph as below: Except where otherwise specifically provided in the Contract, the Contractor shall submit to the Project Manager Officer‐in‐Charge / Employer a notice of a claim for an extension of the Time for Completion and associated cost compensation, together with particulars of the event or circumstance justifying such extension within 14 days or as soon as reasonably practicable after the commencement of such event or circumstance. | Please Refer Amendment-1 |
|  | Section IV GCC 22.1 GCC 16 | Except as otherwise specifically provided in the contract all disputes concerning questions of fact arising under the contract shall be decided by the Officer‐in‐charge subject to a written appeal by the contractor to the Officer‐ in‐charge whose decision shall be final to the parties hereto. On all matters pertaining to execution of the contract, the contractor shall directly interact with the Officer‐in‐Charge. | Bidders requests Owner to clarify the nomination / selection process of the Officer‐in‐Charge. | Please Refer Amendment-1 |
|  | Section IV GCC 22.1 | Except as otherwise specifically provided in the contract all disputes concerning questions of fact arising under the contract shall be decided by the Officer‐in‐charge subject to a written appeal by the contractor to the Officer‐ in‐charge whose decision shall be final to the parties hereto. Any disputes or differences including those considered as such by only one of the parties arising out of or in connection with the contract shall be to the extent possible settled amicably between the parties. If amicable settlement cannot be reached then all disputed issues shall be settled by arbitration as provided in clause No. 23 herein below. | Bidder requests to modify the clause as below: Except as otherwise specifically provided in the contract all disputes concerning questions of fact arising under the contract shall be decided by the Officer‐in‐charge subject to a written appeal by the contractor to the Officer‐in‐charge whose decision shall be final to the parties hereto. The Office‐in‐Charge shall give written notice of his decision within a period of fifteen (15) days after being requested by Contractor to do so. In the event the Officer‐in‐Charge fails to notify his decision as aforesaid within fifteen (15) days, the Contractor may decide to go for Arbitration. Any disputes or differences including those considered as such by only one of the parties arising out of or in connection with the contract or decision of the Officer‐in‐charge shall be to the extent possible settled amicably between the parties. If amicable settlement cannot be reached then all disputed issues shall be settled by arbitration as provided in clause No. 23 herein below. | Provisions of Bidding documents shall prevail. |
|  | Section IV GCC 23.4 | Notwithstanding the existence of any dispute or difference and/or reference for arbitration, the Bidder shall proceed with and continue without hindrance the performance of the work under the contract with due diligence and expedition in a professional manner and the payment due to the Bidders shall not be withheld by the owner on account of such difference or arbitration proceedings unless such payment is subject matter of the arbitration. | Bidder requests modification in the clause as below: Notwithstanding the existence of any dispute or difference and/or reference for arbitration, the Bidder shall proceed with and continue without hindrance the performance of the work under the contract with due diligence and expedition in a professional manner unless such part or whole of the works is a subject matter of the arbitration | Provisions of Bidding documents shall remain unchanged. |
|  | Section IV GCC 23.8 | During settlement of disputes and arbitration proceedings, both parties shall be obliged to carry out their respective obligations under the contract. | Bidder requests modification in the clause as below: During settlement of disputes and arbitration proceedings, both parties shall be obliged to carry out their respective obligations under the contract, unless such obligations are subject matter of the dispute or arbitration. | Provisions of Bidding documents shall remain unchanged. |
|  | Section IV GCC 24 | Not existing | Bidder requests Owner to add the following provision: "In the event of termination of the Contract under GCC Clause 24, the Employer shall pay to the Contractor the following amounts: - the Contract Price, properly attributable to the Work or parts thereof executed by the Contractor as of the date of termination, - the costs reasonably incurred by the Contractor directly or indirectly attributable to the termination, such as any amounts to be paid by the Contractor to its Subcontractors in connection with the termination of any subcontracts, including any cancellation charges, the cost of satisfying all other obligations, commitments and claims that the Contractor may in good faith have undertaken with third parties in connection with the Contract and that are not covered by paragraphs (a) through (b) above." | Bidding Condition shall remain unchanged. |
|  | Section IV GCC 24.1 | The Owner may without prejudice to any other remedy for breach of contract, by written notice of default sent to the contractor, terminate the contract in whole or in part: - if the contractor fails to deliver any or all of the services within the time period(s) specified in the contract or any extension thereof granted by the Owner in writing. if the contractor fails to perform any other obligation(s) under the contract; or | Bidder requests modification in the clause as below: The Owner may without prejudice to any other remedy for breach of contract, by written notice of default sent to the contractor, terminate the contract in whole or in part: - if the contractor persistently fails to deliver any or all of the services within the time period(s) specified in the contract or any extension thereof granted by the Owner in writing, and including the additional period for which Owner is entitled to recover liquidated damages for delay as per GCC 9.2. - if the contractor persistently fails to perform any other material obligation(s) under the contract; or | Bidding Condition shall remain unchanged. |
|  | Section IV GCC 25 | The obligations stipulated in the Bidding documents can only be suspended in the case of any particular item of work, in the event of Force Majeure as defined in Clause No. 15 herein or as a result of an agreement between the parties. | Please refer the underlined text ‐‐ Bidder is of the opinion that it is not complete, and requests Owner to clarify the intent of this text. | Refer Amendment-1 |
|  | Section IV GCC 25 | Not Existing | Please add a new sub clause as below: "In the event any of the following occurs, Contractor may at its option suspend the provision of its obligations under this Contract: - Owner fails to make payment of any amount within 30 days after it has become due and payable, or - Owner fails to perform its obligations necessary for the Contractor to deliver or complete the Work, or - Delivery and/or completion of the Work is prevented by export or other legally mandated restrictions for more than 6 months; or - Owner is insolvent. In the event Contractor suspends the provision of its obligations, Owner shall pay the Contractor all additional costs incurred due to such suspension." | Refer Amendment-1 |
|  | Appendix 1 ‐ Terms and Procedure of Payment 7 | 7. Terms of Payment for Feed Study is as Mentioned Below 7.1.60% of total of FEED‐1 or FEED‐2 Study Payment shall be released after submission of duly signed FEED‐1 or FEED‐2 report as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 7.2. 30% of FEED‐1 and FEED ‐2 Study payments shall be released after clarification by Bidder and acceptance of respective report by POWERGRID. 7.3 7.3. Final 10% of FEED‐1 and FEED ‐2 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. | The Bidder requests for modification of the clause as below: - Terms of Payment for Feed Study are as mentioned below: - 10% of total FEED‐1 Study Contract Price shall be released as interest free advance within 15 days of submission of Advance Bank Guarantee in favour of the Employer for an equivalent amount. 7.1.60% 7.2 80% of total of FEED‐1 or FEED‐2 Study Payment Contract Price shall be released progressively on pro‐rata basis after submission of duly signed FEED‐1 or FEED‐2 report as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 7.2. 30% 7.3 20% of FEED‐1 and FEED ‐2 Study payments Contract Price shall be released progressively on pro‐rata basis after clarification by Bidder and acceptance of respective report by POWERGRID. 7.3 7.3. Final 10% of FEED‐1 and FEED ‐2 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. | Provisions of Bidding documents shall remain unchanged. |
|  | Appendix 1 ‐ Terms and Procedure of Payment 7 | 7.3 7.3. Final 10% of FEED‐1 and FEED ‐2 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. | The Bidder requests for deletion of this clause for reasons mentioned below. As per the Bidder's understanding, the FEED Studies comprising of FEED‐1 Study (Owner's present tender) and FEED‐2 Study (tender to be issued by Owner in due course after completion of FEED‐1 Study) are intended to facilitate the tendering of the main HVDC VSC package considering its unique and unprecedented technical challenges & complexities. The payment for the FEED‐1 Study becomes due to the Contractor immediately upon its completion, and cannot be linked with the Bidder's/Contractor's participation in Owner's future tender for the main HVDC VSC package which is yet to be issued. The Bidder/Contractor of FEED‐1 Study cannot take responsibility for a future tender for which the timelines, scope of work, terms & conditions, etc. are unknown & unpredictable at this point of time. | Provisions of Bidding documents shall remain unchanged. |
|  | Appendix 1 ‐ Terms and Procedure of Payment 7 | In accordance with the provisions of Condition of Contract, the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules. The Contractor may make applications for payment in respect of part deliveries as work proceeds. | The Bidder proposes to submit the Price Breakdown (without prices) e.g. as % of total price, as part of First Envelope submission. This can be discussed and mutually agreed during the post‐bid discussion, prior to issuance of the Notice of Award. | Provisions of Bidding documents shall remain unchanged. |
|  | Appendix 1 ‐ Terms and Procedure of Payment 2, 3 5, 6 7.4 |  | Please refer our comments to similar provisions appearing elsewhere in the tender e.g. Section‐I (IFB), Section‐II (ITB), Section‐III (BDS), etc. viz. Pre‐Bid Queries sr. nos. 1, 2 and 14 respectively. | Provisions of Bidding documents shall prevail. |
|  | Appendix 1 ‐ Terms and Procedure of Payment Section VI Sample Forms and Procedures |  | Appendix 1‐ Terms and Procedures of Payment has been provided in "Section‐VI_Sample Forms and Procedures (SFP).docx" as part of Form of Contract Agreement, as well as separately attached as a Word file "Appendix‐1 Terms and Procedure of Payment.docx". Kindly confirm which one of the two files needs to be considered for bidding / contract purpose. | Appendix 1‐ Terms and Procedures of Payment has been provided in "Section‐VI_Sample Forms and Procedures (SFP).docx" as part of Form of Contract Agreement to be considered. Also Refer Amendment -1. |
|  | Section VI Sample Forms and Procedures 6a.Performance Security Form 6.a. | Not Existing | Bidder understands that the performance security shall be interpreted under Indian law with the jurisdiction of Courts of New Delhi. Kindly confirm Bidder's understanding. Further, Bidder requests to add the following clause in the Performance Security Form: "After expiry of this performance security guarantee, Employer will immediately return this performance security guarantee to the Contractor without any further requests by the Contractor." | Provisions of Bidding documents shall remain unchanged. |
|  | Section VI Form 3 | FORM OF 'NOTIFICATION OF AWARD OF CONTRACT' FOR SUPPLY OF PLANT AND EQUIPMENT .... Sub. :Notification of Award for Supply of Goods Contract for ……….. ..... 2.1 The scope of work under this Notification of Award (NOA). under the Contract for the construction of …… (insert name of Package alongwith name of the Project) ……., unless. this NOA. | As per Section‐I (IFB), this tender is for Front End Engineering & Design Study Services only (FEED‐1 Study). Please correct the highlighted text in Form 3 suitably. | Refer Amendment -1 |
|  | Section VI Form 5 | 1.1 Contract Documents ... VOLUME – A - This Contract Agreement and the Appendices thereto. - Notification of Award Ref. No. …………..……………. dated ………… VOLUME – B - “Bidding Documents” comprising of the following: - Volume –I of Bidding Documents (Document Code No. ), read in conjunction with Amendments …. to …… to the Bidding Documents. - Volume –II of Bidding Documents (Document Code No. ) comprising of Technical Specifications. .... | For sake of clarity and smooth execution of the contract, please modify the clause as follows: "1.1 Contract Documents ... VOLUME – A - This Contract Agreement and the Appendices thereto. - Notification of Award Ref. No. …………..……………. dated ……… - Post‐Bid Discussions on various dates from ……………. to ……………. resulting into the Minutes of Meeting / Record Notes of Post Bid Discussions enclosed as APPENDIX (NOA)‐1. VOLUME – B 3. “Bidding Documents” comprising of the following: - Volume –I of Bidding Documents (Document Code No. ), read in conjunction with Amendments …. to ……, Errata .... to , Clarifications .... to to the Bidding Documents. - Volume –II of Bidding Documents (Document Code No. ) comprising of Technical Specifications, read in conjunction with Amendments …. to ……, Errata .... to ...., Clarifications .... to to the Technical Specifications. .... | Refer Amendment -1. |
|  | Section VI Form 5 | 1.2 Order of Precedence In the event of any ambiguity or conflict between the Contract Documents listed above, the order of precedence shall be the order in which the Contract Documents are listed in Article 1.1 (Contract Documents) above. | For sake of clarity and smooth execution of the contract, please modify the clause as follows: "1.2 Order of Precedence In the event of any ambiguity or conflict between the Contract Documents listed above, the order of precedence shall be the order in which the Contract Documents are listed in Article 1.1 (Contract Documents) above (i.e. 1. having highest precedence, followed by 2. and so on). | Provisions of Bidding documents shall prevail. |
|  | Section VI Form 5 ‐ Appendix 5 | Appendix 5 GUARANTEES, LIQUIDATED DAMAGES FOR NON – PERFORMANCE | Bidder requests to include this Appendix with appropriate serial number in Article 4 of the Contract Agreement, as Appendix‐5 is named as Contract Co‐ordination Procedure in same Article‐4. Furthermore,it is understood that Appendix‐5 (Contract Co‐ordination Procedure) will be prepared and finalized during Post‐Bid Discussion in accordance with GCC 16. | Please refer Amendment -1 |
|  | Bid Form, Price Schedules & Technical Data Sheets Attachment 8 Bid Form, Price Schedules & Technical Data Sheets Attachment 8 | General | Format of Integrity Pact has been provided in the Excel file "First Envelope and Bid Form.xls" as well as separately attached as a Word file "04_Attachment‐(Integrity Pact).doc". Kindly confirm which one of the two files needs to be considered for bidding/contract purpose. | Format of Integrity Pact has been provided in the Excel file "First Envelope and Bid Form.xls" or its revision if any to be considered. |
|  | Price Schedule Sch‐1 | Cell B19 ‐ Township for 132/33 kV Silapathar (new) Cell F20 ‐ Civil works | In accordance with ITB 5.3, we request to make required corrections in the text of cells B19 and F20 of Sch‐1. | Please refer Amendment -1 |