| Sl. No. | Clause ref. | Existing Provision of the Bidding Document | Query asked by the bidders | Comment |
| --- | --- | --- | --- | --- |
|  | Amendment-1 Sl. No: 23 GCC Cl. 29, Section- IV | 29.2.3 If before or during the preparation of the Change Proposal it becomes apparent that the aggregate effect of compliance therewith and with all other Change Orders that have already become binding upon the Contractor under this GCC Clause 33 would be to increase or decrease the Contract Price as originally set forth in Article 2 (Contract Price and Terms of Payment) of the Contract Agreement by more than the percentage if specified in SCC, the Employer and the Contractor shall mutually agree on specific rates for valuation of the Change beyond the specified percentage. | Kindly check the GCC Clause 33 referred in this clause. It is not matching. Please modify. | Refer Amendment-III, Sl. No 1, Vol-I |
|  | Amendment-1 Sl. No: 23 GCC Cl. 29, Section- IV | 29.2.3 If before or during the preparation of the Change Proposal it becomes apparent that the aggregate effect of compliance therewith and with all other Change Orders that have already become binding upon the Contractor under this GCC Clause 33 would be to increase or decrease the Contract Price as originally set forth in Article 2 (Contract Price and Terms of Payment) of the Contract Agreement by more than the percentage if specified in SCC, the Employer and the Contractor shall mutually agree on specific rates for valuation of the Change beyond the specified percentage. | There is no such percentage stated in SCC as mentioned in this clause. Kindly consider 15% of Contract Price as maximum limit for Change Orders and Pending Agreement Amendment. | Refer Amendment- III, Sl. No 2, Vol-I |
|  | Amendment-1 Sl. No: 24 GCC Cl. 30, Section- IV | 30.2.3 The Contractor’s Representative may, subject to the approval of the Employer (which shall not be unreasonably withheld), at any time delegate to any person any of the powers, functions and authorities vested in him or her. Any such delegation may be revoked at any time. Any such delegation or revocation shall be subject to a prior notice signed by the Contractor’s Representative, and shall specify the powers, functions and authorities thereby delegated or revoked. No such delegation or revocation shall take effect unless and until a copy thereof has been delivered to the Employer and the Project Manager. Any act or exercise by any person of powers, functions and authorities so delegated to him or her in accordance with this GCC Sub-Clause 13.2.3 shall be deemed to be an act or exercise by the Contractor’s Representative. | Kindly check the GCC Clause 13.2.3 referred in this clause. It is not matching. | Refer Amendment- III, Sl. No 3, Vol-I |
|  | Amendment-1 Sl. No: 13 GCC Cl. 9, Section-V | The below clause is deleted from SCC as per the amendment Sl. No: 13 : Supplementing Sub-Clause: The Liability Period shall be 03 months from the date of submission of final report and acceptance of the same. | Since the Liability Period of 3 months is not applicable now, we understand that the Contractor's obligations specified under GCC 9.4. Liability of the Contractor is applicable only till completion of acceptance of the final report by the Owner. Please confirm. | Provision of bidding document is amply clear. |
|  | Section-IV_General Condition of contract GCC Cl. 10.2 | GCC 10.2: .................. a. The Liability Period covered under the said performance security shall stand extended and the Contractor shall accordingly extend the validity of the Contract Performance Security to be furnished by the period of delay, over and above the period required as per the Contract | Since the Liability Period of 3 months is not applicable now, we kindly request you to delete the references to the Liability Period mentioned in this clause. | Refer Amendment- III, Sl. No 5, Vol-I |
|  | Amendment-1 Sl. No: 24 GCC Cl. 30, Section- IV | …............................. ................................ 30.1 If the Project Manager is not named in the Contract, then within fourteen (14) days of the Effective Date, the Employer shall appoint and notify the Contractor in writing of the name of the Project Manager. The Employer may from time to time appoint some other person as the project Manager in place of the person previously so appointed, and shall give a notice of the name of such other person to the Contractor without delay. The Employer shall take all reasonable care to see that no such appointment is made at such a time or in such a manner as to impede the progress of work on the Facilities. The Project Manager shall represent and act for the Employer at all times during the currency of the Contract. All notices, instructions, orders, certificates, approvals and all other communications under the Contract shall be given by the Project Manager, except as herein otherwise provided. ................................ ............................... | "Facilities" word is not relevant to the scope of work covered under this contract. Please correct the same. | Refer Amendment- III, Sl. No 4, Vol-I |
|  | Amendment-1 Sl. No: 19 GCC Cl. 30, Section- IV | 20. FORCE MAJEURE …..................... …..................... …..................... | Pursuant to Amendment-1, Force majeure clause is replaced with a new clause. Request to add COVID-19 as one of the Force Majeure event in the new clause. | Provision of bidding documents will remain unchanged. |
|  | Amendment-1 Sl. No: 5 ITB Cl 20.7, Section- II | Replacing Cl 20.7 20.7.Bids containing deviations from critical provisions relating to GCC Clauses 28 (Governing Law), 5 (Contractor’s Responsibilities), 8.4 (Terms of Payment), 10.1 (Performance Security), 11 (Taxes and duties), 18 (Patent Indemnity), 22.1 (Settlement of Disputes), 23 (Arbitration) will be considered as non-responsive and Appendix 2 to the Form of Contract Agreement (Price Adjustment) will be considered as non responsive. | Kindly requesting you to remove "8.4 (Terms of Payment)" from this clause and allow the Bidder to propose suitable deviations on the Terms of Payment. | Provision of bidding documents will remain unchanged. |
|  | Clarification – 1 (Commercial) Section-VI (Vol-1), Sample Forms and Procedures Appendix - 1 TERMS AND PROCEDURES OF PAYMENT | 60% of total of FEED-1 Study Payment shall be released after submission of duly signed FEED-1 report as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 30% of FEED-1 Study payments shall be released after clarification by Bidder and acceptance of respective report by POWERGRID. Final 10% of FEED-1 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. | we once again request you to consider the following changes in the Terms of Payment: 20% as Advance Payment 60% of total of FEED-1 Study Payment shall be released based on agreed delivery milestone and after submission of duly signed FEED-1 respective reports as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 20% of FEED-1 Study payments shall be released after clarification by Bidder and acceptance of respective report by POWERGRID. Final 10% Payment of FEED-1 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. | Provision of bidding documents will remain unchanged. |
|  | Clarification – 1 (Commercial) Sl. No: 32 GCC Cl 7.3, Section- IV | Owner's Reply: Please refer Sr. no. 26. Of Clarification-1 (Technical) dated 31/10/2022. | Pursuant to the technical clarifications, Sl. No. 26, The Employer shall also have the right to amend inputs data and Customer in such event shall be liable only for changes in services/labor cost related thereto, and corresponding extension of time. Please confirm that any such change in the input data shall be governed by the Clause 29 (Change in Contract Elements) added by way of Amendment-1. | Provision of bidding documents will remain unchanged. |
|  | Amendment-1 Sl. No: 20 GCC-Cl 21.1, Section-IV | Replace Clause 21 as below: 21.Extension of Time for Completion The Time(s) for Completion specified in the SCC shall be extended if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: a.Any substantial change in the scope of work. b.any occurrence of Force Majeure as provided GCC Clause 20. c.any suspension order given by the Employer hereof or reduction in the rate of progress pursuant to GCC Cl. 25. d) any changes in laws and regulations as provided in GCC Clause 19 or e.any other manner specifically mentioned in the Contract by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor. | Pursuant to Amendment-1, Extension of Time for Completion clause is replaced with the new one. Request to add the following ground for Contractor’s entitlement towards extension of time for completion: (f) Any delay to Work for reason attributable to the Employer including delay in review / approval. | Provision of bidding documents will remain unchanged. |
|  | Sl. No: 20 GCC-Cl 21.2, Section-IV | 21.2.Except where otherwise specifically provided in the Contract, the Contractor shall submit to the Project Manager a notice of a claim for an extension of the Time for Completion, together with particulars of the event or circumstance justifying such extension as soon as reasonably practicable after the commencement of such event or circumstance. As soon as reasonably practicable after receipt of such notice and supporting particulars of the claim, the Employer and the Contractor shall agree upon the period of such extension. In the event that the Contractor does not accept the Employer’s estimate of a fair and reasonable time extension, the Contractor shall be entitled to refer the matter to Arbitration, pursuant to GCC Sub-Clause 23. | In the event of occurrence of any of the reason(s) listed under clause 21.1 for extension of Time for Completion, the Contractor shall have the right to compensation for additional costs incurred by the Contractor as a result of such reason. | Provision of bidding documents will remain unchanged. |
|  | Sl. No: 55 ITB 6.2, Section-II | The Bidder is advised to visit and examine the site (s) of the subject proposal and its surroundings and obtain for itself on its own responsibility and cost all information that may be necessary for preparing the bid and entering into a contract. The costs of visiting the site shall be at the Bidder’s own expense. | In accordance with Section‐I, IFB 2.4 the scope of this tender is limited to the 1st part of the Front‐End Engineering and Design Study i.e. FEED‐1 Study. Therefore, the requirements mentioned under ITB 6.2 are not relevant, and will not be considered in the Bidder's scope & costing. Owner is requested to confirm this understanding. Alternatively, Owner is requested to state the specific FEED‐1 Study tasks / deliverables (refer Vol‐II) under which such site visit is envisaged during the bidding and/or execution phase. Kindly clarify which clause in the Amendment-1 is referred here. | The clarification may be read as following: “Provision of bidding document shall prevail”. |
|  | Schedule-1 Vol-3, Price_schedule Rev- 01, Sch-1 | "Civil Works" | "Civil Works" is appearing in the item description. Please correct the same. | Refer Amendment- III, Sl. No 1, Vol-III |
|  | Clause No 1.1. Vol‐1 ‐ Sec IV ‐GCC | Group Company | Whether Group Company shall means wherein the Indian entity having technical experience referred under 2.1.2. of Annexure A BDS and the other qualified bidder having technical experience referred under 2.1.1. of Annexure A BDS, having a common source of control, directly or indirectly, so as to exercise a minimum equity participation of 26%, or appoint more than 50% of members of Board of Directors in the Indian bidder. | Refer Amendment-II, Sl. No 1, Vol-I |
|  | Section VI ‐ Appendix 4 | Time for Completion | Completing the FEED-1 in 4 months duration is not feasible. We kindly request you to consider 8 months duration for final report submission from the receipt of Input data and finalization/confirmation of assumptions by the Employer. | As per Bidding Documents Project Completion Schedule is negotiable and same shall be discussed during the Post Bid Discussion. |
|  |  | Terms of Payment: | Keeping in view the benefit of the pro-rata project progress, we request you to consider stage-wise report submissions with corresponding milestone –based payments. A mile –stone based payment schedule to be submitted by the bidder will be more suitable for this project. Considering above, we request you to review the stipulated payment terms and consider advance payment and mile-stone based payment schedule as we suggested in our pre-bid queries. We would also request you to delink the last 10% payment from submission of bid for main project tender. | “Provision of bidding document shall remain unchanged”. |
|  | Section II ITB 6.2 | The Bidder is advised to visit and examine the site (s) of the subject proposal and its surroundings and obtain for itself on its own responsibility and cost all information that may be necessary for preparing the bid and entering into a contract. The costs of visiting the site shall be at the Bidder’s own expense. | Bidder’s Pre bid Comment before Clarification-1 In accordance with Section‐I, IFB 2.4 the scope of this tender is limited to the 1st part of the Front‐End Engineering and Design Study i.e. FEED‐1 Study. Therefore, the requirements mentioned under ITB 6.2 are not relevant, and will not be considered in the Bidder's scope & costing. Owner is requested to confirm this understanding. Alternatively, Owner is requested to state the specific FEED‐1 Study tasks / deliverables (refer Vol‐II) under which such site visit is envisaged during the bidding and/or execution phase. |  |
|  |  |  | Bidder’s Comment after Clarification-1 Amendment-1 is missing. Bidder understands that this clause will be deleted and requests Owner to issue the missing amendment accordingly. | The clarification may be read as following: “Provision of bidding document shall prevail”. |
|  | Section II ITB 11.2 | The bid Prices quoted by the Bidder shall be Fixed during the performance of the contract and not subject to variation on any account | Bidder’s Pre bid Comment before Clarification-1 The Bidder understands that bid prices shall not be subject to variation on account of price indices and such factors. However, the bid prices shall be subject to variation during the course of execution in case of additional scope or work or task, new requirements, changes, repetition of work, extension of time, etc. for reasons not attributable to the bidder/contractor, etc. | “Provision of bidding document shall prevail”. Refer Amendment-I, Sr. No 23, Vol-I |
|  |  |  | Bidder’s Comment after Clarification-1 Amendment-1 is missing. Bidder understands that its comment is acceptable to Owner, and requests Owner to issue the missing amendment accordingly. |  |
|  | Section III Annexure‐A (BDS) Form of Joint Deed of Undertaking by the Parent / Principal / Group Company alongwith the Bidder | WHEREAS the “Employer” invited Bid as per its Specification No. ……………….. for Front End Engineering & Design (FEED) study for Transmission System for evacuation of RE Power Renewable energy parks in Leh (+/‐ 350kV, 5GW Pang‐ Kaithal Link) | For sake of uniformity and clarity of understanding, Bidder requests modification as follows: WHEREAS the “Employer” invited Bid as per its Specification No. ……………….. for FEED‐1 Study of Front End Engineering and Design (FEED) Study for ± 350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Haryana) associated with power generated from renewable energy park. Bidder understands that its comment is acceptable to Owner, and requests Owner to issue the missing amendment accordingly. | Please refer Amendment III, Sl 6, Vol-I for Revised Form of Joint Deed of Undertaking |
|  | Section III Annexure‐A (BDS) Form of Joint Deed of Undertaking by the Parent / Principal / Group Company alongwith the Bidder | Without in any way affecting the generality and total responsibility in terms of this Deed of Undertaking, the Parent/Principal/Group Company in particular hereby agrees to depute their technical experts from time to time to the Bidder’s/ Contractor’s Employer’s site/work/office as mutually considered necessary by the Employer, Bidder/ Contractor and the Parent/Principal/Group Company to ensure successful FEED study which includes but not limited to study of environmental conditions at Pang converter station and their impact on the equipment and HVDC system as a whole in accordance with Contract Specifications and If necessary, the Parent/Principal/Group Company shall advise the Contractor as well shall undertake necessary measures along with the Contractor to discharge the obligations under the contract. | Bidder’s Pre bid Comment before Clarification-1 Bidder requests deletion of this clause. Please refer Bidder's comment to ITB 11.3 and Vol‐II in this regard. Bidder also requests Owner to correct the numbering, for example there is no clause 3.0 between clauses 2.0 and 4.0 of present template. | Please refer Amendment III, Sl 6, Vol-I for Revised Form of Joint Deed of Undertaking |
|  |  |  | Bidder’s Comment after Clarification-1 Bidder understands that its comment is acceptable to Owner, and requests Owner to issue the missing amendment accordingly. Alternatively, Bidder requests Owner refer to it pre-bid comment sr. no. 74 issued prior to Owner's Clarification-1 / Amendment-1. The same has been repeated at sr. no. 6 of this list. |  |
|  | Section III Annexure‐A (BDS) Form of Joint Deed of Undertaking by the Parent / Principal / Group Company alongwith the Bidder | We, the Parent/Principal/Group Company and Bidder/ Contractor agree that this Undertaking shall be irrevocable and shall form an integral part of the Contract and further agree that this Undertaking shall continue to be enforceable till the Employer discharges it. | Bidder’s Pre bid Comment before Clarification-1 Bidder requests modification as follows: We, the Parent/Principal/Group Company and Bidder/ Contractor agree that this Undertaking shall be irrevocable and shall form an integral part of the Contract and further agree that this Undertaking shall continue to be enforceable till the Employer discharges it, or till the end of the liability period as per GCC 9 (SCC 5), whichever is earlier. Thereafter, Employer will immediately return this Undertaking to the Contractor without any further requests by the Contractor." | Please refer Amendment III, Sl 6, Vol-I for Revised Form of Joint Deed of Undertaking |
|  |  |  | Bidder’s Comment after Clarification-1 In view of sr. nos. 6 & 13 of Amendment-1, Bidder proposes modification in the text as below: We, the Parent/Principal/Group Company and Bidder/ Contractor agree that this Undertaking shall be irrevocable and shall form an integral part of the Contract and further agree that this Undertaking shall continue to be enforceable till the Employer discharges it, or till the end of the liability period Time for Completion as per GCC 4 9 (SCC 5), whichever is earlier. Thereafter, Employer will immediately return this Undertaking to the Contractor without any further requests by the Contractor." |  |
|  | Form of Joint Deed of Undertaking by the Parent / Principal / Group Company alongwith the Bidder Section III Annexure‐A (BDS) | Without in any way affecting the generality and total responsibility in terms of this Deed of Undertaking, the Parent/Principal/Group Company in particular hereby agrees to depute their technical experts from time to time to the Bidder’s/ Contractor’s Employer’s site/work/office as mutually considered necessary by the Employer, Bidder/ Contractor and the Parent/Principal/Group Company to ensure successful FEED study which includes but not limited to study of environmental conditions at Pang converter station and their impact on the equipment and HVDC system as a whole in accordance with Contract Specifications and If necessary, the Parent/Principal/Group Company shall advise the Contractor as well shall undertake necessary measures along with the Contractor to discharge the obligations under the contract. | In case Owner does not agree to delete this clause, then Bidder requests modification of this clause as follows: "Without in any way affecting the generality and total responsibility in terms of this Deed of Undertaking, the Parent/Principal/Group Company in particular hereby agrees to depute their technical experts (on chargeable basis) from time to time to the Bidder’s/ Contractor’s Employer’s site/work/office as mutually considered necessary by the Employer, Bidder/ Contractor and the Parent/Principal/Group Company to ensure successful FEED‐1 study which includes but not limited to study of environmental conditions at Pang converter station and their impact on the equipment and HVDC system as a whole in accordance with Contract Specifications and If necessary, the Parent/Principal/Group Company shall advise the Contractor as well shall undertake regarding any necessary measures to be undertaken by along with the Contractor to discharge the obligations under the contract." Please refer Bidder's comment to ITB 11.3 and Vol‐II in this regard. Bidder also requests Owner to correct the numbering, for example there is no clause 3.0 between clauses 2.0 and 4.0 of present template. Owner is requested to amend the Form of Joint Deed of Undertaking as per Bidder's original comment at sr. no. 74. | Provisions of Bidding Document shall prevail. Bidder may Please refer Amendment III, Sl 6, Vol-I for Revised Form of Joint Deed of Undertaking |
|  | Section III Annexure‐A (BDS) 2.1.1 Qualification Requirement (QR) | The bidder shall be a manufacturer of Voltage Source Converter (VSC) High voltage Direct Current Transmission equipment for the last seven (7) years or more as on the originally scheduled date of bid opening i.e. 21/09/2022 and who has implemented a contract wherein the scope involves engineering, manufacturing, supply, erection, testing and commissioning of at least one long distance VSC based HVDC transmission converter station or a VSC based Back‐to Back HVDC system of a unit rating of at least 250MW, along with associated auxiliary equipment and ancillary works and the VSC HVDC system should have been in Satisfactory Operation* for a period of not less than one year as on the originally scheduled date of bid opening i.e. 21/09/2022. | Bidder would like to bring to Owner's attention that in 2019, there was a global restructuring program for the Energy business which included the HVDC portfolio as well. Specifically, the Energy business was carved out and spun‐off into a new company, which included the transfer of assets, employees, credentials and references. Kindly refer separate submissions made by the Bidder in this regard. Hence, the Qualified Bidder [Company A] as per Cl. 2.1.1 of Annexure‐ A (BDS) is in existence for less than 7 years as on 21/09/2022 However, the Original Company [Company B] from which Company A was spun off had been manufacturing VSC HVDC equipment for more than 7 years prior to the spin‐off. Furthermore, the same Company B had implemented a contract wherein the scope involved engineering, manufacturing, supply, erection, testing and commissioning of at least one long distance VSC based HVDC transmission converter station or a VSC based Back‐to Back HVDC system of a unit rating of at least 250MW, along with associated auxiliary equipment and ancillary works and the VSC HVDC system had been in Satisfactory Operation for a period of not less than one year as on the originally scheduled date of bid opening i.e. 21/09/2022. In view of the above, Owner's acceptance of Bidder's understanding as below is requested: 1. Bidder understands that Company A will be deemed to be a manufacturer of VSC HVDC equipment for more than 7 years as on 21/09/2022. 2. Bidder understands that Company A will be deemed to have implemented the contract that was originally signed with Company B, wherein the scope involved engineering, manufacturing, supply, erection, testing and commissioning of at least one long distance VSC based HVDC transmission converter station or a VSC based Back‐to Back HVDC system of a unit rating of at least 250MW, along with associated auxiliary equipment and ancillary works and the VSC HVDC system had been in Satisfactory Operation for a period of not less than one year as on the originally scheduled date of bid opening i.e. 21/09/2022. Owner is requested to amend the Form of Joint Deed of Undertaking as per Bidder's original comment at sr. no. 75. | Please refer Amendment-II Sl. No 1, Vol-I |
|  | Section IV GCC 1.1 (v) | The Time of completion of Contract: Unless otherwise terminated under the provisions of any other relevant clause of the document, contract shall be deemed to have been completed after issuance of the certification from Officer in Charge, that there is no demand outstanding against the contractor and all liabilities under the contract have been satisfactorily fulfilled by the contractor. | Bidder’s Pre bid Comment before Clarification-1 Bidder requests modification in the clause as below: The Time of completion of Contract: Unless otherwise terminated under the provisions of any other relevant clause of the document, contract shall be deemed to have been completed after issuance of the certification from Officer in Charge in accordance with GCC 7 (SCC no. 4), that there is no demand outstanding against the contractor and all liabilities under the contract have been satisfactorily fulfilled by the contractor. |  |
|  |  |  | Bidder’s Comment after Clarification-1 Bidder requests for following text to be added to the clause: The Officer in Charge shall not unreasonably withhold the issuance of the certification of completion. If the Contractor has completed the Work but the Officer in Charge fails to issue the certification of completion, the Work shall be deemed to have been completed on the date the Contractor has issued a notice that the Work has been completed. | Provisions of Bidding documents shall remain unchanged |
|  | Section IV GCC 4 Section V SCC 2 Section VI Form 5 ‐ Appendix 4 | Time for Completion Time for Completion | Bidder’s Pre bid Comment before Clarification-1 Considering the highly specialized nature of work and quantum of studies involved, completion time of 4 months cannot be confirmed. Bidder requests for Time of Completion of 9 (Nine) Months, and inclusion of following clause: "The Owner will ensure that it fulfils its obligations regarding timely provision of required inputs / data / approvals, etc. to achieve the above. Refer Appendix‐3A to the Contract Agreement regarding Owner's Obligations." |  |
|  |  |  | Bidder’s Comment after Clarification-1 1. Time for Completion of 4 months is not feasible and cannot be confirmed. Hence, Bidder again requests for amending the Time for Completion as 9 (Nine) Months. Alternatively, Owner may confirm that Bidder is permitted to take deviation during the bid submission and mention the required Time for Completion based on review of final amendments & clarifications, and the same shall form the basis for contract award. 2. Bidder again requests for inclusion of following clause in accordance with Bidder's comment at sr. no. 10 of this list and as attachment Appendix-4A to Contract Agreement: "The Owner will ensure that it fulfils its obligations regarding timely provision of required inputs / data / approvals, etc. to achieve the above. Refer GCC 6 and Appendix-4A to the Contract Agreement regarding Owner's Obligations." | 1. As per Bidding Documents Project Completion Schedule is negotiable and same shall be discussed during the Post Bid Discussion. 2. Provisions of Bidding documents shall remain unchanged |
|  | Section IV GCC 6 | Void | Bidder’s Pre bid Comment before Clarification-1 Bidder requests to rename this clause as "Owner's Responsibility" and therein include Owner's obligations to ensure smooth and timely completion of the FEED‐1 Study package. Following obligations are proposed for inclusion under this clause: "6. Owner's Responsibility - The Owner will ensure that it fulfils its obligations regarding timely provision of required inputs / data / approvals, etc. to achieve the time for commencement and completion as per GCC 4. - Timeline of Inputs / Data / Approvals to be furnished to successful Bidder / Contractor by Owner: - Inputs and Network Data for FEED‐1 Study including validated PSS/E network files ‐ With the NoA - Confirmation by Owner of assumptions made by Contractor to be used as basis of studies ‐ Within 1 week of submission by Contractor. - Approvals of engineering submission by Contractor ‐ Within 1 week (for critical documents), Within 3 weeks (for other documents) - Other inputs/data as defined in Appendix‐3A to Contract Agreement" Details for d) above will be furnished by the Bidder as part of the Work Completion Schedule, or in next round of pre‐bid clarifications. |  |
|  |  |  | Bidder’s Comment after Clarification-1 Owner is requested to specify clear timelines for their obligations as this has significant impact on the Time for Completion and include these as Appendix-4A to Contract Agreement. Accordingly, Bidder proposes to add the following clause as amendment: "6.3 Once Contractor submits its final report complete in all respects and as per the deliverable in accordance with the technical specification, Employer shall review and issue its acceptance or clarification to the report within 30 15 days of submission. 6.4 Timeline of Inputs / Data / Approvals to be furnished to successful Bidder / Contractor by Owner: a) Inputs and Network Data for FEED-1 Study including validated PSS/E network files - With the NoA b) Confirmation by Owner of assumptions made by Contractor to be used as basis of studies - Within 1 week of submission by Contractor. c) Approvals of engineering submission by Contractor - Within 1 week (for critical documents), Within 2 weeks (for other documents)" | Provisions of Bidding Documents shall prevail, however Timeline related other inputs/Data /approval shall be discussed and mutually agreed during Post-Bid Discussion. |
|  | Section IV GCC 7 Section V SCC sr. no. 3 | Owner/Employer reserves the right to participate in the Feed Study being carried out by the contractor (s) as and when required or is necessary. | Bidder’s Pre bid Comment before Clarification-1 - Owner's right to participate in the FEED‐1 Study is understood to mean fulfilment of Owner's obligations as per GCC 6 (see Bidder's pre‐ bid comment in this regard) i.e. ‐ Providing required inputs, network data, etc. for the FEED‐1 Study to be carried out by the Contractor, ‐ Approval of assumptions used by the Contractor before start of the different studies, ‐ Review and approval of the study results, in accordance with the technical specifications and prevailing standards / regulations. Owner is requested to confirm Bidder's understanding. |  |
|  |  |  | Bidder’s Pre bid Comment before Clarification-1 Bidder wishes to clarify that no training to Owner's personnel or visit of Owner's personnel to Bidder's offices (or their collaborator's offices) is foreseen as part of the FEED‐1 Study. Owner is requested to confirm Bidder's understanding. |  |
|  |  |  | Bidder’s Comment after Clarification-1 1) Bidder has reviewed sr. nos. 11 & 12 of Amendment-1, however neither clarifies the Bidder's original comment regarding interpretation of Owner's right "to participate in the FEED study". Owner is requested to review Bidder's original comment at sr. no. 26 and either confirm Bidder's understanding, or clarify what is the expected role and involvement of Bidder in "Owner's participation in the FEED study". Bidder also refers to sr. no. 60 of Clarification-1 in response to Bidder's pre-bid query sr. no. 10. Bidder confirms that no international travel of their experts is required for the purpose of FEED Study in association with their Group Company and hence no cost will be considered towards the same in their bid price. However, Owner has not clarified their position regarding necessity of international travel of experts to India. In case Owner requires such international travel for their own purpose despite the Bidder / Contractor / associated Group Company not recommending the same, then these travel expenses will be paid to the Contractor under GCC 29. Above clarity is required as these will have impact on the Time for Completion and also the bid price. 2) Owner has not clarified their position regarding travel of Owner's engineers to other countries. Bidder confirms that no international travel of Onwer's engineers is recommended for the purpose of FEED Study in association with their Group Company. In case Owner requires such international travel for their own purpose despite the Bidder / Contractor / associated Group Company not recommending the same, then Owner may specify the details as the Bidder/Contractor needs to consider the impact on the Time for Completion and possibly also the bid price. | 1. Presently Owner do not envisage any expert travels, however in case any clarification/discussion is required same shall be resolved/discussed through Online meeting with experts. 2.Travel is not envisaged. |
|  | Section IV GCC 8.2 Section VI Form 5 Appendix 2 | The Contract Price shall be FIRM. FIRM PRICE BASIS | Bidder’s Pre bid Comment before Clarification-1 The Bidder understands that the Contract Price shall not be subject to variation on account of price indices and such factors. However, the Contract Price shall be subject to variation during the course of execution in case of additional scope or work or task, new requirements, changes, repetition of work, extension of time, etc. for reasons not attributable to the Contractor, etc. |  |
|  |  |  | Bidder’s Comment after Clarification-1 Amendment-1 is missing. Bidder understands that its comment is acceptable to Owner, and requests Owner to issue the missing amendment accordingly. | “Provision of bidding document shall prevail”. Refer Amendment-I, Sr. No 23, Vol-I |
|  | GCC 9.5 Amd-1 Completion Time Guarantee Cl 9.5 Limitation of Liability | Sr. No. 15 of Amendment-1 Adding new Clause; Cl 9.5 Limitation of Liability Except in cases of gross negligence or willful misconduct, a. the Contractor and the Employer shall not be liable to the other party for any indirect or consequential loss or damage, loss of use, loss of production, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the Contractor to pay liquidated damages to the Employer and b. the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed the total Contract Price, provided that this limitation shall not apply to the cost to any obligation of the Contractor to indemnify the Employer with respect to patent infringement. | Bidder requests for changes to clause as below: "Except in cases of gross negligence or willful misconduct, ..... b. the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed the total Contract Price, provided that this limitation shall not apply to the cost to any obligation of the Contractor to indemnify the Employer with respect to Contractor's patent infringement." | Provisions of Bidding documents shall remain unchanged. |
|  | Section IV GCC 11.7 Section VI Form 5 ‐ Appendix 3 | The Contractor shall be liable to take /maintain all necessary insurances at its own cost. Not Applicable. | Bidder’s Pre bid Comment before Clarification-1 - Considering the scope of work i.e. FEED‐2 Study, no insurances are foreseen to be taken by the Bidder/Contractor and no costs towards the same will be considered in the bid price. The Owner is requested to specify the necessary insurances to be taken by the Contractor for the FEED‐1 Study package. In case no insurances are specified by Owner, the Bidder will follow Owner's confirmation "Not Applicable" mentioned in Appendix‐3 to Form of Contract Agreement. |  |
|  |  |  | Bidder’s Comment after Clarification-1 Bidder refers to following text in Owner's clarification: "However, bidder must confirm their position in relation to the insurance requirement." As requested, Bidder confirms as follows: No insurances are foreseen or required to be taken by the Bidder/Contractor for properly executing and completing the scope of work. Hence, no costs towards the same will be considered in the bid price. | Provisions of Bidding documents is clear. |
|  | Section IV GCC 12.1 | The copyright in all the drawings, documents and other materials containing data and information for design(s) which have been developed by the Contractor or by any third party under the Contract shall remain vested in the Employer for the material and in the manner as detailed in the Technical Specification, The Employer shall however be free to reproduce all drawings, documents and other material furnished to the Employer for the purpose of the Contract including, if required. | Bidder’s Pre bid Comment before Clarification-1 Please modify as follows: The copyright in all the drawings, documents and other materials containing data and information for design(s) which have been developed by the Contractor or by any third party under the Contract shall remain vested in the Employer Contractor for the material and in the manner as detailed in the Technical Specification, The Employer shall however be free to reproduce all drawings, documents and other material furnished to the Employer for the purpose of the Contract including, if required. |  |
|  |  |  | Bidder’s Comment after Clarification-1 Bidder requests for modification in the clause as below: 12.1. The copyright in......The Employer/owner shall however be free to reproduce all drawings, documents and other material furnished to the Employer for the purpose of the Contract including, if required, For Tendering and contracting for the Main VSC Package provided that the Employer/owner ensures that the Contractor's copyrights are not violated and remain with the Contractor.. All models.....However, in case same needs to be shared with third parties it will be shared through tripartite the Employer shall ensure that the necessary contractual arrangements, suchs as NDA agreements, are in place to protect the Contractors intellectual property rights." | Provisions of Bidding Document shall prevail. |
|  | Section IV GCC 15.1 Progress Report | Review meetings between the owner and/or his authorised representative and Contractor will be held every month. | Considering the scope and nature of work, Bidder requests for below change to the clause: "Review meetings between the owner and/or his authorised representative and Contractor will be held every alternate month." | Shall be discussed during the award. |
|  | Section IV GCC 17 Handling of Documents | All documents prepared by the contractor in connection with the services to be provided by the contractor shall be the property of the owner. | Bidder’s Pre bid Comment before Clarification-1 Please modify as follows: All documents prepared by the contractor in connection with the services to be provided by the contractor shall be the property of the Contractor owner. |  |
|  |  |  | Bidder’s Comment after Clarification-1 Bidder understands that Owner's property rights over the documents prepared by the Contractor will be subject to the copyright provisions as per GCC 12.1 Accordingly, Bidder requests Owner to modify the clause as below: "All documents prepared by the contractor in connection with the services to be provided by the contractor shall be the property of the owner, however subject to provisions of GCC Clause 12.1." | Provisions of Bidding documents shall remain unchanged. |
|  | Section IV GCC 18.1 Patent Indemnity | The Contractor shall, subject to the Employer’s compliance with GCC Sub-Clause 18.2, indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, which the Employer may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright or other intellectual property right registered or otherwise existing at the date of the Contract. | Bidder requests Owner to modify the clause as below: "The Contractor shall, subject to the Employer’s compliance with GCC Sub-Clause 18.2, indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, which the Employer may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright or other intellectual property right registered or otherwise existing at the date of the Contract arising out of or in connection with any design, data, drawing, or other documents or materials provided or designed by or on behalf of the Contractor." | Provisions of Bidding documents shall remain unchanged. |
|  | Section IV GCC 19 Change in Laws and Regulations | If, after the date seven (07) days prior to the date of Bid Opening,...... | Bidder’s Pre bid Comment before Clarification-1 1. Please modify as follows: If, after the date seven (07) twenty-eight (28) days prior to the date of Bid Opening,...... - Please add at the end of this clause" - "The provisions of this clause will also apply to changes in technical standards, guidelines, regulations, codes. etc." |  |
|  |  |  | Bidder’s Comment after Clarification-1 Bidder understands that the provisions of this clause will also apply to changes in technical standards, guidelines, regulations, codes. etc. Kindly confirm Bidder's understanding since no reference date is mentioned in the bidding documents / technical specification for applicablity of standards, codes, etc. | Technical Standards shall be as per Annexure-7 of technical specification, including draft versions and shall be hold good after the date 07 days prior to the date of bid opening. |
|  | Section IV GCC 20 Amd-1 Force Majeure |  | Bidder’s Pre bid Comment before Clarification-1 Please add the below paragraph at end of the clause: "Contractor shall not be obligated to fulfill the Contract if such fulfillment is prevented by any impediments arising out of national or international foreign trade or customs requirements or any embargoes or other sanctions. The Parties acknowledge the worldwide outbreak of the COVID-19 pandemic, which is likely to affect the execution of the contract. The Parties agree that the Contractor shall be entitled to reasonable adjustments of the delivery schedule / milestones / completion time as well as to reimbursement of costs to the extent the delay and the costs are caused directly or indirectly by the outbreak of COVID-19. The Parties also acknowledge that the outbreak of the military conflict and / or any events related thereto (the “Conflict”) between Ukraine and Russia is likely to negatively affect usual business activities around the globe and /or the execution of the contract in various ways, whether known, unknown, whether foreseeable or unforeseeable. Therefore, the Parties agree that the Contractor shall not be liable for any negative impact or impediment of its performance obligations under or in connection with this contract arising or being aggravated in connection with the Conflict (the “Impact”). Accordingly, the Contractor shall be entitled to an extension of time for execution and / or an adjustment of the contract price and / or other reasonable adjustments to the contract to the extent required to mitigate and / or compensate the above mentioned Impact. In case Force Majeure conditions exceed 180 days for a single event, the parties may terminate the contract after mutual agreement." |  |
|  |  |  | Bidder’s Comment after Clarification-1 1) Bidder requests below changes to be added to the GCC clause 20.1 as amendment: "“Force Majeure” shall mean... (a) war, hostilities or warlike operations (whether war be declared or not), invasion, act of foreign enemy and civil war, (including but not limited to the ongoing Ukraine-Russia conflict), (d) Other unforeseen events like pandemic (including but not limited to the outbreak of the COVID-19 pandemic), epidemic, lock-down and/ or quarantine. 2) Bidder requests Owner's acknowledgement that ongoing events such as Covid-19 pandemic and Ukraine-Russia conflict are likely to negatively affect usual business activities around the globe and /or the execution of the contract in various ways, whether known, unknown, whether foreseeable or unforeseeable. Accordingly, the Contractor shall be entitled to an extension of time for execution and / or an adjustment of the contract price and / or other reasonable adjustments to the contract to the extent required to mitigate and / or compensate the impactcaused directly or indirectly due to these events. | Provisions of Bidding documents shall remain unchanged. |
|  | Section IV GCC 21.1 Extension of Time for Completion | The Time(s) for Completion specified shall be extended if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: a. ... ..... e. ... by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor. | Bidder request for modification to the clause as below: "The Time(s) for Completion specified shall be extended and equitable costs paid to the Contractor if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: a. ... ... e. ... (f) any default or breach of the Contract by the Employer, or any activity, act or omission of the Employer, or employees / representative(s) of Employers, or any other contractors / consultants employed by the Employer, g) Non‐fulfilment of any of its obligationa under the Contract by Owner e.g. delay in providing the inputs / data / approvals etc., by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor. |  |
|  |  |  | Bidder’s Comment after Clarification-1 Bidder requests below bullet point to be added to the GCC clause 21.1 as amendment: "The Time(s) for Completion specified in the SCC shall be extended and equitable costs paid to the Contractor if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: a... f. any default or breach of the Contract by the Employer, or any activity, act or omission or non-fulfillment of the Employer, or employees / representative(s) of Employers, or any other contractors / consultants employed by the Employer, by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor." | Provisions of Bidding documents shall remain unchanged. |
|  | GCC 21.2 Amd-1 Extension of Time for Completion | Except where otherwise specifically provided in the Contract, the Contractor shall submit to the Project Manager a notice of a claim for an extension of the Time for Completion, together with particulars of the event or circumstance justifying such extension as soon as reasonably practicable after the commencement of such event or circumstance. Sr. No. 20 of Amendment-1 Replace Clause 21 as below: 21.2. Except where otherwise specifically provided in the Contract, the Contractor shall submit to the Project Manager a notice of a claim for an extension of the Time for Completion, together with particulars of the event or circumstance justifying such extension as soon as reasonably practicable after the commencement of such event or circumstance. As soon as reasonably practicable after receipt of such notice and supporting particulars of the claim, the Employer and the Contractor shall agree upon the period of such extension. In the event that the Contractor does not accept the Employer’s estimate of a fair and reasonable time extension, the Contractor shall be entitled to refer the matter to Arbitration, pursuant to GCC Sub-Clause 23. | Bidder requests Owner to amend the clause as below: "21.2. Except where.....In the event that the Contractor and the Employer do not reach an agreement on the does not accept the Employer’s estimate of a fair and reasonable time extension, the Contractor Parties shall be entitled to refer the matter to Arbitration, pursuant to GCC Sub-Clause 23." | Provisions of Bidding documents shall remain unchanged. |
|  | Section VI Form 5 | 1.1 Contract Documents ... VOLUME – A - This Contract Agreement and the Appendices thereto. - Notification of Award Ref. No. …………..……………. dated ………… VOLUME – B - “Bidding Documents” comprising of the following: - Volume –I of Bidding Documents (Document Code No. ), read in conjunction with Amendments …. to …… to the Bidding Documents. - Volume –II of Bidding Documents (Document Code No. ) comprising of Technical Specifications. .... | Bidder’s Pre bid Comment before Clarification-1 For sake of clarity and smooth execution of the contract, please modify the clause as follows: "1.1 Contract Documents ... VOLUME – A - This Contract Agreement and the Appendices thereto. - Notification of Award Ref. No. …………..……………. dated ……… - Post‐Bid Discussions on various dates from ……………. to ……………. resulting into the Minutes of Meeting / Record Notes of Post Bid Discussions enclosed as APPENDIX (NOA)‐1. VOLUME – B 3. “Bidding Documents” comprising of the following: - Volume –I of Bidding Documents (Document Code No. ), read in conjunction with Amendments …. to ……, Errata .... to , Clarifications .... to to the Bidding Documents. - Volume –II of Bidding Documents (Document Code No. ) comprising of Technical Specifications, read in conjunction with Amendments …. to ……, Errata .... to ...., Clarifications .... to to the Technical Specifications. .... |  |
|  |  |  | Bidder’s Comment after Clarification-1 Please refer the "Form of Contract Agreement" enclosed in "Section-VI_Sample Forms and Procedures (SFP)-Rev-01". No changes have been made in the relevant clause i.e. "Clause 1.1 Contract Documents". Kindly make the required changes as per Bidder's original comment. | The proposed modifications are included in NOA which shall form part of CA. Refer Amendment – I, Sr No -25, Vol-I. |
|  | Section-VI, Sample Forms and Procedures Appendix 1 ‐ Terms and Procedure of Payment 7 | 7. Terms of Payment for Feed Study is as Mentioned Below 7.1.60% of total of FEED‐1 or FEED‐2 Study Payment shall be released after submission of duly signed FEED‐1 or FEED‐2 report as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 7.2. 30% of FEED‐1 and FEED ‐2 Study payments shall be released after clarification by Bidder and acceptance of respective report by POWERGRID. 7.3 7.3. Final 10% of FEED‐1 and FEED ‐2 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. | Bidder’s Pre bid Comment before Clarification-1 The Bidder requests for modification of the clause as below: - Terms of Payment for Feed Study are as mentioned below: - 10% of total FEED‐1 Study Contract Price shall be released as interest free advance within 15 days of submission of Advance Bank Guarantee in favour of the Employer for an equivalent amount. 7.1.60% 7.2 80% of total of FEED‐1 or FEED‐2 Study Payment Contract Price shall be released progressively on pro‐rata basis after submission of duly signed FEED‐1 or FEED‐2 report as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 7.2. 30% 7.3 20% of FEED‐1 and FEED ‐2 Study payments Contract Price shall be released progressively on pro‐rata basis after clarification by Bidder and acceptance of respective report by POWERGRID. - 7.3. Final 10% of FEED‐1 and FEED ‐2 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. |  |
|  |  |  | Bidder’s Comment after Clarification-1 Owner is requested to re-consider Bidder's concern regarding payment clause 7.3. Accordingly, Bidder requests modification in payment terms as below: "7. Terms of Payment for Feed Study are as mentioned below: 7.1.60% 70% of total of FEED-1 or FEED-2 Study Payment Contract Price shall be released progressively on pro-rata basis after submission of duly signed FEED-1 or FEED-2 report as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 7.2. 30% of FEED-1 and FEED -2 Study payments Contract Price shall be released progressively on pro-rata basis after clarification by Bidder and acceptance of respective report by POWERGRID. 7.3 7.3. Final 10% of FEED-1 and FEED -2 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company." | Provision of Bidding Documents shall remain unchanged. |
|  | Section-VI, Sample Forms and Procedures Appendix 1 ‐ Terms and Procedure of Payment 7 | 7.3 7.3. Final 10% of FEED‐1 and FEED ‐2 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. | Bidder’s Pre bid Comment before Clarification-1 The Bidder requests for deletion of this clause for reasons mentioned below. As per the Bidder's understanding, the FEED Studies comprising of FEED‐1 Study (Owner's present tender) and FEED‐2 Study (tender to be issued by Owner in due course after completion of FEED‐1 Study) are intended to facilitate the tendering of the main HVDC VSC package considering its unique and unprecedented technical challenges & complexities. The payment for the FEED‐1 Study becomes due to the Contractor immediately upon its completion, and cannot be linked with the Bidder's/Contractor's participation in Owner's future tender for the main HVDC VSC package which is yet to be issued. The Bidder/Contractor of FEED‐1 Study cannot take responsibility for a future tender for which the timelines, scope of work, terms & conditions, etc. are unknown & unpredictable at this point of time. |  |
|  |  |  | Bidder’s Comment after Clarification-1 The provisions of this clause are not acceptable for reasons already explained in the Bidder's original comment. Hence, Bidder requests for deletion of this clause and release of this 10% payment along with the progressive payment as per payment clause 7.1. | Provision of Bidding Documents shall remain unchanged. |
|  | Section-VI, Sample Forms and Procedures Appendix 1 ‐ Terms and Procedure of Payment 7 | In accordance with the provisions of Condition of Contract, the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules. The Contractor may make applications for payment in respect of part deliveries as work proceeds. | Bidder’s Pre bid Comment before Clarification-1 The Bidder proposes to submit the Price Breakdown (without prices) e.g. as % of total price, as part of First Envelope submission. This can be discussed and mutually agreed during the post‐bid discussion, prior to issuance of the Notice of Award. |  |
|  |  |  | Bidder’s Comment after Clarification-1 Owner is requested to clarify the procedure for submission of Price Breakdown for billing purpose i.e. Billing Break-up. Bidder requests that the Billing Break-up is discussed and mutually agreed during the post-bid discussion, prior to issuance of the Notice of Award. | Provisions of Bidding documents shall remain unchanged. |
|  | Section VI Form 5 | 1.1 Contract Documents ... VOLUME – A - This Contract Agreement and the Appendices thereto. - Notification of Award Ref. No. …………..……………. dated ………… VOLUME – B - “Bidding Documents” comprising of the following: - Volume –I of Bidding Documents (Document Code No. ), read in conjunction with Amendments …. to …… to the Bidding Documents. - Volume –II of Bidding Documents (Document Code No. ) comprising of Technical Specifications. .... | Bidder’s Pre bid Comment before Clarification-1 For sake of clarity and smooth execution of the contract, please modify the clause as follows: "1.1 Contract Documents ... VOLUME – A - This Contract Agreement and the Appendices thereto. - Notification of Award Ref. No. …………..……………. dated ……… - Post‐Bid Discussions on various dates from ……………. to ……………. resulting into the Minutes of Meeting / Record Notes of Post Bid Discussions enclosed as APPENDIX (NOA)‐1. VOLUME – B 3. “Bidding Documents” comprising of the following: - Volume –I of Bidding Documents (Document Code No. ), read in conjunction with Amendments …. to ……, Errata .... to , Clarifications .... to to the Bidding Documents. - Volume –II of Bidding Documents (Document Code No. ) comprising of Technical Specifications, read in conjunction with Amendments …. to ……, Errata .... to ...., Clarifications .... to to the Technical Specifications. .... |  |
|  |  |  | Bidder’s Comment after Clarification-1 Intention of Bidder's original pre-bid comment was as follows: Bidder understands that amendments & clarifications issued against similar provisions in the bidding documents under different Sections will be appropriately harmonized by the Owner in other relevant sections at the time of contract award. | The proposed modifications are included in NOA which shall form part of CA. Refer Amendment – I, Sr No -25, Vol-I. |
|  | Price Schedule Sch‐1 | Cell B19 ‐ Township for 132/33 kV Silapathar (new) Cell F20 ‐ Civil works | Bidder’s Pre bid Comment before Clarification-1 In accordance with ITB 5.3, we request to make required corrections in the text of cells B19 and F20 of Sch‐1. |  |
|  |  |  | Bidder’s Comment after Clarification-1 Cell F20 has not been corrected in the revised Excel file "Price_schedule Rev-01". It wrongly mentions "Civil Works" as the activity description. Please correct appropriately e.g. "Technical Consulting Services". | Please refer Amendment -III, Sl 1, Vol-III |
|  | GCC 1.1 (b), Section-IV | (b) “Collaborator” or “Parent Company” means the firms/corporations who has provided technological support to the manufacturer for establishing production line for the specific Equipment. | Bidder requests Owner to clarify the purpose of defining the term "Collaborator", as the same is not used as such anywhere in the bidding documents except in the table at GCC 10.5. | Please refer Amendment -III, Sl 7, Vol-I |
|  | Clause No 1.1. (v) Vol‐1 ‐ Sec IV ‐GCC | The time for completion of Contract | Whether the deemed completion shall be construed if the Contractor has not received issuance of the certificate within 7 days of completion or if the employer not provided any written comments within 7 days or the Employer /Owner started its commercial use or otherwise. | Refer Amendment-1, Sl. 11, Vol-I |
|  | Clause 10.1 Vol‐1 ‐ Sec IV ‐GCC | Performance Securities 10.1.1. The Contractor shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Three percent (3%) of the Contract Price, with a validity upto ninety (90) days beyond the completion Period as per contract agreement. The same shall be extended by the Contractor time to time till ninety (90) days beyond the extended completion Period, as may be required under the Contract. | No specific or definite date is specified under these provisions towards the release of Performance Securities. Hence following text is proposed as new clause ‐ "The Performance Securities submitted under the Contract shall be released upon 4 months from Effective Date or the Completion of the Work, which ever is later." | Provisions of bidding document are amply clear. |
|  | Section II ITB 6.4 | POWERGRID will issue clarifications/amendment through E‐Portal. These shall form integral part of the Bidding Documents and accompany the Bidder’s proposal. | Please clarify the underlined text. | Please Refer Amendment -1, Sr No – 4, Vol-I |
|  | Section IV GCC 22.1 GCC 16 | Except as otherwise specifically provided in the contract all disputes concerning questions of fact arising under the contract shall be decided by the Officer‐in‐charge subject to a written appeal by the contractor to the Officer‐ in‐charge whose decision shall be final to the parties hereto. On all matters pertaining to execution of the contract, the contractor shall directly interact with the Officer‐in‐Charge. | Bidders requests Owner to clarify the nomination / selection process of the Officer‐in‐Charge. | Please Refer Amendment-1, Sr. No 10 and 24, Vol-I. |
|  | Section VI Form 3 | FORM OF 'NOTIFICATION OF AWARD OF CONTRACT' FOR SUPPLY OF PLANT AND EQUIPMENT .... Sub. :Notification of Award for Supply of Goods Contract for ……….. ..... 2.1 The scope of work under this Notification of Award (NOA). under the Contract for the construction of …… (insert name of Package alongwith name of the Project) ……., unless. this NOA. | As per Section‐I (IFB), this tender is for Front End Engineering & Design Study Services only (FEED‐1 Study). Please correct the highlighted text in Form 3 suitably. | Refer Amendment -1, Sr. No 25, Vol-I |