| Sr No | Clause/Section | Existing Clause | Amended Clause |
| --- | --- | --- | --- |
| Vol-I |  |  |  |
| 1 | Appendix-1, Sample Forms and Procedures (SFP), Section-VI, | ………………………………………………………………... ………………………………………………………………... 1. TERMS OF PAYMENT FOR FEED STUDY IS AS MENTIONED BELOW 1.1. 60% of total of FEED-1 Study Payment shall be released after submission of duly signed FEED-1 report as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 1.2. 30% of FEED-1 Study payments shall be released after clarification by Bidder and acceptance of respective report by POWERGRID. 1.3. Final 10% of FEED-1 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. 1.4. All payments under the Contract shall be made in Indian Rupees. 1.5. The above payments shall be made after deducting therefrom such other amounts as may be deductible or recoverable under the Contract. 1.6. No interest is admissible on amounts payable by the Owner. 1.7. Applicable GST will be paid/reimbursed extra. ………………………………………………………………... ………………………………………………………………... | Replaced With following: ………………………………………………………………... ………………………………………………………………... 1. TERMS OF PAYMENT FOR FEED STUDY IS AS MENTIONED BELOW 1.1 Interest Bearing Initial Advance (Optional*): Ten percent (10%) of the FEED-1 Study payment shall be paid as an interest bearing initial advance after signing the Contract Agreement and on submission of (a) Proforma invoice(s), (b) Advance Bank Guarantee for 110% (one hundred ten percent) of the amount of Advance, in line with GCC Cl. 10.10, (c) Performance Securities in line with GCC Clause 10.1 and (d) Detailed PERT Network/Bar chart and its approval by the Employer. Provided further that the Proforma Invoice(s) for advance payment along with all supporting documents is submitted by the Contractor to the Employer within 3 months from the date of Notification of Award. In case the Contractor does not submit the requisite documents including applicable Bank Guarantee(s)/Security(ies) within the aforesaid period, the advance shall not be payable. The Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. Note: * This payment is an optional payment. The Contractor has the option of taking the interest bearing initial advance or otherwise. Interest rate applicable on advance payment to the Contractor shall be at the rate equal to one year MCLR rate [One year Tenor rate p.a.] published by State Bank of India prevailing as on the date of drawal of advance. The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid. The interest will be charged considering proportionate adjustment of advance against progressive payment as per 1.1(B) below. The interest shall be calculated on the daily progressive balances outstanding as on the date of recovery/adjustment. It is the Employer’s understanding that as per extant provisions, GST is not payable on interest paid on the amount of Advance. The Contractor is, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account. Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest within 3 months from the end of the quarter in which adjustment of advance has been made for claiming refund from Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate. In case, the Contractor opts not to take interest bearing advance as above, it would be mandatory for him to submit the documents listed at Sl. No. (c), and (d) above within twenty-eight (28) days of issuance of NOA. (The above is to be incorporated in case the Contractor has opted for the interest bearing initial advance, as declared by it in its bid in the relevant Attachment to Bid Form). 1.2. Fifty Percent (50%) ** of total of FEED-1 Study Payment shall be released after submission of duly signed FEED-1 report as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). *In case, the Contractor opts to take interest bearing initial advance and submitted Advance Bank Guarantee in line with Clause 1.1 of Terms of Payment the same shall be released with the payment as at para 1.2 herewith. ** In case, the Contractor opts not to take interest bearing initial advance then this payment shall be 60% instead of 50%. 1.3. 30% of FEED-1 Study payments shall be released after clarification by Bidder and acceptance of final report by POWERGRID. 1.4. Final 10% of FEED-1 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company OR Completion of 6 months from the date of acceptance of final report by POWERGRID as per clause 1.3 above, whichever is earlier. 1.5. All payments under the Contract shall be made in Indian Rupees. 1.6. The above payments shall be made after deducting therefrom such other amounts as may be deductible or recoverable under the Contract. 1.7. No interest is admissible on amounts payable by the Owner. 1.8. Applicable GST will be paid/reimbursed extra. ………………………………………………………………... ………………………………………………………………... |
| 2 | Clause 10.10 Section-IV, GCC | Not Existing | Supplementing Cl.10.10 as follows: 10.10 Advance Payment Security: 10.10.1. The Contractor shall, within twenty-eight (28) days of the notification of contract award, provide a security in an amount equal to as follows: a. 110% (one hundred ten percent) of the {amount of Advance} plus {amount of GST reimbursable on Advance as per the Proforma invoice} for Supply of Services. The above shall be calculated in accordance with the corresponding Appendix - 1 (Terms and Procedures of Payment) to the Contract Agreement, and in the same currency(ies) with initial validity of up to ninety (90) days beyond the date of Completion of the Work. The same shall be extended by the Contractor time to time till ninety (90) days beyond the actual date of Completion of the Work, as may be required under the Contract. 10.10.2 The security shall be in the Form of unconditional Bank Guarantee attached hereto in Section VI - Sample Forms and Procedures. The security shall be discharged after release of payment at para 1.2 of Appendix -1 (Terms and Procedure of Payment). |
| 3 | Clause 11.8 Section-IV, GCC | Not Existing | Adding New Clause 11.8. as Follows: 11.8 The reimbursement of GST except GST on advance payment shall be against Invoice/Debit Note containing particulars specified under the GST Act and related Rules, Notifications, etc as notified by the Government in this regard. In the event that the Contractor fails to provide the invoice in the form and manner prescribed under the GST Act and Rules, the Employer shall not be liable to make any payment against such invoice. Reimbursement of GST payment against Advance payment (applicable for Supply of Services) shall be against a proforma invoice. Further, the Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. |
| 4 | Section-VI_Sample Forms and Procedures (SFP) | Existing File: Section-VI_Sample Forms and Procedures (SFP)-Rev-01 | Replaced With Section-VI_Sample Forms and Procedures (SFP)-Rev-02 |
| 5 | Clause 15.3, Section - IV GCC, | Not Existing | Adding New Clause as 15.3 Within twenty-eight (28) days after the date of Notification of Award, the Contractor shall prepare and submit to the Project Manager a detailed program of performance of the Contract (L2 Network) in the form of the Critical Path Method (CPM), the PERT network, or other internationally used programs and showing the sequence in which, it proposes to execute the contract. The program so submitted by the Contractor shall accord with the Time Schedule included in Appendix-4 (Time Schedule) to the Contract Agreement and any other dates and periods specified in the Contract. The Contractor shall update and revise the program as and when appropriate or when required by the Project Manager, and shall submit all such revisions to the Project Manager. |
| 6 | Clause 9.3, ITB | ………………………………………………………….. ……………………………………. m. Attachment 13: Declaration by the Bidder regarding events encountered pursuant to Clause 2.4 above. n. Attachment 14: Certification by the Bidder as per DoE Order in line with Clause 2.3 above. ………. | ………………………………………………………….. ……………………………………. m. Attachment 13: Declaration by the Bidder regarding events encountered pursuant to Clause 2.4 above. n. Attachment 14: Certification by the Bidder as per DoE Order in line with Clause 2.3 above. o. Attachment 15: Option for Interest Bearing Advance (Initial Advance) and Information for E-payment, PF details and declaration regarding Micro/Small & Medium Enterprises. In this Attachment, the Bidder is required to clearly mention whether the Bidder would opt for Interest bearing advance (s) in addition to providing the other information as above. ………. |
| VOL-III |  |  |  |
| 1 | Vol‐III, First Envelope and Bid Forms | Existing Excel File: “First Envelope and Bid Forms Rev-01” | Existing Excel File “First Envelope and Bid Forms Rev-01” stand Replace with new Excel File “First Envelope and Bid Forms Rev-02” |