| Sl. No. | Clause ref. | Existing Provision of the Bidding Document | Query asked by the bidders | POWERGRID Reply |
| --- | --- | --- | --- | --- |
| 1 | Appendix -1, Terms of Payment | 1.0 TERMS OF PAYMENT FOR FEED STUDY IS AS MENTIONED BELOW 1.1 60% of total of FEED-1 or FEED-2 Study Payment shall be released after submission of duly signed FEED-1 or FEED-2 report as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 1.2 30% of FEED-1 and FEED -2 Study payments shall be released after clarification by Bidder and acceptance of respective report by POWERGRID. 1.3 Final 10% of FEED-1 and FEED -2 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. | “ ……….. ……. Present terms and conditions call for submission of all final reports together at the end of the project and acceptance of the same by Employer only at the end of the project. Keeping in view the benefits of the pro-rata project progress, we request you to consider stage –wise report submissions and acceptance/feedback from the employer which will avoid chances of complete re-work after submission of all final reports together at the end. This will help you to monitor stagewise progress of the deliverables. Further, we request you to consider corresponding milestone –based payments on submission of stagewise reports as per the time schedule. Also, as per the present Terms of Payment, the last 10% payment will be released only after submission of bid for the main HVDC package. We would request you to consider that if the main HVDC package tender submission is delayed beyond 6 months from submission of our last deliverable for FEED-1 tender, the last 10% payment shall be released. ………….” “…………… We once again request you to consider milestone –based payment terms as mentioned below: - 20% as Advance Payment - 70% of total of FEED-1 Study Payment shall be released based on delivery milestone and submission of respective reports as mentioned below: Description; Percentage of Contract Value. 1; Inception report; 10%. 2; Study Models Development Report; 10%. 3; Steady –State Analysis Report; 10%. 4; Dynamic Study report; 20%. 5; Harmonic impedance Sector (HIS) study Report & Switching Transient Study Report; 20%. Also, as per the present Terms of Payment, the last 10% payment will be released only after submission of bid for the main HVDC package. We would request you to consider the release of last 10% payment within 6 months from the submission of our last deliverable for FEED-1 Study (or) submission of our bid for main HVDC package whichever is earlier. | The Section wise reports as and when completed by the contractor can be submitted as draft to POWERGRID and shall be progressively verified so that the re-works in the studies can be minimized. However, the date of submission of report in complete shape as envisaged in Terms of Payment (Appendix-1 (Rev.1) of Bidding Document) shall be considered for Contractual purpose Regarding payment terms please refer Amendment No. IV. The proposed report stages are not identified in the tender documents. FEED-1 Study report can be considered as complete with submission of final report and hence stage wise reports as proposed can`t be considered for release of payments. Regarding payment terms please refer Amendment No.IV. |
| 2 | GCC 9.4 | 9.4. Liability of the Contractor Any mistake or inadequacy appear in the documents submitted by the Contractor, the Contractor shall perform at its own initiative and no extra cost to POWERGRID, all such services as shall be necessary to remedy the said mistake or inadequacy. The Contractor shall be further liable for the consequences resulting from errors and commissions due to negligence or from inadequacy on its part or on the part of its employees or associates or experts to the extent of the fees actually received by the Contractor. Contractor shall indemnify and hold harmless POWERGRID against any and all claims, demands, and/or judgements of any nature brought against POWERGRID arising out of the services by Contractor and it's staff under this Agreement. The obligation under this paragraph shall survive the termination of this Agreement. | “In the Original tender condition, Section-V SCC, Sl.No. 5, the Liability Period mentioned earlier was 3 months. But in subsequent amendment released by you, the 3 months Liability Period sentence has been deleted. But Liability requirements as per GCC 9.4. Liability of the Contractor are still applicable. It is not clear from the T&C till when the Liability requirement mentioned under GCC Clause 9.4 will be applicable. We kindly request you to accept these changes and confirm the same. We look forward to your kind consideration and assure you the best of our services every time. | Provision of Bidding document is amply clear. |
| 3 | ITB 6.2, Section-II | The Bidder is advised to visit and examine the site (s) of the subject proposal and its surroundings and obtain for itself on its own responsibility and cost all information that may be necessary for preparing the bid and entering into a contract. The costs of visiting the site shall be at the Bidder’s own expense. | Bidder’s earlier pre-bid Query In accordance with Section-I, IFB 2.4 the scope of this tender is limited to the 1st part of the Front-End Engineering and Design Study i.e. FEED-1 Study. Therefore, the requirements mentioned under ITB 6.2 are not relevant, and will not be considered in the Bidder's scope & costing. Owner is requested to confirm this understanding. Alternatively, Owner is requested to state the specific FEED-1 Study tasks / deliverables (refer Vol-II) under which such site visit is envisaged during the bidding and/or execution phase. |  |
|  |  |  | Bidder’s Query after Clarification – II Bidder refers to its original comment. Bidder repeats that no site visits are required nor envisaged for FEED-1 Study related scope during bidding or execution phase. In case site visits are required in future for FEED-2 Study and/or for Main HVDC Package related work, these will be considered separately at the time of their respective tendering. Bidder requests Owner to provide a clear response in order to avoid unnecessary conflicts during execution. | Site visit is optional to the bidder for preparation of their bid for submission for subject package. |
| 4 | Section III Annexure-A (BDS), 2.1.1 | The bidder shall be a manufacturer of Voltage Source Converter (VSC) High voltage Direct Current Transmission equipment for the last seven (7) years or more as on the originally scheduled date of bid opening i.e. 21/09/2022 and who has implemented a contract wherein the scope involves engineering, manufacturing, supply, erection, testing and commissioning of at least one long distance VSC based HVDC transmission converter station or a VSC based Back-to Back HVDC system of a unit rating of at least 250MW, along with associated auxiliary equipment and ancillary works and the VSC HVDC system should have been in Satisfactory Operation* for a period of not less than one year as on the originally scheduled date of bid opening i.e. 21/09/2022. | Bidder’s earlier pre-bid Query Bidder would like to bring to Owner's attention that in 2019, there was a global restructuring program for the Energy business which included the HVDC portfolio as well. Specifically, the Energy business was carved out and spun-off into a new company, which included the transfer of assets, employees, credentials and references. Kindly refer separate submissions made by the Bidder in this regard. Hence, the Qualified Bidder [Company A] as per Cl. 2.1.1 of Annexure-A (BDS) is in existence for less than 7 years as on 21/09/2022. However, the Original Company [Company B] from which Company A was spun off had been manufacturing VSC HVDC equipment for more than 7 years prior to the spinoff. Furthermore, the same Company B had implemented a contract wherein the scope involved engineering, manufacturing, supply, erection, testing and commissioning of at least one long distance VSC based HVDC transmission converter station or a VSC based Back-to Back HVDC system of a unit rating of at least 250MW, along with associated auxiliary equipment and ancillary works and the VSC HVDC system had been in Satisfactory Operation for a period of not less than one year as on the originally scheduled date of bid opening i.e. 21/09/2022. In view of the above, Owner's acceptance of Bidder's understanding as below is requested: 1. Bidder understands that Company A will be deemed to be a manufacturer of VSC HVDC equipment for more than 7 years as on 21/09/2022. 2. Bidder understands that Company A will be deemed to have implemented the contract that was originally signed with Company B, wherein the scope involved engineering, manufacturing, supply, erection, testing and commissioning of at least one long distance VSC based HVDC transmission converter station or a VSC based Back-to Back HVDC system of a unit rating of at least 250MW, along with associated auxiliary equipment and ancillary works and the VSC HVDC system had been in Satisfactory Operation for a period of not less than one year as on the originally scheduled date of bid opening i.e. 21/09/2022. |  |
|  |  |  | Bidder’s Query after Clarification – II Bidder has reviewed sr. no. 1 of Amendment-II to Vol-I. However, Bidder's concerns raised in original comment are not addressed / clarified by this amendment. Bidder requests Owner to review Bidder's original comment and provide a clear response in order to avoid any misunderstanding of the Qualifying Requirements. | Bidder is requested to submit its bid in line with the provision of bidding documents. |
| 5 | Section IV GCC 20 Amd-1, Force Majeure | Replacing Cl 20 20. FORCE MAJEURE 20.1 “Force Majeure” shall mean any event beyond the reasonable control of the Employer or of the Contractor, as the case may be, and which is unavoidable notwithstanding the reasonable care of the party affected, and shall include, without limitation, the following: (a) war, hostilities or warlike operations (whether war be declared or not), invasion, act of foreign enemy and civil war, (b) rebellion, revolution, insurrection, mutiny, usurpation of government, conspiracy, riot and civil commotion, (c) earthquake, landslide, volcanic activity, flood or cyclone, or other inclement weather condition, nuclear and pressure waves or other natural or physical disaster, | Bidder’s earlier pre-bid Query 1) Bidder refers to its original comment and accordingly requests below changes to be added to the GCC clause 20.1 as amendment: "“Force Majeure” shall mean... (a) war, hostilities or warlike operations (whether war be declared or not), invasion, act of foreign enemy and civil war, (including but not limited to the ongoing Ukraine-Russia conflict), (d) Other unforeseen events like pandemic (including but not limited to the outbreak of the COVID-19 pandemic), epidemic, lock-down and/ or quarantine. 2) Bidder requests Owner's acknowledgement that ongoing events such as Covid-19 pandemic and Ukraine-Russia conflict are likely to negatively affect usual business activities around the globe and /or the execution of the contract in various ways, whether known, unknown, whether foreseeable or unforeseeable. Accordingly, the Contractor shall be entitled to an extension of time for execution and / or an adjustment of the contract price and / or other reasonable adjustments to the contract to the extent required to mitigate and / or compensate the impactcaused directly or indirectly due to these events. |  |
|  |  |  | Bidder’s Query after Clarification – II Bidder refers to the original text of GCC 20, extract reproduced below: "A. Natural phenomena including but not limited to floods, droughts, earthquakes and epidemics. B. Acts of any government, domestic or foreign, including but not limited to war, declared or undeclared, priorities, quarantines, embargoes" Owner's new GCC 20 does not mention some events e.g. epidemics, quarantines, etc. for which specific concerns were raised by the Bidder in its original comment as well post-Clarification-1 comment, Bidder requests Owner to reinstate the missing events that were included in original GCC but removed in amended GCC (see underlined text above). | Provisions of Bidding documents shall remain unchanged. |
| 6 | Section VI Appendix 1 - Terms and Procedure of Payment | 1. Terms of Payment for Feed Study is as Mentioned Below 1.1.60% of total of FEED‐1 Study Payment shall be released after submission of duly signed FEED‐1 or FEED‐2 report as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 1.2. 30% of FEED‐1 Study payments shall be released after clarification by Bidder and acceptance of respective report by POWERGRID. 1.3 Final 10% of FEED‐1 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. | Bidder’s Comment after Clarification-1 Owner is requested to re-consider Bidder's concern regarding payment clause 7.3. Accordingly, Bidder requests modification in payment terms as below: "7. Terms of Payment for Feed Study are as mentioned below: 7.1.60% 70% of total of FEED-1 or FEED-2 Study Payment Contract Price shall be released progressively on pro-rata basis after submission of duly signed FEED-1 or FEED-2 report as per deliverable checklist (as per FEED Technical specification) (In case of Indian Entity, report shall also be counter signed by their Parent/Principal/Group Company who shall meet the specified QR for HVDC OEM). 7.2. 30% of FEED-1 and FEED -2 Study payments Contract Price shall be released progressively on pro-rata basis after clarification by Bidder and acceptance of respective report by POWERGRID. 7.3 7.3. Final 10% of FEED-1 and FEED -2 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company." |  |
|  |  |  | Bidder’s Comment after Clarification-II Bidder again requests Owner's acceptance to Bidder's Comment after Clarification-1. Since the scope involves multiple number of engineering studies (refer Vol-II, Cl. 5.1) only and there is no provision for interest-free advance payment, the Bidder requests Owner's understanding that healthy cash flow is essential for smooth execution. Hence, Bidder again equests Owner to allow progressive billing on pro-rata basis. Bidder will submit notional billing break-up latest at the post-bid discussion phase (prior to contract finalization) for this purpose. | Please refer Amendment-IV dated 16/12/2022 |
| 7 | Section VI Appendix 1 - Terms and Procedure of Payment | Final 10% of FEED-1 and FEED -2 Study payments shall be released after submission of bid for the HVDC package (±350 kV, 4x1250MW, VSC Based Symmetrical Monopole (Parallel) HVDC Link between Pang Pooling station (Leh) and Kaithal Pooling station (Harayana) associated with power generated from 5 GW renewable energy park) by the bidder or its parent/principal or group company. | Bidder’s earlier pre-bid Query The Bidder requests for deletion of this clause for reasons mentioned below. As per the Bidder's understanding, the FEED Studies comprising of FEED-1 Study (Owner's present tender) and FEED-2 Study (tender to be issued by Owner in due course after completion of FEED-1 Study) are intended to facilitate the tendering of the main HVDC VSC package considering its unique and unprecedented technical challenges & complexities. The payment for the FEED-1 Study becomes due to the Contractor immediately upon its completion, and cannot be linked with the Bidder's/Contractor's participation in Owner's future tender for the main HVDC VSC package which is yet to be issued. The Bidder/Contractor of FEED-1 Study cannot take responsibility for a future tender for which the timelines, scope of work, terms & conditions, etc. are unknown & unpredictable at this point of time. |  |
|  |  |  | Bidder’s Comment after Clarification-1 Bidder refers to its original comment as well as post-Clarification-1 comment. Bidder requests Owner to understand Bidder's concern and appropriately amend the clause. As an alternative, Bidder proposes that final 10% payment shall be unconditionally released latest 3 months after completion of FEED-1 Study. | Please refer Amendment-IV dated 16/12/2022 |
| 8 | Section VI Appendix 1 - Terms and Procedure of Payment | In accordance with the provisions of Condition of Contract, the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules. The Contractor may make applications for payment in respect of part deliveries as work proceeds. | Bidder’s earlier pre-bid Query The Bidder proposes to submit the Price Breakdown (without prices) e.g. as % of total price, as part of First Envelope submission. This can be discussed and mutually agreed during the post-bid discussion, prior to issuance of the Notice of Award. |  |
|  |  |  | Bidder’s earlier pre-bid Query Owner is requested to clarify the procedure for submission of Price Breakdown for billing purpose i.e. Billing Break-up. Bidder requests that the Billing Break-up is discussed and mutually agreed during the post-bid discussion, prior to issuance of the Notice of Award. |  |
|  |  |  | Bidder’s Comment after Clarification-II Bidder refers to its original comment as well as post-Clarification-1 comment. Since the scope involves multiple number of engineering studies (refer Vol-II, Cl. 5.1) only and there is no provision for interest-free advance payment, the Bidder requests Owner's understanding that healthy cash flow is essential for smooth execution. Hence, Bidder again requests Owner to allow submission of notional billing break-up latest at the post-bid discussion phase (prior to contract finalization) to enable progressive billing on prorate basis. | Please refer Amendment-IV dated 16/12/2022 |
| 9 | ITB 2.4 (4), Section II GCC 14, Section IV | *For the purpose of working out 50% of the Contract, following shall be taken into account: (a) Scope of the contract which is permissible to be sub-contracted as per bidding documents, shall be excluded. The contractor shall not assign or sub-contract any portion of this work without the prior written consent of POWERGRID. | Bidder's Pre-Bid Comments Considering the requirements of ITB 2.1 and Annexure-A (BDS), and the scope of work (FEED Study - 1) of this tender, the Bidder requests the following amendment: "In case the bidder is an Indian entity (as per Cl. 2.1.2 of Annexure-A (BDS), then the bidder/contractor shall be permitted to sub-contract major portion of this work (more than 50%) to the Parent / Principal / Group Company of the bidder that meets the qualifying requirements as per Cl. 2.1.1 of Annexure-A (BDS)" |  |
|  |  |  | Bidder’s Comment after Clarification-II Provisions of bidding document are not clear. Bidder refers to its original comment. Bidder further draws Owner's attention to Note 3(b) of bidding form "Attachment- 13": (b) Scope of the Contract which primarily relates to the Qualification Requirement (QR) of the bidder as illustrated below: ..... The guiding principles as illustrated above shall be followed while dealing with other packages/contracts ." From the above statement, it appears that Bidder cannot subcontract more than 50% of the work regardless of the QR. Hence, Owner is requested to issue required amendment (refer Bidder's proposal in original pre-bid comment) to avoid unintended consequences for future bids where similar declaration has to be provided by the Bidder. | As per QR & JDU, the bidder along with Parent/ Principal/Group company shall take up jointly the FEED Study. Hence, engagement of Parent/ Principal/Group company shall not be considered as subcontracting. |