## Sheet1
Appendix-E
Annexure-E
IMPLEMENTATION SCHEDULE
Sl. No. | Description of Work | Commencement | Completion
(Period in Days from date of NOA)
1 | Approval of Survey format/ Design Document/ DRS | 0 | 7
2 | Submission of MTCTE, Type Test etc Certificates/ Reports & their accepatnce | 0 | 7
3 | Approval of Functiona Test, FAT & SAT Procedures | 0 | 7
4 | Lot-1 (Green Field)
i | BoQ Finalization (Intra-City) | 0 | 7
ii | FAT & Despatch clearance | 8 | 63
iii | Transportation to sites | 64 | 70
iv | Site Installation, Testing & commissioning (SAT1 & SAT2) including Functional Test | 71 | 91
5 | Lot-2 (TMN)
i | BoQ Finalization | 8 | 14
ii | Physical Inspection of TMN & Despatch clearance | 64 | 70
iii | Transportation to sites | 71 | 77
iv | Site Installation, Testing & commissioning (SAT-3), FAT & Functional Test | 78 | 91
6 | Lot-3 (Brown Field)
i | BoQ Finalization (Ahmedabad-Mumbai & Ahmedabad-Delhi including respective Metros) | 64 | 70
ii | FAT & Despatch clearance | 71 | 126
iii | Transportation to sites | 127 | 140
iv | Site Installation, Testing & commissioning (SAT1 & SAT2) | 141 | 161
7 | Lot-4 (Brown Field)
i | BoQ Finalization (Chennai Intracity) | 127 | 133
ii | FAT & Despatch clearance | 134 | 189
iii | Transportation to sites | 190 | 203
iv | Site Installation, Testing & commissioning (SAT1 & SAT2) | 204 | 224
8 | Lot-5 (Brown Field)
i | BoQ Finalization (Pune-Bangalore including respective Metros) | 191 | 197
ii | FAT & Despatch clearance | 198 | 253
iii | Transportation to sites | 254 | 267
iv | Site Installation, Testing & commissioning (SAT1 & SAT2) | 268 | 288
9 | SAT-3 for complete* Network | 289 | 316
10 | VAPT and implementation of its mitigation plan | 310 | 365
Note:
1 | PowerTel may prepone/ postpone any of the LOT based on requirement.
2 | PowerTel may increase/ decrease the no of LOT for delivery of equipment, based on requirement.
3 | Completion period for any new LOT (Green/ Brown field) will be finalized equivalent to the time defined for Lot-4/5
4 | PowerTel may delay in the implimentation of TMN
5 | In case of change in scope of Work in any of the above LOT, the completion schedule shall be finalized with mutual discussion.
6 | TOC (Taking over Certificate) will be issued on LOT basis after completion of SAT-3
7 | VAPT can be preponed and performed after 60% completion of scope of work (including TMN).
8 | * SAT-3 will be performed as per the timeline specified above with aleast one Green Field & one Brown Field Link.