Tower Package TW02 for diversion of various transmission existing transmission lines including supply of materials

MAJOR MILESTONES

- Completion schedule in month from date of LOA: 01 (one) year

- Supply:  Within 06 (six) months from the date of LOA

- Erection activity completion time  from the date of LOA

- Mobilization and Survey: 15 days

- Tower Foundation including earthing: 06 months

- Tower Erection: 07 months

- Stringing: 10 months

- Final checking & intimation for readiness of lines for application to CEA: 11 (eleven) months

- Commissioning: 12 months