| Sl. No | Clause Ref. No. | Existing provision | Amended as |
| --- | --- | --- | --- |
|  | ITB 24.1 (c), Section-III, BDS, Vol-I of bidding documents | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 765kV Transformer Package 7TR-19-BULK for 13 x 500 MVA, 765/400/33kV, 1-Ph Transformers under Procurement of 765kV & 400kV class Transformers and Reactors of various Capacities (Lot-7). Specification no.: CC/NT/W-TR/DOM/A06/26/02882; Remark (Indicative Period in Months from Award). Unit-1; 21 Months; Engineering: 0-8 months Dispatch: 16-18 months Rcpt at site:17-19 months Erection & Ready for Commissioning:18-21 months (1st-6th) 6 units by 21 months. Unit-2. Unit-3. Unit-4. Unit-5. Unit-6. Unit-7; 25 Months; Engineering: 0-9 months Dispatch: 19-22 months Rcpt at site:20-23 months Erection & Ready for Commissioning:21-25 months (7th-13th) 7 units by 25 months. Unit-8. Unit-9. Unit-10. Unit-11. Unit-12. Unit-13. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformer. | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 765kV Transformer Package 7TR-19-BULK for 13 x 500 MVA, 765/400/33kV, 1-Ph Transformers under Procurement of 765kV & 400kV class Transformers and Reactors of various Capacities (Lot-7). Specification no.: CC/NT/W-TR/DOM/A06/26/02882; Remark (Indicative Period in Months from Award). Unit-1; 21 Months; Engineering: 0-8 months Dispatch: 16-18 months Rcpt at site:17-19 months Erection & Ready for Commissioning:18-21 months (1st-6th) 6 units by 21 months. Unit-2; 21 Months. Unit-3; 21 Months. Unit-4; 21 Months. Unit-5; 21 Months. Unit-6; 21 Months. Unit-7; 25 Months; Engineering: 0-9 months Dispatch: 19-22 months Rcpt at site:20-23 months Erection & Ready for Commissioning:21-25 months (7th-13th) 7 units by 25 months. Unit-8; 25 Months. Unit-9; 25 Months. Unit-10; 25 Months. Unit-11; 25 Months. Unit-12; 25 Months. Unit-13; 25 Months. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformer. |
|  | GCC 1.1(e) & 1.1(ee), Section-V, SCC, Vol-I of bidding documents | Supplementing Sub-Clause GCC 1.1(ee) The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 765kV Transformer Package 7TR-19-BULK for 13 x 500 MVA, 765/400/33kV, 1-Ph Transformers under Procurement of 765kV & 400kV class Transformers and Reactors of various Capacities (Lot-7). Specification no.: CC/NT/W-TR/DOM/A06/26/02882; Remark (Indicative Period in Months from Award). Unit-1; 21 Months; Engineering: 0-8 months Dispatch: 16-18 months Rcpt at site:17-19 months Erection & Ready for Commissioning:18-21 months (1st-6th) 6 units by 21 months. Unit-2. Unit-3. Unit-4. Unit-5. Unit-6. Unit-7; 25 Months; Engineering: 0-9 months Dispatch: 19-22 months Rcpt at site:20-23 months Erection & Ready for Commissioning:21-25 months (7th-13th) 7 units by 25 months. Unit-8. Unit-9. Unit-10. Unit-11. Unit-12. Unit-13. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformer. | Supplementing Sub-Clause GCC 1.1(ee) The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 765kV Transformer Package 7TR-19-BULK for 13 x 500 MVA, 765/400/33kV, 1-Ph Transformers under Procurement of 765kV & 400kV class Transformers and Reactors of various Capacities (Lot-7). Specification no.: CC/NT/W-TR/DOM/A06/26/02882; Remark (Indicative Period in Months from Award). Unit-1; 21 Months; Engineering: 0-8 months Dispatch: 16-18 months Rcpt at site:17-19 months Erection & Ready for Commissioning:18-21 months (1st-6th) 6 units by 21 months. Unit-2; 21 Months. Unit-3; 21 Months. Unit-4; 21 Months. Unit-5; 21 Months. Unit-6; 21 Months. Unit-7; 25 Months; Engineering: 0-9 months Dispatch: 19-22 months Rcpt at site:20-23 months Erection & Ready for Commissioning:21-25 months (7th-13th) 7 units by 25 months. Unit-8; 25 Months. Unit-9; 25 Months. Unit-10; 25 Months. Unit-11; 25 Months. Unit-12; 25 Months. Unit-13; 25 Months. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformer. |
|  | GCC 21.1, Section-V, SCC, Vol-I of bidding documents | Supplementing the Clause GCC 21.1 with the following: The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 765kV Transformer Package 7TR-19-BULK for 13 x 500 MVA, 765/400/33kV, 1-Ph Transformers under Procurement of 765kV & 400kV class Transformers and Reactors of various Capacities (Lot-7). Specification no.: CC/NT/W-TR/DOM/A06/26/02882; Remark (Indicative Period in Months from Award). Unit-1; 21 Months; Engineering: 0-8 months Dispatch: 16-18 months Rcpt at site:17-19 months Erection & Ready for Commissioning:18-21 months (1st-6th) 6 units by 21 months. Unit-2. Unit-3. Unit-4. Unit-5. Unit-6. Unit-7; 25 Months; Engineering: 0-9 months Dispatch: 19-22 months Rcpt at site:20-23 months Erection & Ready for Commissioning:21-25 months (7th-13th) 7 units by 25 months. Unit-8. Unit-9. Unit-10. Unit-11. Unit-12. Unit-13. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformer. | Supplementing the Clause GCC 21.1 with the following: The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 765kV Transformer Package 7TR-19-BULK for 13 x 500 MVA, 765/400/33kV, 1-Ph Transformers under Procurement of 765kV & 400kV class Transformers and Reactors of various Capacities (Lot-7). Specification no.: CC/NT/W-TR/DOM/A06/26/02882; Remark (Indicative Period in Months from Award). Unit-1; 21 Months; Engineering: 0-8 months Dispatch: 16-18 months Rcpt at site:17-19 months Erection & Ready for Commissioning:18-21 months (1st-6th) 6 units by 21 months. Unit-2; 21 Months. Unit-3; 21 Months. Unit-4; 21 Months. Unit-5; 21 Months. Unit-6; 21 Months. Unit-7; 25 Months; Engineering: 0-9 months Dispatch: 19-22 months Rcpt at site:20-23 months Erection & Ready for Commissioning:21-25 months (7th-13th) 7 units by 25 months. Unit-8; 25 Months. Unit-9; 25 Months. Unit-10; 25 Months. Unit-11; 25 Months. Unit-12; 25 Months. Unit-13; 25 Months. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformer. |
|  | Appendix-4 to Contract Agreement, Section-VI, Vol-I of bidding documents | - The Project Completion Schedule shall be as follows: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 765kV Transformer Package 7TR-19-BULK for 13 x 500 MVA, 765/400/33kV, 1-Ph Transformers under Procurement of 765kV & 400kV class Transformers and Reactors of various Capacities (Lot-7). Specification no.: CC/NT/W-TR/DOM/A06/26/02882; Remark (Indicative Period in Months from Award). Unit-1; 21 Months; Engineering: 0-8 months Dispatch: 16-18 months Rcpt at site:17-19 months Erection & Ready for Commissioning:18-21 months (1st-6th) 6 units by 21 months. Unit-2. Unit-3. Unit-4. Unit-5. Unit-6. Unit-7; 25 Months; Engineering: 0-9 months Dispatch: 19-22 months Rcpt at site:20-23 months Erection & Ready for Commissioning:21-25 months (7th-13th) 7 units by 25 months. Unit-8. Unit-9. Unit-10. Unit-11. Unit-12. Unit-13. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformer. ……………………………………………………. ……………………………………………………….. | - The Project Completion Schedule shall be as follows: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 765kV Transformer Package 7TR-19-BULK for 13 x 500 MVA, 765/400/33kV, 1-Ph Transformers under Procurement of 765kV & 400kV class Transformers and Reactors of various Capacities (Lot-7). Specification no.: CC/NT/W-TR/DOM/A06/26/02882; Remark (Indicative Period in Months from Award). Unit-1; 21 Months; Engineering: 0-8 months Dispatch: 16-18 months Rcpt at site:17-19 months Erection & Ready for Commissioning:18-21 months (1st-6th) 6 units by 21 months. Unit-2; 21 Months. Unit-3; 21 Months. Unit-4; 21 Months. Unit-5; 21 Months. Unit-6; 21 Months. Unit-7; 25 Months; Engineering: 0-9 months Dispatch: 19-22 months Rcpt at site:20-23 months Erection & Ready for Commissioning:21-25 months (7th-13th) 7 units by 25 months. Unit-8; 25 Months. Unit-9; 25 Months. Unit-10; 25 Months. Unit-11; 25 Months. Unit-12; 25 Months. Unit-13; 25 Months. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformer. ……………………………………………………. ……………………………………………………….. |