## Sheet2
ACTIVITY SCHEDULE for Qualifying Requirements for Provision of two nos. 220 kV Line Bays at 765kV Fatehpur Substation
S. NO. | DESCRPTION OF ACTIVITIES | DAYS
| Total | 52 weeks
1 | SITE MOBLIZATION
2 | S0URCE APPROVAL, STORE CONSTRUCTION, STATUTARY COMPLIANCE SUCH AS LABOUR LICENCE , WCP, CAR POLICY ETC , LAYOUT MARKING, APPROVAL OF VENDOR
3 | SITE LEVELLING
5 | Submission of Drawings and documents
a. | SLD
b | OGA and Electrical Plan and Section Layouts
c | Foundation and cable trench layout
d | EKD, clearance and Earth Mat layout
f | Control and Protection system drawings
g | Power and control cable schedules
h | Equipment drawings
6 | Supply of Items at site (Including vendor finalization, Inspection, testing, delivery at site)
a. | Circuit Breaker, CT, CVT, Isolator, Wave trap, Surge arresstor
b | Control and Protection Panels
c | Telecom Equipments
d | Erection Hardware Items
f | Power and control cables
g | Towers and structures
h | Other Items
h | Spares
8 | COMPLETION OF EQUIPMENT FOUNDATION
9 | COMPLETION OF SPR CIVIL WORK |  | ,
10 | Erection
a. | Circuit Breaker, CT, CVT, Isolator, Wave trap, Surge arresstor
b | Control and Protection Panels
c | Telecom Equipments
d | Erection Hardware Items
f | Power and control cables
g | Structures
h | Other Items
11 | Commissioning
12 | COMPLETION OF ROAD AND DRAIN
13 | COMPLETION OF SECURITY GATE AND BOUNDARY WALL WORK and all associated work.
14 | FINAL CLEANING AND HANDING OVER