| Sl. No | Cl. Ref. | Existing Provision in the Bidding Documents | Amended as |
| --- | --- | --- | --- |
|  | Section Project Clause 4 (PHYSICAL AND OTHER DESIGN DATA) | …………… COASTAL AREA – Yes …………… | …………… COASTAL AREA – NA …………… |
|  | ITB 24.1 (c) in BDS | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-09-BULK for procurement of 15x500 MVA, 400/220/33KV, 3-Ph Transformers under Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-5). Specification no.: CC/NT/W-TR/DOM/A01/25/03728; Remark (Indicative Period in Months from Award). Unit-1; 18 Months; Engineering: 0-16 months Dispatch: 15-22 months 2 units in each month (15-21 months) 1 unit in each month (22 months) Receipt at site: 16-23 months 2 units in each month (16-22 months) 1 unit in each month (23 months) Erection & Ready for Commissioning: 18-25 months 2 units in each month (18-24 months) 1 unit in each month (25 months). Unit-2; 18 Months. Unit-3; 19 Months. Unit-4; 19 Months. Unit-5; 20 Months. Unit-6; 20 Months. Unit-7; 21 Months. Unit-8; 21 Months. Unit-9; 22 Months. Unit-10; 22 Months. Unit-11; 23 Months. Unit-12; 23 Months. Unit-13; 24 Months. Unit-14; 24 Months. Unit-15; 25 Months. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/ equipment/ material/ services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformers. | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-09-BULK for procurement of 15x500 MVA, 400/220/33KV, 3-Ph Transformers under Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-5). Specification no.: CC/NT/W-TR/DOM/A01/25/03728; Remark (Indicative Period in Months from Award). Unit-1; 20 Months; Engineering: 0-16 months Dispatch: 15-22 months 6 units in every 3 months from 15th to 20th month 3 units in 2 months from 21st to 22nd month Receipt at site: 16-23 months 6 units in every 3 months from 16th to 21st month 3 units in 2 months from 22nd to 23rd month Erection & Ready for Commissioning: 1st unit-6th unit by 20th month 7th unit-12th unit by 23rd month 13th unit-15th unit by 25th month. Unit-2; 20 Months. Unit-3; 20 Months. Unit-4; 20 Months. Unit-5; 20 Months. Unit-6; 20 Months. Unit-7; 23 Months. Unit-8; 23 Months. Unit-9; 23 Months. Unit-10; 23 Months. Unit-11; 23 Months. Unit-12; 23 Months. Unit-13; 25 Months. Unit-14; 25 Months. Unit-15; 25 Months. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/ equipment/ material/ services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformers. |
|  | GCC 1.1(e) & 1.1(ee) in SCC | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-09-BULK for procurement of 15x500 MVA, 400/220/33KV, 3-Ph Transformers under Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-5). Specification no.: CC/NT/W-TR/DOM/A01/25/03728; Remark (Indicative Period in Months from Award). Unit-1; 18 Months; Engineering: 0-16 months Dispatch: 15-22 months 2 units in each month (15-21 months) 1 unit in each month (22 months) Receipt at site: 16-23 months 2 units in each month (16-22 months) 1 unit in each month (23 months) Erection & Ready for Commissioning: 18-25 months 2 units in each month (18-24 months) 1 unit in each month (25 months). Unit-2; 18 Months. Unit-3; 19 Months. Unit-4; 19 Months. Unit-5; 20 Months. Unit-6; 20 Months. Unit-7; 21 Months. Unit-8; 21 Months. Unit-9; 22 Months. Unit-10; 22 Months. Unit-11; 23 Months. Unit-12; 23 Months. Unit-13; 24 Months. Unit-14; 24 Months. Unit-15; 25 Months. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/ equipment/ material/ services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformers. | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-09-BULK for procurement of 15x500 MVA, 400/220/33KV, 3-Ph Transformers under Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-5). Specification no.: CC/NT/W-TR/DOM/A01/25/03728; Remark (Indicative Period in Months from Award). Unit-1; 20 Months; Engineering: 0-16 months Dispatch: 15-22 months 6 units in every 3 months from 15th to 20th month 3 units in 2 months from 21st to 22nd month Receipt at site: 16-23 months 6 units in every 3 months from 16th to 21st month 3 units in 2 months from 22nd to 23rd month Erection & Ready for Commissioning: 1st unit-6th unit by 20th month 7th unit-12th unit by 23rd month 13th unit-15th unit by 25th month. Unit-2; 20 Months. Unit-3; 20 Months. Unit-4; 20 Months. Unit-5; 20 Months. Unit-6; 20 Months. Unit-7; 23 Months. Unit-8; 23 Months. Unit-9; 23 Months. Unit-10; 23 Months. Unit-11; 23 Months. Unit-12; 23 Months. Unit-13; 25 Months. Unit-14; 25 Months. Unit-15; 25 Months. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/ equipment/ material/ services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformers. |
|  | GCC 21.1 in SCC | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-09-BULK for procurement of 15x500 MVA, 400/220/33KV, 3-Ph Transformers under Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-5). Specification no.: CC/NT/W-TR/DOM/A01/25/03728; Remark (Indicative Period in Months from Award). Unit-1; 18 Months; Engineering: 0-16 months Dispatch: 15-22 months 2 units in each month (15-21 months) 1 unit in each month (22 months) Receipt at site: 16-23 months 2 units in each month (16-22 months) 1 unit in each month (23 months) Erection & Ready for Commissioning: 18-25 months 2 units in each month (18-24 months) 1 unit in each month (25 months). Unit-2; 18 Months. Unit-3; 19 Months. Unit-4; 19 Months. Unit-5; 20 Months. Unit-6; 20 Months. Unit-7; 21 Months. Unit-8; 21 Months. Unit-9; 22 Months. Unit-10; 22 Months. Unit-11; 23 Months. Unit-12; 23 Months. Unit-13; 24 Months. Unit-14; 24 Months. Unit-15; 25 Months. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/ equipment/ material/ services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformers. | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-09-BULK for procurement of 15x500 MVA, 400/220/33KV, 3-Ph Transformers under Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-5). Specification no.: CC/NT/W-TR/DOM/A01/25/03728; Remark (Indicative Period in Months from Award). Unit-1; 20 Months; Engineering: 0-16 months Dispatch: 15-22 months 6 units in every 3 months from 15th to 20th month 3 units in 2 months from 21st to 22nd month Receipt at site: 16-23 months 6 units in every 3 months from 16th to 21st month 3 units in 2 months from 22nd to 23rd month Erection & Ready for Commissioning: 1st unit-6th unit by 20th month 7th unit-12th unit by 23rd month 13th unit-15th unit by 25th month. Unit-2; 20 Months. Unit-3; 20 Months. Unit-4; 20 Months. Unit-5; 20 Months. Unit-6; 20 Months. Unit-7; 23 Months. Unit-8; 23 Months. Unit-9; 23 Months. Unit-10; 23 Months. Unit-11; 23 Months. Unit-12; 23 Months. Unit-13; 25 Months. Unit-14; 25 Months. Unit-15; 25 Months. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/ equipment/ material/ services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformers. |
|  | Appendix-4: TIME SCHEDULE, Section-VI: FP, Vol.-I of the Bidding Documents | 1. The Project Completion Schedule shall be as follows: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-09-BULK for procurement of 15x500 MVA, 400/220/33KV, 3-Ph Transformers under Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-5). Specification no.: CC/NT/W-TR/DOM/A01/25/03728; Remark (Indicative Period in Months from Award). Unit-1; 18 Months; Engineering: 0-16 months Dispatch: 15-22 months 2 units in each month (15-21 months) 1 unit in each month (22 months) Receipt at site: 16-23 months 2 units in each month (16-22 months) 1 unit in each month (23 months) Erection & Ready for Commissioning: 18-25 months 2 units in each month (18-24 months) 1 unit in each month (25 months). Unit-2; 18 Months. Unit-3; 19 Months. Unit-4; 19 Months. Unit-5; 20 Months. Unit-6; 20 Months. Unit-7; 21 Months. Unit-8; 21 Months. Unit-9; 22 Months. Unit-10; 22 Months. Unit-11; 23 Months. Unit-12; 23 Months. Unit-13; 24 Months. Unit-14; 24 Months. Unit-15; 25 Months. ……………………… | 1. The Project Completion Schedule shall be as follows: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-09-BULK for procurement of 15x500 MVA, 400/220/33KV, 3-Ph Transformers under Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-5). Specification no.: CC/NT/W-TR/DOM/A01/25/03728; Remark (Indicative Period in Months from Award). Unit-1; 20 Months; Engineering: 0-16 months Dispatch: 15-22 months 6 units in every 3 months from 15th to 20th month 3 units in 2 months from 21st to 22nd month Receipt at site: 16-23 months 6 units in every 3 months from 16th to 21st month 3 units in 2 months from 22nd to 23rd month Erection & Ready for Commissioning: 1st unit-6th unit by 20th month 7th unit-12th unit by 23rd month 13th unit-15th unit by 25th month. Unit-2; 20 Months. Unit-3; 20 Months. Unit-4; 20 Months. Unit-5; 20 Months. Unit-6; 20 Months. Unit-7; 23 Months. Unit-8; 23 Months. Unit-9; 23 Months. Unit-10; 23 Months. Unit-11; 23 Months. Unit-12; 23 Months. Unit-13; 25 Months. Unit-14; 25 Months. Unit-15; 25 Months. ……………………… |
|  | First Envelope and Bid Forms | In view of the above amendments, ‘First Envelope and Bid Forms’ excel stand revised as ‘First_Envelope_and_Bid_Forms_rev02’. Note- Bidders are requested to consider the revised excel ‘First_Envelope_and_Bid_Forms_rev02’ for bid preparation/submission. It may be noted that while submitting the bid, Bidders are required to change the excel file name from ‘First_Envelope_and_Bid_Forms_rev02’ to ‘First_Envelope_and_Bid_Forms’. As per the provisions of the portal, it is mandatory to upload the excel file titled ‘First_Envelope_and_Bid_Forms’ (Bidders may refer user manuals at the portal https://etender.powergrid.in regarding submission of bid). |  |