## Clarification No-II (Technical)
CLARIFICATION NO.-II (TECHNICAL) DATED 17.07.2023 to bidding documents of TRANSMISSION LINE PACKAGE TW01 FOR DIVERSION WORKS OF 5 NOS. OF POWERGRID TRANSMISSION LINES FOR BANDA MAJOR IRRIGATION DAM PROJECT OVER DHASAN RIVER IN DISTT-SAGAR (M.P.) BY WATER RESOURCE DEPARTMENT SAGAR INCLUDING SUPPLY OF TOWER, CONDUCTOR, INSULATOR, EARTHWIRE, OPGW, HARDWARE FITTINGS AND ACCESSORIES FOR CONDUCTOR, EARTHWIRE & OPGW AND DE-STRINGING / DISMANTLING WORKS UNDER CONSULTANCY SERVICES TO M/S. WATER RESOURCE DEPARTMENT, BINA PMU (WRD);SPECIFICATION NO.: CC/NT/W-TW/DOM/A00/23/04535
Sl No: | TS Reference/subject | Description as per Bid Documant | Query / Clarification | Reply
1 | Dismantling work :Tower parts, Bolts & Nuts |  | Kindly confirm the dismantling of tower is to be done as manually i.e. piece wise dismantling or to cut from stub level with the help of gas cutter. Also confirm full stub has to be dismantled by braking concrete till base or stub to be cutupto ground leve | It is to confirm that dismantling of tower is to be done manually i.e. piecewise dismantling. Wherever tack welded sections of tower are encountered, the same may be cut with suitable methods in consultation with POWERGRID site in-charge. Dismantling of stub is not in the scope of bidder.
2 |  |  | Dismantled towers are to be returned in scape condition or in usable condition. Whether dismantled tower has to be stacked mark number wise in PGCIL store | Dismantled towers are to be returned in usable condition and the same has to be stacked mark number wise in PGCIL store by Bidder.
3 |  |  | Dismantled material’s segregation and staking at PGCIL Store in whose scope | Dismantled material’s segregation and staking at PGCIL Store is in the scope of Bidder.
4 |  |  | Dismantled Bolt Nuts can not be return as per BOM weight as there are chances of misplaced during disentitling work, Please confirm | All both and nuts removed from the towers shall be returned to POWERGRID in good condition. In respect of tack welded Bolt & Nuts, the same shall be returned as scrap.
5 | Dismantling work : Conductor |  | Whether dismantled conductor has to be rewinded in drum and to be returned in good usable condition or it has to be returned in scrap condition i.e bits of random length. | The conductor/EW/OPGW removed from the existing line is envisaged for re-use/ utilization by the employer in other projects. Proper handling and safety of the conductor during de-stringing, storage at site, measuremant of conductor lengths, rewinding on drums at site and safe transportation to employers designated stores shall be included in the scope of work. Complete conductor de-strung from line have to be returned in good usable condition
6 |  |  | What percentage will be considered towards conduction erosion to work out unit weight of dismantled conductor
7 | Dismantling work :Earthwire |  | Whether dismantled earth wire/OPGW has to be re-winded in drum and to be returned in good usable condition or it has to be returned in scrap condition i.e bits of random length
8 | Dismantling work : Insulator |  | Long rod/Disc/polymer insulator must have been used in existing line, while dismantling some of the insulators/Grading rings may get damaged/misplaced. Whether damaged insulator/grading ring will be considered as accepted while returning | Bidder have to return Long Rod/Disc/Polymer insulator in good condition.Further, If any damage happens during destringing unexpectedly, the same is to be notified to POWERGRID site-in-charge and damaged items are also to be returned to POWERGRID designated store as scrap.
9 | Dismantling work : Line Hardware Fittings |  | It might happen, that corona ring, arcing horn, bolts & nuts are missing in existing line hardware fittings, also while dismantling some of the items may get misplaced so whether dismantled material i.e hardware has to be retuned in scrap condition or weight basis, Pls confirm | Bidder have to return Hardware Fittings in good condition. In case any missing parts in the existing line, the same is to be notified to POWERGRID site-in-charge. Further, if any damage happens during destringing unexpectedly, the same is to be notified to POWERGRID site-in-charge and damaged items are also to be returned to POWERGRID designated store as scrap.
10 | BIRD FLY DIVERTORS |  | Since this is very new item, kindly clarify us which type ofBird Flight Diverter is to be supplied i.e. The dynamic solar powered LED type OR LED type OR Non-LED type. Also the quantity bifurcation of the Bird Flight Diverter is required | Kindly refer clause 1.3.7 of section IVC
11 | BPS |  | Based on our past experience, in 765 KV S/C Transmission lines 120 KN SRI was used. However in this tender-BOQ there is requiremant of 160 KN SRI instead of 120 KN. We request you to kindly clarify whether 160KN or 120 KN SRI will be used in 765KV S/C line | Please refer Amendment-I
12 | BPS |  | If 160KN SRI is to be used, then please inform design test and String test is required for 765KV S/C TL- 160KN Insulators.
13 | BPS |  | Also we have observed that there is mismatch of quantity calculation in both 765KV DC and SC lines w.r.t. hardware quantities. Kindly clarify.
14 | Dismantling work :Tower parts, Bolts & Nuts |  | Please confirm the PGCIL store location to surrender the existing line dismantled Tower parts and Stringing materials. This help the to estimate the proper transportation cost. | Dismantled Tower parts and line materials are to be handed over to POWERGRID, Bina Substation with address given below. POWER GRID CORPORATION OF INDIA LTD, 765/400/220 Kv Sub Station, Village Dhanora, Khimlasa Road, Bina, District: Sagar Madhya Pradesh - 470113
15 | Dismantling work :Tower parts, Bolts & Nuts |  | Please confirm the dismantled Tower parts and Stringing materials is to be surrender in good condition / damaged condition. | Dismantled towers are to be returned in usable condition and the same has to be stacked mark number wise in PGCIL store by Bidder.
16 | Dismantling work : Conductor/earthwire |  | To rewind the dismantled Conductor and Earthwire the empty drums will be provided by PGCIL or it will be in the scope of contractors. Please confirm. | The conductor/Earthwire/OPGW removed from the existing line is envisaged for re-use/ utilization by the employer in other projects. Proper handling and safety of the conductor during de-stringing, storage at site, measuremant of conductor lengths, rewinding on drums at site and safe transportation to employers designated stores shall be included in the scope of work. Empty Conductor drums after utilization of conductor supplied by the bidder shall be used for rewinding of de-strung conductor.
17 | Dismantling work :Tower parts, Bolts & Nuts |  | Whether dismantling of existing foundation to be done completely (3.5M) or its limited to some ground level. Please confirm. | Dismantling of stub is not in scope of bidder.
18 | 01_1 Section IA WRD 06062023, 1.3 .1, Pg 8 The entire quantity of dismantled line materials viz. tower parts, conductor, earthwire, OPGW, hardware fittings, insulators and conductor, earthwire & OPGW accessories removed from the existing line shall be transported to the designated POWERGRID stores by the contractor at his own cost. The Bidder shall submit his offer taking into consideration transportation cost of the dismantled material. |  | We request you to kindly confirm the store locations where dismantled material is to be transported. | Dismantled Tower parts and line materials are to be handed over to POWERGRID, Bina Substation with address given below. POWER GRID CORPORATION OF INDIA LTD, 765/400/220 Kv Sub Station, Village Dhanora, Khimlasa Road, Bina, District: Sagar Madhya Pradesh - 470113
19 |  |  | We understand that stacking of dismantled material at store is not in contractor's scope. Kindly confirm. | Dismantled towers are to be returned in usable condition and the same has to be stacked mark number wise in PGCIL store by Bidder.
20 |  |  | We understand that handing over of dismantled tower material is to be done on weight basis in presence of employer. If any difference in weight is encountered with respect to PGCIL design weights not attributable to contractor same shall not be liability of contractor. Contractor will not be charged for same. Kindly confirm. | It is the responsibility of the bidder to return entire towers dismantled from the transmission line in good condition. In case any missing tower members in the existing line, the same is to be notified to POWERGRID site-in-charge before dismantling of the tower.
21 |  |  | We understand during dismantling there may be damage to individual sections. Contractor will not hold any liability for that. Kindly confirm. | Proper handling and safety during dismantling, storage at site and safe transportation to employers designated stores is included in the scope of work.