POWER GRID CORPORATION OF INDIA LIMITED

(A Government of India Enterprise)

TERM OF REFERENCE (ToR)

FOR

(SECTION-II of RFP DOCUMENTS)

Appointment of consultant for developing various engineering drawings during execution of 400 kV AIS Substation Extension works for Substation Pkg SS-129.

(Specification No.: CC/NT/S-CONS/DOM/A04/24/13294)

Registered Office

B-9, Qutab Institutional Area, Katwaria Sarai, New Delhi – 110 016

Corporate office

“Saudamini”, Plot No.2, Sector 29, Gurgaon – 122 001 (Haryana)

(This document is meant for exclusive purpose of bidding against this specification only and shall not be transferred, reproduced or otherwise used for purpose other than that for which it is specifically issued)

- Scope of Works:

Scope of Work for developing various engineering drawings/documents during execution of 765 kV and 400 kV AIS Substation Extension works under Substation Package SS-129:

  - The consultant is engaged to develop and provide engineering drawings and documents for Substation Extension works under Substation Pkg SS-129. The list of drawings/documents proposed to be developed with its respective submission schedule are listed in Appendix-I for respective substations mentioned in Appendix-II.

  - The Engineering Consultant shall develop and provide detailed engineering drawings and documents necessary for the successful completion of the extension of the 765 kV and 400 kV AIS substation. The Drawing/Document developed by consultant shall ensure compliance with necessary electrical and mechanical statutory requirements, relevant Indian and International standards, regulations, and POWERGRID Technical Specifications. The broad requirements for preparation and submission of Engineering Drawings and Documents are outlined below:

- The drawings shall be prepared and provided using AutoCAD software and shall be construction ready.

- The Consultant shall provide PDF versions of the drawings to be released to the site for construction through POWERGRID DREAMS Portal.

- The drawings shall include a comprehensive BOM (Bill of Materials) wherever necessary.

- The Consultant shall make multiple revisions to the drawings and design documents as required and informed by POWERGRID until the completion of the work.

- Preparation and submission of as-built drawings post-construction, reflecting any changes made during execution in editable format, is also included in the current scope.

- The drawings and documents are considered complete only after the final submission of their as-built versions, including all previous revisions in any/all approval categories.

- The Contractor shall prepare and submit drawings and documents as per the submission schedule mentioned in Appendix-I.

- The drawings prepared shall be clearly marked and version controlled.

- The Consultant is required to attend meetings at the POWERGRID Gurgaon office for discussions and review of drawings as and when required.

- Coordination with existing substation, other contractors, and suppliers for the preparation of drawings to ensure seamless integration of the extension work is within the current scope.

- It is the responsibility of the Consultant to develop the necessary drawings/documents with input available and provided by POWERGRID. If existing details are not available in AutoCAD or PDF format, the responsibility to develop the drawings lies with the Consultant.

- For the extension work of the substation, if necessary, inputs are required to be collected from the respective site, the Consultant shall visit the site and prepare the drawings.

  - The price quoted by the consultant is firm and covers the complete scope of the work mentioned above. It is the responsibility of the consultant to develop and provide the necessary drawings and documents for the successful execution of the complete substation extension work. Any details required for the detailed engineering drawings/documents not mentioned above but necessary for the successful execution of the construction work at the site are deemed to be included.

- Employer (POWERGRID) Provided Inputs:

- Input drawings (in PDF format) of the existing substation as available.

- Equipment drawings (Transformers, Reactors, CB, ISO, CT, CVT, LA & WT).

- Gantry Structure Drawing.

- Timelines:

| S.no. | Scope of work | Completion from the date of Award |
| --- | --- | --- |
| 1 | Appointment of consultant for developing various engineering drawings during execution of 400 kV AIS Substation Extension works for Substation Pkg SS-129. | 3 Months |

- The price quoted must be inclusive of all charges except applicable GST, which shall be paid extra as applicable.

- Payment Terms

- Release of Payment:

- 80% of the payment for respective drawings/documents shall be released after final approval of the drawing in Category-I.

- The remaining 20% of the complete contract amount shall be released together after the submission of as-built drawings for all substations.

- The prices shall be firm and not be subject to any price variation whatsoever during the currency of the Contract.

*****

Appendix-I

| Sl.No | Drawing details | Submission Schedule from the date of LOA | Re-submission of revised drawings in CAT-II/III | Remarks |
| --- | --- | --- | --- | --- |
|  | Overall Electrical Layout-Plan & Sections as per scope in Tender drawing / Technical Specification | 10 days | Within 5days after release of drawing |  |
|  | Electrical & Foundation layout for HV/IV Auxiliary buses, tertiary delta formation including tertiary auxiliary bus, Neutral formation including Neutral auxiliary bus for 3-ph bank formation with 1-ph units of 765kV Transformers (including structural & foundation design & drawings of support structure) | 10 days | -do- |  |
|  | DSLP layout drawing. | 10 days | -do- |  |
|  | Overall switchyard Foundation Layout plan for Towers/equipment’s | 20 days | -do- |  |
|  | Structural & Foundation design & drawing of tertiary delta & Neutral Bus Arrangement. |  |  |  |
|  | Switchyard Cable Trench Layout with invert level (BOM of PVC pipes, Hume pipes, cable tray & covers etc. to be shown in drawings) | 20 days | -do- |  |
|  | Substation Earthing Layout including Gravel layout. | 25 days | -do- |  |
|  | Power and control cable schedule (including BOM for cable/glands/lugs to be shown in drawings) | 25 days | -do- |  |
|  | Erection Key Diagram & Erection Bill of Quantity | 30 days | -do- |  |
|  | Outdoor/Indoor Illumination Layout-Layout and SLD (BOM) | 30 days | -do- |  |
|  | Indoor Cable trench & Earthing Layout for SPR | 30 days | -do- |  |

Approval Category of Drawings:

- Approved/released for fabrication/construction.

- Approved/released for fabrication/ construction subject to incorporation of comments and modification as noted. Revised drawing required for approval.

- To be resubmitted for approval after incorporating the comments.

Appendix-II

- LOCATION OF SUBSTATION:

| S. No. | Name of Substation | Name of State | Nearest Railway Station |
| --- | --- | --- | --- |
| 1 | 765/400kVJhatikara S/S | New Delhi | New Delhi Railway Station |
| 2 | 400 kV Rajgarh S/S | Madhya Pradesh | Rajgarh |
| 3 | 400/220kV Tumkur (Pavagada) S/S | Karnataka | Hindupur (AP) |