Section – 6: TERMS AND PROCEDURES OF PAYMENT

The Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules.  Payments will be made in the currencies quoted by the Bidder unless otherwise agreed between the parties. The Contractor may make applications for payment in respect of part deliveries as work proceeds.

1. TERMS OF PAYMENT

The following terms & Conditions will apply.

| S.N. | Activity | Payment Terms |
| --- | --- | --- |
| 1 | Route Alignment | 90% Payment upon completion of route alignment for entire line, submission of soft copy of documents and route alignment report & acceptance by Engineer-In-Charge. Balance 10% Final payment after successful completion of entire scope of work and acceptance/certification by the Engineer-In-Charge. |
| 2 | Detail Survey | Progressive payment of 65% upon completion of detail survey for section and submission of soft copy of PLSCADD profiles & acceptance by Engineer-In-Charge. 25% of the total payment against detailed survey shall be released only after submission of necessary documents required for forest proposal. Balance 10% Final payment after successful completion of entire scope of work and acceptance/certification by the Engineer-In-Charge. |
| 3 | Soil Investigation | 40 % payment upon submission of borelog data & acceptance by Engineer-In-Charge. 50 % payment upon completion of work and submission of Soil investigation report & acceptance by Engineer-In-Charge. Balance 10% Final payment after successful completion of entire scope of work and acceptance/certification by the Engineer-In-Charge. |

| 1.2 | Payment towards Price adjustment: Not Applicable |
| --- | --- |

1.3     Payment towards Taxes and Duties

Taxes and duties applicable as per Indian Tax laws, concerning Supply of Services in respect of transaction between the Employer and the Contractor, shall be reimbursed by the Employer as follows:

(a) In case of Services, the GST shall be reimbursed along with payment on completion of Services as brought out above.

Payment towards taxes & duties shall be released by the Employer directly to the Contractor.

2.	PAYMENT PROCEDURES

2.1	Method of Payment

The Employer shall make payments promptly within Fifteen (15) days of submission of an invoice/claim by the Contractor, complete in all respects and supported by the requisite documents and fulfillment of stipulated conditions, if any.  All the payment shall be released to the Contractor directly.

All payments to be made directly to the Contractor shall be made by the Employer though electronic payment mechanism (e-payment) for which necessary details shall be tied up during execution of the Contract. However, a request for payment to be released through cheque shall be considered on case to case basis and merit of the same.

Note:	Pro-rata shall refer to functionally complete part(s) of the facilities, for which unit rates are identified in the contract.

2.1.1 POWERGRID is registered on TReDS (Trade Receivables Discounting System) platforms namely i.e. RXIL (Receivable Exchange of India Limited ), M1-xchange (Mynd Solutions Private Limited) and Invoicemart (A.TReDS Limited) and the facility of the same may be availed by Micro, Small and Medium Enterprises (MSMEs) for payment.

2.2	Bill Tracking System

Prior to submission of bills in physical form, the Contractor shall submit its bills using POWERGRID’s Vendor Bill Tracking System as per procedure detailed herein below. Further ,the Contractor may track the status of its bills using POWERGRID’s ‘On-line Vendor Bill Tracking System’. To use this system the Contractor is required to get itself registered once online at POWRGRID’s ERP Portal with the link URL (https://etender.powergrid.in). Once registered, the Contractor may track status of bills submitted, passed and paid by POWERGRID’s Corporate Centre and Regional Office under this Contract and other Contracts awarded on it by POWERGRID by following the method detailed herein below:

- Once registered, the Contractor can log-in to POWERGRID’s Vendor Bill Tracking System with Vendor Log-In ID and Password.

- After login as at (a) above, Contractor is required to make the entry on POWERGRID’s ERP Portal under the tab “Submit New Invoice” and shall fill all details along with the MSE status. Upon submission, a 16 digit unique BTS number will be generated and the Contractor/Supplier will receive an automated e-mail forwarding the unique BTS number.

- The physical bills alongwith printed copy of e-mail received from BTS (unique BTS number) shall be submitted by the Contractor.

- On receipt of physical bill, concerned POWERGRID’s official shall online acknowledge the receipt of bill. This action will trigger an automated mail to the Contractor intimating that the physical copy of the bill has been received and is under verification / processing. However, on receipt of incomplete bill and/or non-receipt of physical bill by POWERGRID official, the incomplete bills/ digital entry in BTS (as the case may be) shall be returned to the Contractor by POWERGRID, which can be viewed under the tab “Invoice Returned”.

- The day the payment is made a mail stating the “Bill number, net payment amount and details of the bank from where the payment has been made” will be sent to the Contractor.

- The status of Bill submitted by the Contractor can be checked through the BTS number under tab “Invoice Submitted”.