## A
Table- A-1 IMPLEMENTATION PLAN
Sl. No. | Description of Work | Commencement | Completion
(Period in weeks from LOA)
1 | Preparation of Survey format/ Design Document/ DRS approval | 1 | 2
2 | Preparation of Functional test procedure, plan & approval | 3 | 4
3 | Preparation of Type Test procedure,plan & approval | 3 | 4
4 | Preparation of FAT documents & approval | 4 | 5
5 | Preparation of SAT Documents & approval | 8 | 10
6 | Type & Functional Testing | 6 | 12
7 | Batch-1*
i | BOQ Finalization (Lot-1) | 2 | 3
ii | FAT & Despatch clearance (LOT-1) | 10 | 12
iii | Transportation to sites (LOT-1) | 13 | 15
iv | Site Installation, Testing & commissioning (SAT1 & SAT2) of LOT-1 | 14 | 18
v | BOQ Finalization (TMN) | 2 | 4
vi | FAT & Despatch clearance (TMN) | 12 | 13
vii | Transportation to sites (TMN) | 14 | 15
viii | TMN Installation,Commissioning & Testing (main & back up systems) | 16 | 18
ix | BOQ Finalization (Lot-2) | 14 | 15
x | FAT & Despatch clearance (LOT-2) | 22 | 24
xi | Transportation to sites (LOT-2) | 25 | 27
xii | Site Installation ,Testing & commissioning (SAT1 & SAT2) of LOT-2 | 26 | 30
8 | Batch-2*
i | BOQ Finalization (LOT-1) | 26 | 27
ii | FAT & Despatch clearance | 34 | 36
iii | Transportation to sites | 37 | 39
iv | Site Installation ,Testing & commissioning (SAT1 & SAT2) of LOT-1 | 40 | 44
v | BOQ Finalization (LOT-2) | 37 | 38
vi | FAT & Despatch clearance | 45 | 47
vii | Transportation to sites | 48 | 50
viii | Site Installation ,Testing & commissioning (SAT1 & SAT2) of LOT-2 | 51 | 55
9 | Batch-3*
i | BOQ Finalization (LOT-1) | 49 | 50
ii | FAT & Despatch clearance | 57 | 59
iii | Transportation to sites | 60 | 62
iv | Site Installation ,Testing & commissioning (SAT1 & SAT2) of LOT-1 | 63 | 67
v | BOQ Finalization (LOT-2) | 61 | 62
vi | FAT & Despatch clearance | 69 | 71
vii | Transportation to sites | 72 | 72
viii | Site Installation ,Testing & commissioning (SAT1 & SAT2) of LOT-1 | 73 | 77
10 | Batch-4*
i | BOQ Finalization (LOT-1) | 73 | 74
ii | FAT & Despatch clearance | 81 | 82
iii | Transportation to sites | 83 | 84
iv | Site Installation ,Testing & commissioning (SAT1 & SAT2) of LOT-1 | 84 | 86
v | BOQ Finalization (LOT-2) | 84 | 85
vi | FAT & Despatch clearance | 92 | 93
vii | Transportation to sites | 94 | 95
viii | Site Installation ,Testing & commissioning (SAT1 & SAT2) of LOT-1 | 96 | 97
9 | SAT-3 | 97 | 99
10 | Network Security Audit/ Vulnerability assessment and implementation of mitigation plan | 98 | 104
* | Batch wise projection of requirement of equipments
Batch-1 (Approx. 600 Backbone & Access Equipments)
Batch-2 (Approx. 600 Backbone & Access Equipments)
Batch-3 (Approx. 500 Backbone & Access Equipments)
Batch-4 (Approx. 300 Backbone & Access Equipments)
Note:
1 | POWERGRID may increase/ decrease the quantity of Equipment in each Batch and/ or LOT based on requirement.
2 | POWERGRID may increase/ decrease the no of BATCH/ LOT for delivery of equipment, based on requirement.
3 | POWERGRID may advance/ delay in the implimentation of TMN
4 | SAT-III can be preponed & performed after completion of work under Batch-1/2/3/4.