## Table 1 (hidden)
Tender: | Refurbishment of HVDC Control, Protection, SCADA, Valve Hall Equipment and Valve Cooling System for 2x500 MW Chandrapur HVDC Back to Back (BTB) Station under Add-Cap
Bidder: | Hitachi Energy India Limited
Title: | Set -1 of Commercial Deviations / Clarifications
Sl. No. | Bidding Document | Clause Reference No. | Clause Header | Deviation / Clarification | Provisions as per the bidding document | Detailed description of Deviations / Clarifications the bidder | Reason for Change
1 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section IV, GCC C 4.1, Section-IV, Vol-I | Definitions | Clarification | 4. Time for Commencement and Completion 4.1 The Contractor shall commence work on the Facilities from the Effective Date of Contract and without prejudice to GCC Sub-Clause 21.2 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified in the corresponding Appendix – 4 (Time Schedule) to the Contract Agreement. ................................ | We request to add the definition of "Commencement Date" "Commencement Date" means the date of fulfilment of all conditions stated below: (a) This Contract Agreement has been duly executed for and on behalf of the Employer and the Contractor. (b) The Employer has paid the Contractor the advance payment within 15 days of receipt of eqvt. advance bank guarantee (ABG) C contract performance bank guarantee (CPBG) from contractor. The Contractor shall submit the ABG C CPBG within 15 days from date of of NoA/LoA. Sub Clause 4.1 : The Contractor shall commence work on the Facilities from the Commencement Date of Contract and without prejudice to GCC Sub-Clause 21.2 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified in the corresponding Appendix – 4 (Time Schedule) to the Contract Agreement Time for completion shall be measured from Commencement Date.
2 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section IV, GCC 3.2 | Scope of Facilities | Clarification | The Contractor shall, unless specifically excluded in the Contract, perform all such work and/or supply all such items and materials not specifically mentioned in the Contract but that can be reasonably inferred from the Contract as being required for attaining Completion of the Facilities as if such work and/or items and materials were expressly mentioned in the Contract. | Please clarify if below modification to this Sub-clause is acceptable; 'The Contractor shall, unless specifically excluded in the Contract, perform all such work and/or supply all such items and materials not specifically as mentioned in the Contract but that can be reasonably inferred from the Contract in accordance with the technical specifications as being required for attaining Completion of the Facilities as if such work and/or items and materials were expressly mentioned in the Contract.
3 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section IV, SCC 5, GCC 3.3 | Scope of Facilities | Deviation | If so desired by the Employer, the Contractor shall submit the specifications, price and the terms and conditions relating to the supply thereof for such spares identified by the Employer with validity period of 6 months within 30 days of receipt of request from Employer for its consideration and placement of order. | Request to change the clause as below: If so desired by the Employer, the Contractor shall submit the specifications, price and the terms and conditions relating to the supply thereof for such spares identified by the Employer within the mutually agreed validity period of 6 months within 30 days of receipt of request from Employer for its consideration and placement of order.
4 | Section - V SPECIAL CONDITIONS OF CONTRACT (SCC) | Section V SCC 5, GCC 3.3 | Scope of Facilities | Deviation | The supply of Mandatory Spare Parts, if any, shall be included in the Contract. Beside the aforesaid Mandatory Spares parts, the Contractor shall ensure the availability functionally equivalent spare parts required for the operation and maintenance of the Facilities to the Employer for a minimum period of 15 years from Completion of the Facilities. | Request to change the clause as below: 'The supply of Mandatory Spare Parts, if any, shall be included in the Contract. Beside the aforesaid Mandatory Spares parts, the Contractor shall ensure the availability of functionally equivalent spare parts required for the operation and maintenance of the Facilities to the Employer for a minimum period of 15 years 10 years from Completion of the Facilities.
5 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section IV, SCC 6, GCC 3.4 | Scope of Facilities | Deviation | The Contractor shall guarantee that in the event of termination of production of spare parts by the Contractor or his Sub-Contractor: (i) The Contractor shall send advance notification to the Employer of the pending termination, with 2 (two) years time to permit the Employer to procure needed requirements, and (ii) Following such termination, the Contractor shall furnish at no cost to the Employer the relevant information/ documents and specification of the spare parts from third party, information/documents and specifications of the spare parts shall be furnished by the Contractor to the extent that such documents are available to the Contractor. | Kindly consider the time of advance notification of 6 months as the time period of 2 years may not be possible for advance notification especially under current technological trend.
6 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section IV, GCC 3.5 | Scope of Facilities | Deviation | In case the Contractor fails to supply the spares parts in accordance with the terms stipulated above, the Employer shall sanction the Contractor declaring them ineligible for a stated period of time for future projects. | Request for deletion of the clause.

## Clarification No-VIII
Clarification No-VIII dated 21.01.2025 to the bidding documents of Refurbishment of HVDC Control, Protection, SCADA, Valve Hall Equipment and Valve Cooling System for 2x500 MW Chandrapur HVDC Back to Back (BTB) Station under Add-Cap; Specification Number: CC/NT/W-HVDC/DOM/A00/24/12849
Sl. No. | Bidding Document | Clause Reference No. | Clause Header | Deviation / Clarification | Provisions as per the bidding document | Detailed description of Deviations / Clarifications the bidder | Employer's Response
1 | TS Chapter-11 | Clause 11.8.2(d) | FULFILLMENT OF AVAILABILITY GUARANTEE | Clarification | (d) In case average annual energy availability as described in Para (c) above, is found to be below 98% the system (under present scope) shall be rejected by employer. The system rejection shall be governed as per provision of contract. | We request you to delete the term ‘Rejection of System’ from the said clause. | TS Requirement shall be fullfilled

## Table 3 (hidden)
Tender: | Refurbishment of HVDC Control, Protection, SCADA, Valve Hall Equipment and Valve Cooling System for 2x500 MW Chandrapur HVDC Back to Back (BTB) Station under Add-Cap
Title: | Set -1 of Commercial Deviations / Clarifications
Sl. No. | Bidding Document | Clause Reference No. | Clause Header | Deviation / Clarification | Provisions as per the bidding document | Detailed description of Deviations / Clarifications the bidder | Reason for Change
66 | SECTION - VI SAMPLE FORMS AND PROCEDURES (FORMS) | Section VI Sample Forms and Procedures, APPENDIX-3: INSURANCE REǪUIREMENTS (d).II | Workmen Compensation Policy: | Clarification | The policy may either be project specific covering all men of the Contractor and its Subcontractors. The policy shall be kept valid till the date of Operational Acceptance of the project. Alternatively, if the Contractor has an existing ‘Workmen Compensation Policy’ for all its employees including that of the Subcontractor(s), the Contractor must include the interest of the Employer for this specific Project in its existing ‘Workmen Compensation Policy’ | The policy may either be project specific covering all men of the Contractor and its Subcontractors. The policy shall be kept valid till the date of Operational Acceptance TOC of the project. Alternatively, if the Contractor has an existing ‘Workmen Compensation Policy’ for all its employees including that of the Subcontractor(s), the Contractor must include the interest of the Employer for this specific Project in its existing ‘Workmen
Compensation Policy’
67 | SECTION - VI SAMPLE FORMS AND PROCEDURES (FORMS) | Section VI Sample Forms and Procedures, APPENDIX-3: INSURANCE REǪUIREMENTS (d).III | Workmen Compensation Policy: | Clarification | Without relieving the Contractor of its obligations and responsibilities under this Contract, before commencing work the Contractor shall insure against liability for death of or injury to persons employed by the Contractor including liability by statute and at common law. The insurance cover shall be maintained until all work including remedial work is completed including the Defect Liability Period. The insurance shall be extended to indemnify the Principal for the Principal’s statutory liability to persons employed by the Contractor. | Without relieving the Contractor of its obligations and responsibilities under this Contract, before commencing work the Contractor shall insure against liability for death of or injury to persons employed by the Contractor including liability by statute and at common law. The insurance cover shall be maintained until all work including remedial work is completed including the Defect Liability Period. The insurance shall be extended to indemnify the Principal for the Principal's statutory liability to persons employed by the Contractor. The Contractor shall also ensure that each of its Subcontractors shall effect and maintain insurance on the same basis as the 'Workmen Compensation Policy' effected by the Contractor. | Contractor will maintain WC policy covering its employees and workers as per local ACT.
The Contractor shall also ensure that each of its Subcontractors shall effect and maintain insurance on the same basis as the 'Workmen Compensation Policy' effected by the Contractor.
68 | SECTION - VI SAMPLE FORMS AND PROCEDURES (FORMS) | Section VI Sample Forms and Procedures, APPENDIX-3: INSURANCE REǪUIREMENTS (e) | Contractor’s Plant and Machinery (CPM) Insurance | Clarification | Contractor’s Plant and Machinery (CPM) Insurance The Employer (including without limitation any consultant, servant, agent or employee of the Employer) shall not in any circumstances be liable to the Contractor for any loss of or damage to any of the Contractor’s Equipment or for any losses, liabilities, costs, claims, actions or demands which the Contractor may incur or which may be made against it as a result of or in connection with any such loss or damage. | Contractor’s Plant and Machinery (CPM) Insurance The Employer (including without limitation any consultant, servant, agent or employee of the Employer) shall not in any circumstances be liable to the Contractor for any loss of or damage to any of the Contractor’s Equipment or for any losses, liabilities, costs, claims, actions or demands which the Contractor may incur or which may be made against it as a result of or in connection with any such loss or damage.
69 | SECTION - VI SAMPLE FORMS AND PROCEDURES (FORMS) | Section VI Sample Forms and Procedures, APPENDIX-3: INSURANCE REǪUIREMENTS (e) | Contractor’s Plant and Machinery (CPM) Insurance | Clarification | The Employer shall be jointly insured under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 34.1, except for the Third Party Liability, Automobile Liability Insurance, Workmen Compensation Policy and Contractor's Plant and Machinery (CPM) Insurances, and the Contractor’s Subcontractors shall be jointly insured under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 34.1 except for the Cargo Insurance During Transport, Automobile Liability Insurance, Workmen Compensation Policy and Contractor's Plant and Machinery (CPM ) Insurances. All insurer’s rights of subrogation against such jointly insured for losses or claims arising out of the performance of the Contract shall be waived under such policies. | The Employer shall be jointly named as additional insured under all insurance policies taken out by the Contractor pursuant to GCC Sub- Clause 34.1, except for the Third Party Liability, Automobile Liability Insurance, Workmen Compensation policy and Contractors Plant and Machinery (CPM) Insurances, and the Contractor’s Subcontractors shall be jointly named as additional insured under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 34.1 except for the Cargo Insurance During Transport, Automobile Liability Insurance, Workmen Compensation Policy Insurances, and Contractors Plant and Machinery (CPM) insurances. All insurer’s rights of subrogation against such jointly insureds for losses or claims arising out of the performance of the Contract shall be waived under such policies. | The Employer and subcontractors shall be additional insured under the EAR insurance policy, for its interests under the Contract, in all of the relevant insurances.