| Sl. No. | Clause Ref. No. | Existing provision | Amended as |
| --- | --- | --- | --- |
| Section-III, Vol-I: Bid Data Sheet |  |  |  |
|  | ITB 9.3(p) | Attachment 15: Option for Initial Advance (either Interest Bearing Initial Advance or No Initial Advance) and Information for E-payment, PF details and declaration regarding Micro/Small & Medium Enterprises Scanned copy of Sample Cheque (Cancelled) shall also be uploaded (refer para 15.4 below). In this Attachment, the Bidder is required to clearly mention whether the Bidder would opt for Interest bearing initial advance in addition to providing the other information as above. | Attachment 15: Information for E-payment, PF details and declaration regarding Micro/Small & Medium Enterprises Scanned copy of Sample Cheque (Cancelled) shall also be uploaded (refer para 15.4 below). |
| Section-IV, Vol-I: General Conditions of Contract |  |  |  |
|  | GCC 9.2.1 | The Contractor shall, within twenty-eight (28) days of the notification of contract award, provide a security in an amount equal to as follows: a. 110% (one hundred ten percent) of the amount of Advance for Supply of Goods; and b. 110% (one hundred ten percent) of the {amount of Advance} plus {amount of GST reimbursable on Advance as per the Proforma invoice} for Supply of Services. The above shall be calculated in accordance with the corresponding Appendix - 1 (Terms and Procedures of Payment) to the Contract Agreement, and in the same currency(ies) with initial validity of up to ninety (90) days beyond the date of Completion of the Facilities in accordance with GCC Sub-Clause 20.1. The same shall be extended by the Contractor time to time till ninety (90) days beyond the actual date of Completion of the Facilities, as may be required under the Contract. | The Contractor shall, within twenty-eight (28) days of the notification of contract award, provide a security in an amount equal to as follows: a. 100% (one hundred percent) of the amount of Advance for Supply of Goods; and b. 100% (one hundred percent) of the {amount of Advance} plus {amount of GST reimbursable on Advance as per the Proforma invoice} for Supply of Services. The above shall be calculated in accordance with the corresponding Appendix - 1 (Terms and Procedures of Payment) to the Contract Agreement, and in the same currency(ies) with initial validity of up to ninety (90) days beyond the date of Completion of the Facilities in accordance with GCC Sub-Clause 20.1. The same shall be extended by the Contractor time to time till ninety (90) days beyond the actual date of Completion of the Facilities, as may be required under the Contract. |
| Section-V, Vol-I: Special Conditions of Contract |  |  |  |
|  | GCC 36A.3 | In case of partial offloading under the Contract, in case, the contractor has opted for taking interest bearing advances, the contractor shall refund the outstanding advance against the offloaded portion and the same would be adjusted. In case the contractor requests that the outstanding advance against the offloaded portion cannot be refunded due to their financial constraints, the additional advance would be considered as special advance and the rate of recovery of advance shall be enhanced in the live portion of the Contract so as to adjust the amount as per contractual provisions before attempting for recovery through other tools as available. [In cases where Interest free advance is released with a time bound recovery, the same shall be adjusted as per the instalments/duration of recovery defined in the contract. (Applicable for cases where Interest Free Advance is extended to the Contractor)] | In case of partial offloading under the Contract, in case, interest free advances subject to time-based recovery are paid to the Contractor, the contractor shall refund the outstanding advance against the offloaded portion and the same would be adjusted. In case the contractor requests that the outstanding advance against the offloaded portion cannot be refunded due to their financial constraints, the additional advance would be considered as special advance and the rate of recovery of advance shall be enhanced in the live portion of the Contract so as to adjust the amount as per instalments/duration of recovery defined in the Contract before attempting for recovery through other tools as available. However, in such a case, the interest free advance for the offloaded portion would be deemed as interest bearing advance which shall be charged at one-year MCLR (One Year Tenor Rate p.a.) published by State Bank of India, prevailing as on the date of drawal of advance. In such case, interest shall be charged on the portion of advance remained unadjusted for the offloaded portion on the date of part termination of Contract or is not paid back by the Contractor. Further, the date from which the interest shall be charged shall be the first day from the date of first default notice issued for the offloaded portion under the contract and shall be compounded on quarterly basis till the date of part termination notice. In case the balance unadjusted advance is not paid back/recovered from the contractor on the date of part termination, the interest shall be compounded on quarterly basis till recovered/adjusted subsequently. |
| Section-VI, Vol-I: Sample Forms & Procedures |  |  |  |
|  | 4. Form of ‘Notification of Award of Contract’ | …………… 5.0 For release of advance payment (admissible as per the bidding documents) equal to ……..% of the Ex-works Price component of the Contract Price, you are, inter-alia, required to furnish a Bank Guarantee for [{110% (one hundred ten percent) of the amount of Advance}]. The validity of the Advance Bank Guarantee shall be up to and including ………….. Further, please note that furnishing of all the Contract Performance Securities under the ‘First Contract’ and ‘Second Contract’ shall be one of the conditions precedent to release of advance under this Contract. ……………………… | …………… 5.0 For release of advance payment (admissible as per the bidding documents) equal to ……..% of the Ex-works Price component of the Contract Price, you are, inter-alia, required to furnish a Bank Guarantee for [{100% (one hundred percent) of the amount of Advance}]. The validity of the Advance Bank Guarantee shall be up to and including ………….. Further, please note that furnishing of all the Contract Performance Securities under the ‘First Contract’ and ‘Second Contract’ shall be one of the conditions precedent to release of advance under this Contract. ……………………… |
|  | Para 1.1 A & B of Appendix-1 to Contract Agreement, Terms and Procedures of Payment | - Supply of Goods Portion A1. Interest Bearing Advance (Optional*): Ten percent (10%) of the Ex-works price component of Main Equipment/Materials (including Thyristor Valves but excluding all Spares) shall be paid as an interest bearing initial advance after signing the Contract Agreement and on submission of: - Proforma invoice(s), - Advance Bank Guarantee for 110% (one hundred ten percent) of the amount of Advance, in line with GCC Clause 9.2, - Performance Securities in line with GCC Clause 9.3 and - Detailed PERT Network/Bar chart and its approval by the Employer. Provided further that the Proforma Invoice(s) for advance payment along with all supporting documents is submitted by the Contractor to the Employer within 3 months from the date of Notification of Award. In case the Contractor does not submit the requisite documents including applicable Bank Guarantee(s)/Security(ies) within the aforesaid period, the advance shall not be payable. The Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. Note: * This payment is an optional payment. The Contractor has the option of taking the interest bearing initial advance or otherwise. Interest rate applicable on advance payment to the Contractor shall be at the rate equal to one year MCLR rate [One year Tenor rate p.a.] published by State Bank of India prevailing as on the date of drawal of advance. The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid. The interest will be charged considering proportionate adjustment of advance against progressive payment as per 1.1(B) below. The interest shall be calculated on the daily progressive balances outstanding as on the date of recovery/adjustment. It is the Employer’s understanding that as per extant provisions, GST is not payable on interest paid on the amount of Advance. The Contractor is, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account. Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest within 3 months from the end of the quarter in which adjustment of advance has been made for claiming refund from Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate. In case, the Contractor opts not to take interest bearing advance as above, it would be mandatory for him to submit the documents listed at Sl. No. (c), and (d) above within twenty-eight (28) days of issuance of NOA. (The above is to be incorporated in case the Contractor has opted for the interest bearing initial advance, as declared by it in its bid in the relevant Attachment to Bid Form). B. Interest Bearing Interim Advance (Optional**): (B.1) Fifteen percent (15%) of the Ex-works price component of Main Equipment/Materials (excluding Thyristor Valves and all Spares) of each item (as identified in the price schedule) shall be paid on submission of: (a) Approval of designs, drawings & guaranteed technical particulars as per Technical Specifications, Volume-II of the Bidding Documents. (b) Proforma Invoice (c) Advance Bank Guarantee for 110% (one hundred ten percent) of the amount of Advance; (B.2) Fifteen percent (15%)^^^ of the Ex-works price component of Main Equipment/Materials (excluding Thyristor Valves and all Spares) of each item (as identified in the price schedule) shall be paid on submission of: (a) Start of Factory System Test (FST) as per Technical Specifications, Volume-II of the Bidding Documents. (b) Proforma Invoice, (c) Advance Bank Guarantee for 110% (one hundred ten percent) of the amount of Advance; In case of advance on Ex-works supply portion, the Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. Interest rate applicable on advance payment to the Contractor shall be at the rate equal to one year MCLR rate [One year Tenor rate p.a.] published by State Bank of India prevailing as on the date of drawal of advance. The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid. The interest will be charged considering proportionate adjustment of advance against progressive payment as per 1.1(C1) below. The interest shall be calculated on the daily progressive balances outstanding as on the date of recovery/adjustment. It is the Employer’s understanding that as per extant provisions, GST is not payable on interest paid on the amount of Advance. The Contractor is, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account. Note: ** This payment is an optional payment. The Contractor has the option of taking the interest bearing initial advance or otherwise. Note: ^^^ After release of 2nd Installment, the rate of recovery of the advance shall be re-adjusted. (The above is to be incorporated in case the Contractor has opted for the interest bearing interim advance, as declared by it in its bid in the relevant Attachment to Bid Form) Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest within 3 months from the end of the quarter in which adjustment of advance has been made for claiming refund from Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate. | - Supply of Goods Portion A1. Interest Free Advance: Ten percent (10%) of the Ex-works price component of Main Equipment/Materials (including Thyristor Valves but excluding all Spares) shall be paid as an interest free initial advance subject to time-based recovery after signing the Contract Agreement and on submission of: (a) Proforma invoice(s), (b) Advance Bank Guarantee for 100% (one hundred percent) of the amount of Advance, in line with GCC Clause 9.2, (c) Performance Securities in line with GCC Clause 9.3 and (d) Detailed PERT Network/Bar chart and its approval by the Employer. Provided further that the Proforma Invoice(s) for advance payment along with all supporting documents is submitted by the Contractor to the Employer within 3 months from the date of Notification of Award. In case the Contractor does not submit the requisite documents including applicable Bank Guarantee(s)/Security(ies) within the aforesaid period, the advance shall not be payable. The Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. The initial advance will be proportionately adjusted against progressive payment as per 1.1 C below. Time based recovery of advance payment: The recovery of initial advance paid to the contractor shall be time based as mentioned below: - Recovery of not less than 30% advance amount at the end of 18 Months from the Effective Date of Contract - Recovery of not less than 70% cumulative advance amount at the end of 27 Months from the Effective Date of Contract - Recovery of complete advance amount at the end of 36 Months from the Effective Date of Contract In case certain portion of advance remains unadjusted beyond the specified time schedule as mentioned above or is not paid back by the Contractor, interest shall be charged on spill-over unadjusted advance portion beyond specified time schedule, as per following: - Interest rate shall be one-year MCLR (One Year Tenor Rate p.a.) published by State Bank of India prevailing as on the date of drawal of advance. - The date from which the interest shall be charged shall be the first day after the end date as per above time schedule on which certain portion of advance remains unadjusted or not paid back by the Contractor. - The said interest rate shall remain fixed and shall be applicable till the spill over unadjusted advance portion beyond specified time schedule is adjusted. - The interest shall be calculated on daily progressive unadjusted advance amount outstanding as on the date of recovery/adjustment. - The interest, as above, will be charged against progressive payments, due for release, as per 1.1 (C) below. However, subsequently if it is ascertained by the owner that the delay vis-à-vis contractual schedule is not attributable to the contractor, the interest charged on spill-over unadjusted advance portion shall be paid/adjusted along with succeeding bills of the contractor. Notwithstanding above, in case of termination of Contract due to Contractor’s default, the interest free advance would be deemed as interest bearing advance which shall be charged at one-year MCLR (One Year Tenor Rate p.a.) published by State Bank of India, prevailing as on the date of drawal of advance. In such case, interest shall be charged on the portion of advance remained unadjusted on the date of termination of Contract or is not paid back by the Contractor. Further, the date from which the interest shall be charged shall be the first day from the date of first default notice issued under the contract and shall be compounded on quarterly basis till the date of termination notice. In case the balance unadjusted advance is not paid back/recovered from the contractor on the date of termination, the interest shall be compounded on quarterly basis till recovered/adjusted subsequently. It is the Employer’s understanding that as per extant provisions, GST is not payable on interest, charged as above, as applicable. The Contractor is, however, advised to check the position from its own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account. Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest, charged as above, as applicable, within 3 months from the end of the quarter in which interest has been charged for claiming refund from the Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc. to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate. It would be mandatory for the Contractor to submit the documents listed at Sl. No. (c), and (d) above within twenty eight(28) days of issuance of NOA. B. Interest Free Interim Advance (Optional**): (B.1) Fifteen percent (15%) of the Ex-works price component of Main Equipment/Materials (excluding Thyristor Valves and all Spares) of each item (as identified in the price schedule) shall be paid as an interest-free interim advance subject to time-based recovery on submission of: (a) Approval of designs, drawings & guaranteed technical particulars as per Technical Specifications, Volume-II of the Bidding Documents. (b) Proforma Invoice (c) Submission of an unconditional & irrevocable Bank Guarantee in favour of the Employer for 100% (one hundred percent) of the amount of Interim Engineering Advance as per the proforma attached with Section-VI: Forms, Conditions of Contract, Volume-I of the Bidding Documents. (B.2) Fifteen percent (15%)^^^ of the Ex-works price component of Main Equipment/Materials (excluding Thyristor Valves and all Spares) of each item (as identified in the price schedule) shall be paid as an interest-free interim advance subject to time-based recovery on submission of: (a) Start of Factory System Test (FST) as per Technical Specifications, Volume-II of the Bidding Documents. (b) Proforma Invoice, (c) Submission of an unconditional & irrevocable Bank Guarantee in favour of the Employer for 100% (one hundred percent) of the amount of Interim Engineering Advance as per the proforma attached with Section-VI: Forms, Conditions of Contract, Volume-I of the Bidding Documents. The Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. The Interest Free Interim Advance will be proportionately adjusted against progressive payment as per 1.1 C below. Time based recovery of advance payment: The recovery of Engineering advance paid to the contractor shall be time based as mentioned below: - Recovery of not less than 30% advance amount at the end of 18 Month from the Effective Date of Contract - Recovery of not less than 70% cumulative advance amount at the end of 27 Month from the Effective Date of Contract - Recovery of complete advance amount at the end of 36 Month from the Effective Date of Contract In case certain portion of advance remains unadjusted beyond the specified time schedule as mentioned above or is not paid back by the Contractor, interest shall be charged on spill-over unadjusted advance portion beyond specified time schedule, as per following: - Interest rate shall be one-year MCLR (One Year Tenor Rate p.a.) published by State Bank of India prevailing as on the date of drawal of advance. - The date from which the interest shall be charged shall be the first day after the end date as per above time schedule on which certain portion of advance remains unadjusted or not paid back by the Contractor. - The said interest rate shall remain fixed and shall be applicable till the spill over unadjusted advance portion beyond specified time schedule is adjusted. - The interest shall be calculated on daily progressive unadjusted advance amount outstanding as on the date of recovery/adjustment. - The interest, as above, will be charged against progressive payments, due for release, as per 1.1 (C) below. However, subsequently if it is ascertained by the owner that the delay vis-à-vis contractual schedule is not attributable to the contractor, the interest charged on spill-over unadjusted advance portion shall be paid/adjusted along with succeeding bills of the contractor. Notwithstanding above, in case of termination of Contract due to Contractor’s default, the interest free advance would be deemed as interest bearing advance which shall be charged at one-year MCLR (One Year Tenor Rate p.a.) published by State Bank of India, prevailing as on the date of drawal of advance. In such case, interest shall be charged on the portion of advance remained unadjusted on the date of termination of Contract or is not paid back by the Contractor. Further, the date from which the interest shall be charged shall be the first day from the date of first default notice issued under the contract and shall be compounded on quarterly basis till the date of termination notice. In case the balance unadjusted advance is not paid back/recovered from the contractor on the date of termination, the interest shall be compounded on quarterly basis till recovered/adjusted subsequently. It is the Employer’s understanding that as per extant provisions, GST is not payable on interest, charged as above, as applicable. The Contractor is, however, advised to check the position from its own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account. Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest, charged as above, as applicable, within 3 months from the end of the quarter in which interest has been charged for claiming refund from the Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc. to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate. It would be mandatory for the Contractor to fulfill the conditions mentioned at Sl. No. (a), (b) and (c) above as per terms & conditions of Contract and agreed work schedule. |
|  | Para 1.1 C of Appendix-1 to Contract Agreement, Terms and Procedures of Payment | C Progressive Payment Payment of the Ex-works price of Main Equipment/ materials (excluding Thyristor Valves and all Spares) for each consignment shall be made progressively on certification of the Employer and on the basis of work performed using the following guidelines: C.1 Fifteen percent (15%)^# of the Ex-Works price component of Main Equipment/Materials (excluding Thyristor Valves and all Spares) shall be paid progressively after dispatch of the Equipment/Materials and on submission of documents indicated hereinunder: …………………………………… ^ (i) In case, the Contractor opts not to take interest bearing advances (initial and interim) or has opted to take interest bearing advances (initial and interim) but the advance payment(s) has become inadmissible for the reason specified in 1.1A and 1.1B above, then this payment shall be 55% instead of 15%. (ii) In case, the Contractor opts not to take interest bearing initial advance or has opted to take interest bearing initial advance but the advance payment has become inadmissible for the reason specified in 1.1A above and Contractor has taken interest bearing interim advance, then this payment shall be 25% instead of 15%. (iii) In case, the Contractor has taken interest bearing initial advance and opts not to take interest bearing interim advance or has opted to take interest bearing interim advance but the interim advance payment has become inadmissible for the reason specified in 1.1B above, then this payment shall be 45% instead of 15%. # In case of Thyristor Valves, this payment shall be 40% instead of 15%. In case, the Contractor opts not to take interest bearing initial advance or has opted to take interest bearing initial advance but the advance payment has become inadmissible for the reason specified in 1.1A above, then this payment shall be 50% instead of 40%. …………………………………. | C Progressive Payment Payment of the Ex-works price of Main Equipment/ materials (excluding Thyristor Valves and all Spares) for each consignment shall be made progressively on certification of the Employer and on the basis of work performed using the following guidelines: C.1 Fifteen percent (15%)^# of the Ex-Works price component of Main Equipment/Materials (excluding Thyristor Valves and all Spares) shall be paid progressively after dispatch of the Equipment/Materials and on submission of documents indicated hereinunder: …………………………………… ^ (i) In case, the Contractor opts not to take interest free advances (initial and interim) or has opted to take interest free advances (initial and interim) but the advance payment(s) has become inadmissible for the reason specified in 1.1A and 1.1B above, then this payment shall be 55% instead of 15%. (ii) In case, the Contractor opts not to take interest free initial advance or has opted to take interest free initial advance but the advance payment has become inadmissible for the reason specified in 1.1A above and Contractor has taken interest free interim advance, then this payment shall be 25% instead of 15%. (iii) In case, the Contractor has taken interest free initial advance and opts not to take interest free interim advance or has opted to take interest free interim advance but the interim advance payment has become inadmissible for the reason specified in 1.1B above, then this payment shall be 45% instead of 15%. # In case of Thyristor Valves, this payment shall be 40% instead of 15%. In case, the Contractor opts not to take interest free initial advance or has opted to take interest free initial advance but the advance payment has become inadmissible for the reason specified in 1.1A above, then this payment shall be 50% instead of 40%. …………………………………. |
|  | Para 1.5A of Appendix-1 to Contract Agreement, Terms and Procedures of Payment | 1.5 Supply of Services Portion: Price Component for Installation (including Civil Works) A. Interest Bearing Advance (Optional^^) Ten percent (10%): A.1 1st Installment: 5% (five percent) of the total Installation price component shall be paid as an interest bearing advance on submission of (a) Proforma invoice, (b) Establishment of Contractor’s site offices for preparatory to mobilisation for Installation establishment, (c) Advance Bank Guarantee for [{110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice(s)}] in line with GCC Clause 9.2 and (d) Performance Securities in line with GCC Clause 9.3. A.2 2nd Installment: 5% (five percent) of the total Installation price component shall be paid as an interest bearing advance on submission of (a) Proforma invoice, (b) On start of equipment erection*, (c) Advance Bank Guarantee for [{110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice(s)}] in line with GCC Clause 9.2 and (d) A declaration by the contractor stating that 1st Installment (5%) of advance has been utilized against the mobilization works for the subject contract. * After the release of 2nd Installment, the rate of recovery of the advance shall be re-adjusted. Ten percent (10%) of the total Installation price component (including Civil Works) shall be paid on Establishment of Contractor’s site offices and on submission of (a) Proforma invoice(s), (b) Advance Bank Guarantee for {110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice} in line with GCC Clause 9.2 and (c) Performance Securities in line with GCC Clause 9.3. Note: ^^ This payment is an optional payment. The Contractor has the option of taking the interest bearing advance or otherwise. Provided further that the Proforma Invoice(s) for advance payment along with all supporting documents is submitted by the Contractor to the Employer within 3 months from the date of fulfillment of the requisite activities, as per the L2 network. In case the Contractor does not submit the requisite documents including applicable Bank Guarantee(s)/ Security(ies) within the aforesaid period, the advance shall not be payable. The Contractor, shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. Note: ^^: This payment is an optional payment. The Contractor has the option of taking the interest bearing advance or otherwise. Interest rate applicable on advance payment to the Contractor shall at the rate equal to one year MCLR rate [One year Tenor rate p.a.] published by State Bank of India prevailing as on the date of drawal of advance. The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid. The interest will be charged considering proportionate adjustment of advance against progressive payment for the work done as per 1.4(B) below. The interest shall be calculated on the daily progressive balances outstanding as on the date of recovery/adjustment. It is the Employer’s understanding that as per extant provisions, GST is not payable on Interest paid on the amount of Advance. The Contractor may, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account. (The above is to be incorporated in case the Contractor has opted for the interest bearing initial advance, as declared by it in its bid in the relevant Attachment to Bid Form). Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest within 3 months from the end of the quarter in which adjustment of advance has been made for claiming refund from Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate. In case, the Contractor opts not to take interest bearing advance as above, it would be mandatory for him to submit the document listed at Sl. No. (d) above within twenty eight (28) days of issuance of NOA. | 1.5 Supply of Services Portion: Price Component for Installation (including Civil Works) A. Interest Free Advance Ten percent (10%): A.1 1st Installment: 5% (five percent) of the total Installation price component shall be paid as an interest free advance subject to time based recovery on submission of (a) Proforma invoice, (b) Establishment of Contractor’s site offices for preparatory to mobilisation for Installation establishment, (c) Advance Bank Guarantee for [{100% (one hundred percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice}] in line with GCC Clause 9.2 and (d) Performance Securities in line with GCC Clause 9.3. A.2 2nd Installment^^^: 5% (five percent) of the total Installation price component shall be paid as an interest free advance subject to time based recovery on submission of (a) Proforma invoice(s), (b) On start of equipment erection, (c) Advance Bank Guarantee for [{100% (one hundred percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice}] in line with GCC Clause 9.2, (d) A declaration by the Contractor stating that 1st Installation (5%) of advance has been utilized against the mobilization works for the subject contract. ^^^After the release of 2nd Installment, the rate of recovery of the advance shall be re-adjusted. Provided further that the Proforma Invoice(s) for advance payment along with all supporting documents is submitted by the Contractor to the Employer within 3 months from the date of fulfillment of the requisite activities, as per the L2 network. In case the Contractor does not submit the requisite documents including applicable Bank Guarantee(s)/ Security(ies) within the aforesaid period, the advance shall not be payable. The Contractor, shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. The advance will be proportionately adjusted against progressive payment as per 1.5 (B) below. Time based recovery of advance payment: The recovery of initial advance paid to the contractor shall be time based as mentioned below: - Recovery of not less than 30% advance amount at the end of 18 Month from the Effective Date of Contract - Recovery of not less than 70% cumulative advance amount at the end of 27 Month from the Effective Date of Contract - Recovery of complete advance amount at the end of 36 Month from the Effective Date of Contract In case certain portion of advance remains unadjusted beyond the specified time schedule as mentioned above or is not paid back by the Contractor, interest shall be charged on spill-over unadjusted advance portion beyond specified time schedule, as per following: - Interest rate shall be one-year MCLR (One Year Tenor Rate p.a.) published by State Bank of India prevailing as on the date of drawal of advance. - The date from which the interest shall be charged shall be the first day after the end date as per above time schedule on which certain portion of advance remains unadjusted or not paid back by the Contractor. - The said interest rate shall remain fixed and shall be applicable till the spill over unadjusted advance portion beyond specified time schedule is adjusted. - The interest shall be calculated on daily progressive unadjusted advance amount outstanding as on the date of recovery/adjustment. - The interest, as above, will be charged against progressive payments, due for release, as per 1.5 (B) below. However, subsequently if it is ascertained by the owner that the delay vis-à-vis contractual schedule is not attributable to the contractor, the interest charged on spill-over unadjusted advance portion shall be paid/adjusted along with succeeding bills of the contractor. Notwithstanding above, in case of termination of Contract due to Contractor’s default, the interest free advance would be deemed as interest bearing advance which shall be charged at one-year MCLR (One Year Tenor Rate p.a.) published by State Bank of India, prevailing as on the date of drawal of advance. In such case, interest shall be charged on the portion of advance remained unadjusted on the date of termination of Contract or is not paid back by the Contractor. Further, the date from which the interest shall be charged shall be the first day from the date of first default notice issued under the contract and shall be compounded on quarterly basis till the date of termination notice. In case the balance unadjusted advance is not paid back/recovered from the contractor on the date of termination, the interest shall be compounded on quarterly basis till recovered/adjusted subsequently. It is the Employer’s understanding that as per extant provisions, GST is not payable on Interest paid on the amount of Advance. The Contractor is, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account Further, the Contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest, charged as above, as applicable, within 3 months from the end of the quarter in which interest has been charged for claiming refund from the Employer. No claim for refund will be entertained after end of the aforesaid period of 3 months. Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc. to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate. It would be mandatory for the Contractor to submit the document listed at Sl. No. (d) above within twenty-eight (28) days of issuance of NOA. |
|  | Para 1.5B of Appendix-1 to Contract Agreement, Terms and Procedures of Payment | B Progressive Payment: Eighty percent (80%)^^ of the total Installation price component (including Civil Works) shall be paid on completion the each of the items of Erection activity and on successful completion of quality check point involved in Installation, submission of the details of items, components, raw materials, services etc. procured/availed from MSEs, if any, for the preceding 6 months, in respect of all the contracts in the respective executing Region of POWERGRID as per format enclosed at Section VI, Forms, Volume-I of the bidding documents and certification by Employer’s representative and on submission of GST invoice. ^^ This payment shall be 90% instead of 80% in case, the Contractor opts not to take interest bearing initial advance or has opted to take interest bearing initial advance but the advance payment has become inadmissible for the reason specified in 1.4 (A) above. Further, one of the conditions for release of first progressive payment / subsequent payment shall be submission of ‘Safety Plan’ alongwith all requisite documents in line with GCC clause on Safety Precaution and proforma provided in this Section – Sample Forms and Procedure and approval of the same by the Engineer In-Charge. …………………………….. | B Progressive Payment: Eighty percent (80%)^^^^ of the total Installation price component (including Civil Works) shall be paid on completion the each of the items of Erection activity and on successful completion of quality check point involved in Installation, submission of the details of items, components, raw materials, services etc. procured/availed from MSEs, if any, for the preceding 6 months, in respect of all the contracts in the respective executing Region of POWERGRID as per format enclosed at Section VI, Forms, Volume-I of the bidding documents and certification by Employer’s representative and on submission of GST invoice. ^^^^ This payment shall be 85% instead of 80% in the following cases: - the 1st Installment interest free initial advance has become inadmissible for the reason specified in 1.5(A) above, and 2nd Installment interest free initial advance has been paid to the Contractor. OR - the 2nd Installment interest free initial advance has become inadmissible for the reason specified in 1.5(A) above, and 1st Installment interest free initial advance has been paid to the Contractor. ^^^^This payment shall be 90% instead of 870% in case, both the installments of interest free initial advance has become inadmissible for the reason specified in 1.4(A) above. Further, one of the conditions for release of first progressive payment / subsequent payment shall be submission of ‘Safety Plan’ alongwith all requisite documents in line with GCC clause on Safety Precaution and proforma provided in this Section – Sample Forms and Procedure and approval of the same by the Engineer In-Charge. …………………………….. |
|  | 7. Bank Guarantee Form for Advance Payment | ………………………… Whereas, in accordance with the terms of the said Contract, the Employer has agreed to pay or cause to be paid to the Contractor an interest bearing Advance Payment against furnishing of an irrevocable bank guarantee for an amount of ………………………..(Amount in figures and words) ……………which is equal to [{110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice, if applicable}]. …………………………. Provided always that the Bank's obligation shall be limited to the amount of this Bank guarantee or an amount equal to the outstanding balance of the Advance Payment and the accrued interest on the Advance Payment, taking into account such amounts, which have been repaid by the Contractor from time to time in accordance with the terms of payment of the said Contract, as certified by you. This Guarantee shall remain in full force from the date upon which the said Advance Payment is received by the Contractor up to ninety (90) days beyond the date on which the entire Advance Payment along with the accrued interest if any due thereon has been fully adjusted in terms of the Contract i.e., up to ninety (90) days beyond the date of Completion of the Facilities under the Contract. This Guarantee may be extended from time to time, as may be desired by M/s. ……………………….. on whose behalf this Guarantee has been issued. …………………………………. | ………………………… Whereas, in accordance with the terms of the said Contract, the Employer has agreed to pay or cause to be paid to the Contractor interest free Advance Payment(s) against furnishing of an irrevocable bank guarantee for amount of ………………………..(Amount in figures and words) …………. which is equal to [{100% (one hundred percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice, if applicable}]. …………………………. Provided always that the Bank's obligation shall be limited to the amount of this Bank guarantee or an amount equal to the outstanding balance of the Advance Payment and the accrued interest on the Advance Payment, taking into account such amounts, which have been repaid by the Contractor from time to time in accordance with the terms of payment of the said Contract, as certified by you. This Guarantee shall remain in full force from the date upon which the said Advance Payment(s) are received by the Contractor up to ninety (90) days beyond the date on which the entire Advance Payment(s) along with the accrued interest if any due thereon has been fully adjusted in terms of the Contract i.e., up to ninety (90) days beyond the date of Completion of the Facilities under the Contract. This Guarantee may be extended from time to time, as may be desired by M/s. ……………………….. on whose behalf this Guarantee has been issued. …………………………………. |
| Volume-III: First Envelope Bid Form & Attachments |  |  |  |
|  | 2.0 (p) of 1st Env. Bid Form | (p) Attachment 15 :; Option for Initial Advance (either Interest Bearing Initial Advance or No Initial Advance) and Information for E-payment, PF details and declaration regarding Micro/Small & Medium Enterprises. | (p) Attachment 15 :; Information for E-payment, PF details and declaration regarding Micro/Small & Medium Enterprises. |
|  | Attachment-15 of First Envelope Bid Form | …………………. I; We have read the provisions in the Bidding Documents regarding furnishing the option for advance payment. Accordingly, as per ITB Clause 9.3 as provided in Section BDS, Section III, Vol.-I of the Bidding Documents, we hereby confirm to opt the following:. A1 Interest Bearing Initial Advance:. (a) Supply Portion:. (b) Services Portion:. A2 B. Interest Bearing Interim Advance for Supply Portion :. II; We are furnishing the following details of Statutory Registration Numbers and details of Bank for electronic payment.. ……………………… | …………………. I; We are furnishing the following details of Statutory Registration Numbers and details of Bank for electronic payment.. ……………………… |
|  | ITB 9.3(ff), Section-II: ITB, Vol.-I of the Bidding Documents | - | Add new clause ITB 9.3(ff) in Section: BDS: (ff) Attachment-31: Declaration by the bidder for Acknowledgement and Acceptance of ‘Supplier Code of Conduct’ The ‘Supplier Code of Conduct’. is attached as Appendix-III to the Special Conditions of Contract. |
|  | ITB 21.1, Section-III: BDS, Vol.-I of the Bidding Documents | Replace the existing provision with the following: During bid evaluation, the Employer may, at its discretion, ask the Bidder for a clarification of its bid. In case of erroneous/non submission of following documents related to/identified in ITB Sub-Clause 9.3 (b), (o), (s) , (t), (u) , (v), (w), (x), (z), (aa), (bb), (cc), (dd) and (ee) or Deed of Joint Undertaking pursuant to ITB Sub-Clause 9.3 (c) & (e) or the complete annual reports together with Audited statement of accounts pursuant to ITB Sub-Clause 9.3 (c), Online Payment Acknowledgement towards the cost of Bidding Documents pursuant to ITB 5.4, documentary evidence with regard to registration with designated Authority of GoI under the Public Procurement Policy for MSEs pursuant ITB 5.5 or 13.1, documentary evidence with regard to MSE owned by SC/ST entrepreneurs or women in line with Public Procurement Policy for MSEs pursuant to ITB 9.3(p), Confirmation regarding furnishing Declaration for non-participation if pre-selected for associating with POWERGRID for the purpose of tariff bidding, required to be submitted by the Bidder as per the provisions of the Bidding Documents, the Employer may give the Bidder not more than 7 working days notice to rectify/furnish such documents, failing which the bid shall be rejected. The request for clarification and the response shall be in writing, and no change in the price or substance of the bid shall be sought, offered or permitted. In case of non-submission of documents related to/identified in Attachment-11 {‘Information regarding ex-employee(s) of Employer in Bidder’s firm’}, the Employer may give the Bidder not more than 7 working days’ notice to rectify/furnish such documents, failing which Employer reserves the right to reject such bids. Employer shall be sole judge in this regard. | Replace the existing provision with the following: During bid evaluation, the Employer may, at its discretion, ask the Bidder for a clarification of its bid. In case of erroneous/non submission of following documents related to/identified in ITB Sub-Clause 9.3 (b), (o), (s) , (t), (u) , (v), (w), (x), (z), (aa), (bb), (cc), (dd) (ee) and (ff) or Deed of Joint Undertaking pursuant to ITB Sub-Clause 9.3 (c) & (e) or the complete annual reports together with Audited statement of accounts pursuant to ITB Sub-Clause 9.3 (c), Online Payment Acknowledgement towards the cost of Bidding Documents pursuant to ITB 5.4, documentary evidence with regard to registration with designated Authority of GoI under the Public Procurement Policy for MSEs pursuant ITB 5.5 or 13.1, documentary evidence with regard to MSE owned by SC/ST entrepreneurs or women in line with Public Procurement Policy for MSEs pursuant to ITB 9.3(p), Confirmation regarding furnishing Declaration for non-participation if pre-selected for associating with POWERGRID for the purpose of tariff bidding, required to be submitted by the Bidder as per the provisions of the Bidding Documents, the Employer may give the Bidder not more than 7 working days notice to rectify/furnish such documents, failing which the bid shall be rejected. The request for clarification and the response shall be in writing, and no change in the price or substance of the bid shall be sought, offered or permitted. In case of non-submission of documents related to/identified in Attachment-11 {‘Information regarding ex-employee(s) of Employer in Bidder’s firm’}, the Employer may give the Bidder not more than 7 working days’ notice to rectify/furnish such documents, failing which Employer reserves the right to reject such bids. Employer shall be sole judge in this regard. |
|  | Cl. 2.0 of Bid Form (1st Envelope), Vol-III of the Bidding Documents | Attachments to the Bid Form (First Envelope): ……………. ……………. ……………. | Attachments to the Bid Form (First Envelope): ……………. ……………. (ff) Attachment-31: Declaration by the bidder for Acknowledgement and Acceptance of Supplier Code of Conduct |
|  | ‘First Envelope and Bid Forms’ excel sheet | In view of the above Amendment, the ‘’First_Envelope_and_Bid_Forms_rev03’ excel stand revised as ‘First_Envelope_and_Bid_Forms_rev04’ and is enclosed herewith. Note- Bidders are requested to consider the revised excel ‘First Envelope and Bid Forms_rev04’ for bid preparation/submission. It may be noted that while submitting the bid, Bidders are required to change the excel file name from ‘First Envelope and Bid Forms_rev04’ to ‘First Envelope and Bid Forms’. As per the provisions of the portal, it is mandatory to upload the excel file titled ‘First Envelope and Bid Forms’ (Bidders may refer user manuals at the portal https://etender.powergrid.in regarding submission of bid). |  |

*************