## Table 1 (hidden)
Tender: | Refurbishment of HVDC Control, Protection, SCADA, Valve Hall Equipment and Valve Cooling System for 2x500 MW Chandrapur HVDC Back to Back (BTB) Station under Add-Cap
Bidder: | Hitachi Energy India Limited
Title: | Set -1 of Commercial Deviations / Clarifications
Sl. No. | Bidding Document | Clause Reference No. | Clause Header | Deviation / Clarification | Provisions as per the bidding document | Detailed description of Deviations / Clarifications the bidder | Reason for Change
1 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section IV, GCC C 4.1, Section-IV, Vol-I | Definitions | Clarification | 4. Time for Commencement and Completion 4.1 The Contractor shall commence work on the Facilities from the Effective Date of Contract and without prejudice to GCC Sub-Clause 21.2 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified in the corresponding Appendix – 4 (Time Schedule) to the Contract Agreement. ................................ | We request to add the definition of "Commencement Date" "Commencement Date" means the date of fulfilment of all conditions stated below: (a) This Contract Agreement has been duly executed for and on behalf of the Employer and the Contractor. (b) The Employer has paid the Contractor the advance payment within 15 days of receipt of eqvt. advance bank guarantee (ABG) C contract performance bank guarantee (CPBG) from contractor. The Contractor shall submit the ABG C CPBG within 15 days from date of of NoA/LoA. Sub Clause 4.1 : The Contractor shall commence work on the Facilities from the Commencement Date of Contract and without prejudice to GCC Sub-Clause 21.2 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified in the corresponding Appendix – 4 (Time Schedule) to the Contract Agreement Time for completion shall be measured from Commencement Date.
2 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section IV, GCC 3.2 | Scope of Facilities | Clarification | The Contractor shall, unless specifically excluded in the Contract, perform all such work and/or supply all such items and materials not specifically mentioned in the Contract but that can be reasonably inferred from the Contract as being required for attaining Completion of the Facilities as if such work and/or items and materials were expressly mentioned in the Contract. | Please clarify if below modification to this Sub-clause is acceptable; 'The Contractor shall, unless specifically excluded in the Contract, perform all such work and/or supply all such items and materials not specifically as mentioned in the Contract but that can be reasonably inferred from the Contract in accordance with the technical specifications as being required for attaining Completion of the Facilities as if such work and/or items and materials were expressly mentioned in the Contract.
3 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section IV, SCC 5, GCC 3.3 | Scope of Facilities | Deviation | If so desired by the Employer, the Contractor shall submit the specifications, price and the terms and conditions relating to the supply thereof for such spares identified by the Employer with validity period of 6 months within 30 days of receipt of request from Employer for its consideration and placement of order. | Request to change the clause as below: If so desired by the Employer, the Contractor shall submit the specifications, price and the terms and conditions relating to the supply thereof for such spares identified by the Employer within the mutually agreed validity period of 6 months within 30 days of receipt of request from Employer for its consideration and placement of order.
4 | Section - V SPECIAL CONDITIONS OF CONTRACT (SCC) | Section V SCC 5, GCC 3.3 | Scope of Facilities | Deviation | The supply of Mandatory Spare Parts, if any, shall be included in the Contract. Beside the aforesaid Mandatory Spares parts, the Contractor shall ensure the availability functionally equivalent spare parts required for the operation and maintenance of the Facilities to the Employer for a minimum period of 15 years from Completion of the Facilities. | Request to change the clause as below: 'The supply of Mandatory Spare Parts, if any, shall be included in the Contract. Beside the aforesaid Mandatory Spares parts, the Contractor shall ensure the availability of functionally equivalent spare parts required for the operation and maintenance of the Facilities to the Employer for a minimum period of 15 years 10 years from Completion of the Facilities.
5 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section IV, SCC 6, GCC 3.4 | Scope of Facilities | Deviation | The Contractor shall guarantee that in the event of termination of production of spare parts by the Contractor or his Sub-Contractor: (i) The Contractor shall send advance notification to the Employer of the pending termination, with 2 (two) years time to permit the Employer to procure needed requirements, and (ii) Following such termination, the Contractor shall furnish at no cost to the Employer the relevant information/ documents and specification of the spare parts from third party, information/documents and specifications of the spare parts shall be furnished by the Contractor to the extent that such documents are available to the Contractor. | Kindly consider the time of advance notification of 6 months as the time period of 2 years may not be possible for advance notification especially under current technological trend.
6 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section IV, GCC 3.5 | Scope of Facilities | Deviation | In case the Contractor fails to supply the spares parts in accordance with the terms stipulated above, the Employer shall sanction the Contractor declaring them ineligible for a stated period of time for future projects. | Request for deletion of the clause.

## Clarification No-V
Clarification No-V dated 08.01.2025 to the bidding documents of Refurbishment of HVDC Control, Protection, SCADA, Valve Hall Equipment and Valve Cooling System for 2x500 MW Chandrapur HVDC Back to Back (BTB) Station under Add-Cap; Specification Number: CC/NT/W-HVDC/DOM/A00/24/12849
Sl. No. | Bidding Document | Clause Reference No. | Clause Header | Provisions as per the bidding document | Detailed description of Deviations / Clarifications the bidder | Employer's Response
1 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section - VI Forms and Proceedures | Terms and procedures of payment (Appendix-1) | 1.1 D. Final Payment Balance 30% (Thirty percent) of the Ex-works price component of Main Equipment/Materials (including Thyristor Valves but excluding all Spares) shall be paid on: a) 10% (Ten Percent) on Proof of submission of required number of reproducible, O&M Manuals, approved drawings, data sheets, test report, pamphlets and manuals of mandatory spares, maintenance & testing equipment. b) 20% (Twenty Percent) on successful completion of erection, testing and commissioning and issuance of Taking Over Certificate. c) However, in case of delay in testing and commissioning & issuance of taking over certificate by Employer beyond six (6) months from the date of receipt of equipment at site, the last 20% of CIF/Ex-Works price of respective equipment shall be paid after issuance of a certificate by POWERGRID’s representative that the equipment have been received in good conditions and on submission of a bank guarantee of equivalent amount, which shall be kept valid initially for a period of twelve (12) months or until three (3) months after the expected date of commissioning (in case it is possible to anticipate the same), whichever is earlier, provided all other conditions as per para a), b) & c) above are complied with by the Contractor. If the commissioning does not take place within the validity period of BG, the validity of BG shall be extended from time to time. The bank guarantee shall, however, be released within one month of successful commissioning of the respective equipment by the Employer. | Terms of Payment: Looking into the long gestation period of the project, 30% Final retention payment against supply items are causing substantial negative Cash flow for a prolonged duration during the project execution. We hence request you to kindly amend the retention amount to 10% instead of 30%. In this regard you may refer our proposed payment terms as mentioned below: (f) Final Payment - 10% (Twenty Percent) on successful completion of erection, testing and commissioning and issuance of Taking Over Certificate | refer Amendment No-V | Commencement date start after advance payment by the employer
3 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section - VI Forms and Proceedures | Terms and procedures of payment (Appendix-1) | C Progressive Payment Payment of the Ex-works price of Main Equipment/ materials (excluding Thyristor Valves and all Spares) for each consignment shall be made progressively on certification of the Employer and on the basis of work performed using the following guidelines: C.1 Fifteen percent (15%)^# of the Ex-Works price component of Main Equipment/Materials (excluding Thyristor Valves and all Spares) shall be paid progressively after dispatch of the Equipment/Materials and on submission of documents indicated hereinunder: ..................................... C.2 Fifteen percent (15%)## of the Ex-works price of Main Equipment/Materials (excluding Thyristor Valves and all Spares) shall be paid on receipt and storage at site and on physical verification and furnishing of necessary certificate by Employer’s representative. .................................... | (d) Thirty Five percent (35%) of the Ex-Works price component shall be paid progressively after dispatch of the Equipment/Materials and on submission of documents indicated hereinunder: (a) Evidence of dispatch. (e) Fifteen percent (15%) shall be paid on receipt and storage at site and on physical verification and furnishing of necessary certificate by Employer’s representative. For Thyristor Valves: (a) 10% interest Free Advance. (b) 60% against Dispatch Documents. (‘c) 20% against receipt of Materials at site. (c) 10% against Taking Over Certificate. | refer Amendment No-V | termination of equiupment advance information to employer 2 years to 6 months
4 | Section - IV GENERAL CONDITIONS OF CONTRACT (GCC) | Section - VI Forms and Proceedures | Terms and procedures of payment (Appendix-1) | 1.5 Supply of Services Portion: Price Component for Installation (including Civil Works) A. Interest Bearing Advance (Optional) Ten percent (10%): A.1 1st Installment: 5% (five percent) of the total Installation price component shall be paid as an interest bearing advance on submission of (a) Proforma invoice, (b) Establishment of Contractor’s site offices for preparatory to mobilisation for Installation establishment, (c) Advance Bank Guarantee for [{110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice(s)}] in line with GCC Clause 9.2 and (d) Performance Securities in line with GCC Clause 9.3. ........................... B Progressive Payment Eighty percent (80%)^^ of the total Installation price component (including Civil Works) shall be paid on completion the each of the items of Erection activity and on successful completion of quality check point involved in Installation, submission of the details of items, components, raw materials, services etc. procured/availed from MSEs, if any, for the preceding 6 months, in respect of all the contracts in the respective executing Region of POWERGRID as per format enclosed at Section VI, Forms, Volume-I of the bidding documents and certification by Employer’s representative and on submission of GST invoice. .............................. C. Final Payment Balance 10% (ten percent) payment shall be made as follow: Balance 10% (ten percent) of the Installation price component (including Civil Works) shall be paid on commissioning and issuance of Taking Over Certificate. | For SERVICE Portion: (a) 10% against Mobilization. (b) 80% pro rata basis. (‘c) 10% after Handing Over. | refer Amendment No-IV
5 | S. No. (52) of SCC: | Section-V SCC | liquidated damages to the Employer | Replace the Sub- Clause GCC 23.3(b) in SCC: pay liquidated damages to the Employer | B) Refer S. No. (52) of SCC: Changes in LD Parameter: Overall capping on the cumulative LD for Availability, Reliability, Station Power Rating, Transient Disturbances and Outage Schedule is requested to be reduced to 8% of Contract Price instead of 15% as mentioned in Tender Documents. | Requirement of the TS shall be fulfilled
6 | Chapter-11-Vol-II | Vol-IIPart-1: | Availability Requirement | C) Clause No. 11.8 – Changes ‘Availability Requirement’ mentioned in Chapter-11-Vol-IIPart-1: | C) Clause No. 11.8 – Changes ‘Availability Requirement’ mentioned in Chapter-11-Vol-IIPart-1: The Guaranteed Minimum Energy Availability Requirement (EA) of each HVDC block shall not be less than 97% instead of 99.8 % & In case average annual energy availability as described in Para (c) above, is found to be below 95% instead of 98% the system (under present scope) shall be rejected by employer. | TS requirement shall prevail

## Table 3 (hidden)
Tender: | Refurbishment of HVDC Control, Protection, SCADA, Valve Hall Equipment and Valve Cooling System for 2x500 MW Chandrapur HVDC Back to Back (BTB) Station under Add-Cap
Title: | Set -1 of Commercial Deviations / Clarifications
Sl. No. | Bidding Document | Clause Reference No. | Clause Header | Deviation / Clarification | Provisions as per the bidding document | Detailed description of Deviations / Clarifications the bidder | Reason for Change
66 | SECTION - VI SAMPLE FORMS AND PROCEDURES (FORMS) | Section VI Sample Forms and Procedures, APPENDIX-3: INSURANCE REǪUIREMENTS (d).II | Workmen Compensation Policy: | Clarification | The policy may either be project specific covering all men of the Contractor and its Subcontractors. The policy shall be kept valid till the date of Operational Acceptance of the project. Alternatively, if the Contractor has an existing ‘Workmen Compensation Policy’ for all its employees including that of the Subcontractor(s), the Contractor must include the interest of the Employer for this specific Project in its existing ‘Workmen Compensation Policy’ | The policy may either be project specific covering all men of the Contractor and its Subcontractors. The policy shall be kept valid till the date of Operational Acceptance TOC of the project. Alternatively, if the Contractor has an existing ‘Workmen Compensation Policy’ for all its employees including that of the Subcontractor(s), the Contractor must include the interest of the Employer for this specific Project in its existing ‘Workmen
Compensation Policy’
67 | SECTION - VI SAMPLE FORMS AND PROCEDURES (FORMS) | Section VI Sample Forms and Procedures, APPENDIX-3: INSURANCE REǪUIREMENTS (d).III | Workmen Compensation Policy: | Clarification | Without relieving the Contractor of its obligations and responsibilities under this Contract, before commencing work the Contractor shall insure against liability for death of or injury to persons employed by the Contractor including liability by statute and at common law. The insurance cover shall be maintained until all work including remedial work is completed including the Defect Liability Period. The insurance shall be extended to indemnify the Principal for the Principal’s statutory liability to persons employed by the Contractor. | Without relieving the Contractor of its obligations and responsibilities under this Contract, before commencing work the Contractor shall insure against liability for death of or injury to persons employed by the Contractor including liability by statute and at common law. The insurance cover shall be maintained until all work including remedial work is completed including the Defect Liability Period. The insurance shall be extended to indemnify the Principal for the Principal's statutory liability to persons employed by the Contractor. The Contractor shall also ensure that each of its Subcontractors shall effect and maintain insurance on the same basis as the 'Workmen Compensation Policy' effected by the Contractor. | Contractor will maintain WC policy covering its employees and workers as per local ACT.
The Contractor shall also ensure that each of its Subcontractors shall effect and maintain insurance on the same basis as the 'Workmen Compensation Policy' effected by the Contractor.
68 | SECTION - VI SAMPLE FORMS AND PROCEDURES (FORMS) | Section VI Sample Forms and Procedures, APPENDIX-3: INSURANCE REǪUIREMENTS (e) | Contractor’s Plant and Machinery (CPM) Insurance | Clarification | Contractor’s Plant and Machinery (CPM) Insurance The Employer (including without limitation any consultant, servant, agent or employee of the Employer) shall not in any circumstances be liable to the Contractor for any loss of or damage to any of the Contractor’s Equipment or for any losses, liabilities, costs, claims, actions or demands which the Contractor may incur or which may be made against it as a result of or in connection with any such loss or damage. | Contractor’s Plant and Machinery (CPM) Insurance The Employer (including without limitation any consultant, servant, agent or employee of the Employer) shall not in any circumstances be liable to the Contractor for any loss of or damage to any of the Contractor’s Equipment or for any losses, liabilities, costs, claims, actions or demands which the Contractor may incur or which may be made against it as a result of or in connection with any such loss or damage.
69 | SECTION - VI SAMPLE FORMS AND PROCEDURES (FORMS) | Section VI Sample Forms and Procedures, APPENDIX-3: INSURANCE REǪUIREMENTS (e) | Contractor’s Plant and Machinery (CPM) Insurance | Clarification | The Employer shall be jointly insured under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 34.1, except for the Third Party Liability, Automobile Liability Insurance, Workmen Compensation Policy and Contractor's Plant and Machinery (CPM) Insurances, and the Contractor’s Subcontractors shall be jointly insured under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 34.1 except for the Cargo Insurance During Transport, Automobile Liability Insurance, Workmen Compensation Policy and Contractor's Plant and Machinery (CPM ) Insurances. All insurer’s rights of subrogation against such jointly insured for losses or claims arising out of the performance of the Contract shall be waived under such policies. | The Employer shall be jointly named as additional insured under all insurance policies taken out by the Contractor pursuant to GCC Sub- Clause 34.1, except for the Third Party Liability, Automobile Liability Insurance, Workmen Compensation policy and Contractors Plant and Machinery (CPM) Insurances, and the Contractor’s Subcontractors shall be jointly named as additional insured under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 34.1 except for the Cargo Insurance During Transport, Automobile Liability Insurance, Workmen Compensation Policy Insurances, and Contractors Plant and Machinery (CPM) insurances. All insurer’s rights of subrogation against such jointly insureds for losses or claims arising out of the performance of the Contract shall be waived under such policies. | The Employer and subcontractors shall be additional insured under the EAR insurance policy, for its interests under the Contract, in all of the relevant insurances.