| Sl. No. | Clause Ref. No. | Existing provision | Amended as |
| --- | --- | --- | --- |
|  | Para 1.1 C & D of Appendix-1 to Contract Agreement, Terms and Procedures of Payment | 1.1 Supply of Goods Portion ………………………. C. Progressive Payment Payment of the Ex-works price of Main Equipment/ materials (excluding Thyristor Valves and all Spares) for each consignment shall be made progressively on certification of the Employer and on the basis of work performed using the following guidelines: C.1 Twenty percent (20%)^# of the Ex-Works price component of Main Equipment/Materials (excluding Thyristor Valves and all Spares) shall be paid progressively after dispatch of the Equipment/Materials and on submission of documents indicated hereinunder: (a) Evidence of dispatch [Consignment Note (R/R or L/R)] (b) Contractor’s GST invoice, claim & packing list identifying contents of each shipment. (c) Insurance policy/certificate (d) Manufacturer’s/Contractor’s guarantee certificate of Quality. (e) Material Inspection Clearance Certificate (MICC) for despatch issued by the Employer’s representative and the Contractor’s factory inspection report (f) Test certificate (g) Additional performance securities, if required, as per Technical Specification. (h) the details of items, components, raw materials, services etc. procured/availed from MSEs, if any, for the preceding 6 months, in respect of all the contracts in the respective executing Region of POWERGRID as per format enclosed at Section VI, Forms, Volume-I of the bidding documents. (i) Submission of (i) Authorization certificate issued by domestic manufacturer for selling Domestically Manufactured Iron & Steel Products, if applicable; and (ii) Affidavit of Self certification regarding Domestic Value Addition in Iron & Steel Products; in line with GCC Clause 5.7. (j) Value- addition certificate on half-yearly basis (Sep 30 and Mar 31), duly certified by the Statutory Auditors of the Domestic Manufacturer, that the claims of value-addition made for the product during the preceding 6 months are in accordance with the ‘Policy for providing preference to Domestically Manufactured Iron & Steel Products in Government Procurement’. ^ (i) In case, the Contractor opts not to take interest free advances (initial and interim) or has opted to take interest free advances (initial and interim) but the advance payment(s) has become inadmissible for the reason specified in 1.1A and 1.1B above, then this payment shall be 60% instead of 20%. (ii) In case, the Contractor opts not to take interest free initial advance or has opted to take interest free initial advance but the advance payment has become inadmissible for the reason specified in 1.1A above and Contractor has taken interest free interim advance, then this payment shall be 30% instead of 20%. (iii) In case, the Contractor has taken interest free initial advance and opts not to take interest free interim advance or has opted to take interest free interim advance but the interim advance payment has become inadmissible for the reason specified in 1.1B above, then this payment shall be 50% instead of 20%. # In case of Thyristor Valves, this payment shall be 45% instead of 20%. In case, the Contractor opts not to take interest free initial advance or has opted to take interest free initial advance but the advance payment has become inadmissible for the reason specified in 1.1A above, then this payment shall be 55% instead of 45%. C.2 Twenty percent (20%)## of the Ex-works price of Main Equipment/Materials (excluding Thyristor Valves and all Spares) shall be paid on receipt and storage at site and on physical verification and furnishing of necessary certificate by Employer’s representative. ## In case of Thyristor Valves, this payment shall be 25% instead of 20%. D Final Payment Balance 20% (Twenty percent) of the Ex-works price component of Main Equipment/Materials (including Thyristor Valves but excluding all Spares) shall be paid on: a) 05% (Five Percent) on Proof of submission of required number of reproducible, O&M Manuals, approved drawings, data sheets, test report, pamphlets and manuals of mandatory spares, maintenance & testing equipment. b) 15% (Fifteen Percent) on successful completion of erection, testing and commissioning and issuance of Taking Over Certificate. c) However, in case of delay in testing and commissioning & issuance of taking over certificate by Employer beyond six (6) months from the date of receipt of equipment at site, the last 20% of CIF/Ex-Works price of respective equipment shall be paid after issuance of a certificate by POWERGRID’s representative that the equipment have been received in good conditions and on submission of a bank guarantee of equivalent amount, which shall be kept valid initially for a period of twelve (12) months or until three (3) months after the expected date of commissioning (in case it is possible to anticipate the same), whichever is earlier, provided all other conditions as per para a), b) & c) above are complied with by the Contractor. If the commissioning does not take place within the validity period of BG, the validity of BG shall be extended from time to time. The bank guarantee shall, however, be released within one month of successful commissioning of the respective equipment by the Employer. | 1.1 Supply of Goods Portion ………………………. C. Progressive Payment Payment of the Ex-works price of Main Equipment/ materials (excluding Thyristor Valves and all Spares) for each consignment shall be made progressively on certification of the Employer and on the basis of work performed using the following guidelines: C.1 Twenty Five percent (25%)^# of the Ex-Works price component of Main Equipment/Materials (excluding Thyristor Valves and all Spares) shall be paid progressively after dispatch of the Equipment/Materials and on submission of documents indicated hereinunder: (a) Evidence of dispatch [Consignment Note (R/R or L/R)] (b) Contractor’s GST invoice, claim & packing list identifying contents of each shipment. (c) Insurance policy/certificate (d) Manufacturer’s/Contractor’s guarantee certificate of Quality. (e) Material Inspection Clearance Certificate (MICC) for despatch issued by the Employer’s representative and the Contractor’s factory inspection report (f) Test certificate (g) Additional performance securities, if required, as per Technical Specification. (h) the details of items, components, raw materials, services etc. procured/availed from MSEs, if any, for the preceding 6 months, in respect of all the contracts in the respective executing Region of POWERGRID as per format enclosed at Section VI, Forms, Volume-I of the bidding documents. (i) Submission of (i) Authorization certificate issued by domestic manufacturer for selling Domestically Manufactured Iron & Steel Products, if applicable; and (ii) Affidavit of Self certification regarding Domestic Value Addition in Iron & Steel Products; in line with GCC Clause 5.7. (j) Value- addition certificate on half-yearly basis (Sep 30 and Mar 31), duly certified by the Statutory Auditors of the Domestic Manufacturer, that the claims of value-addition made for the product during the preceding 6 months are in accordance with the ‘Policy for providing preference to Domestically Manufactured Iron & Steel Products in Government Procurement’. ^ (i) In case, the Contractor opts not to take interest free advances (initial and interim) or has opted to take interest free advances (initial and interim) but the advance payment(s) has become inadmissible for the reason specified in 1.1A and 1.1B above, then this payment shall be 65% instead of 25%. (ii) In case, the Contractor opts not to take interest free initial advance or has opted to take interest free initial advance but the advance payment has become inadmissible for the reason specified in 1.1A above and Contractor has taken interest free interim advance, then this payment shall be 35% instead of 25%. (iii) In case, the Contractor has taken interest free initial advance and opts not to take interest free interim advance or has opted to take interest free interim advance but the interim advance payment has become inadmissible for the reason specified in 1.1B above, then this payment shall be 55% instead of 25%. # In case of Thyristor Valves, this payment shall be 50% instead of 25%. In case, the Contractor opts not to take interest free initial advance or has opted to take interest free initial advance but the advance payment has become inadmissible for the reason specified in 1.1A above, then this payment shall be 60% instead of 50%. C.2 Twenty Five percent (25%)## of the Ex-works price of Main Equipment/Materials (excluding Thyristor Valves and all Spares) shall be paid on receipt and storage at site and on physical verification and furnishing of necessary certificate by Employer’s representative. ## In case of Thyristor Valves, this payment shall be 30% instead of 25%. D Final Payment Balance 10% (Ten percent) of the Ex-works price component of Main Equipment/Materials (including Thyristor Valves but excluding all Spares) shall be paid on: a) 05% (Five Percent) on Proof of submission of required number of reproducible, O&M Manuals, approved drawings, data sheets, test report, pamphlets and manuals of mandatory spares, maintenance & testing equipment. b) 05% (Five Percent) on successful completion of erection, testing and commissioning and issuance of Taking Over Certificate. c) However, in case of delay in testing and commissioning & issuance of taking over certificate by Employer beyond six (6) months from the date of receipt of equipment at site, the last 20% of CIF/Ex-Works price of respective equipment shall be paid after issuance of a certificate by POWERGRID’s representative that the equipment have been received in good conditions and on submission of a bank guarantee of equivalent amount, which shall be kept valid initially for a period of twelve (12) months or until three (3) months after the expected date of commissioning (in case it is possible to anticipate the same), whichever is earlier, provided all other conditions as per para a), b) & c) above are complied with by the Contractor. If the commissioning does not take place within the validity period of BG, the validity of BG shall be extended from time to time. The bank guarantee shall, however, be released within one month of successful commissioning of the respective equipment by the Employer. |
|  | IFB (8.2) | # 8.2 Under the Integrity Pact Program (IPP), a panel of Independent External Monitors (IEMs) comprising Sh. Nand Lal Singh, Sh. Subodh Kumar Jaiswal and Sh. R. Govindrajan has been appointed by CVC. Correspondence, if any, to the panel of IEMs be addressed to the following: Independent External Monitor C/o CGM (CS-P&S), Contract Services department Power Grid Corporation of India Limited, ‘Saudamini’, 3rd Floor, Plot No. – 2, Sector – 29, Gurgaon – 122001, Haryana E-mail IDs of IEMs: nlsingh3@gmail.com subodhjaiswal22@gmail.com rgrvig@gmail.com | # 8.2 Under the Integrity Pact Program (IPP), a panel of Independent External Monitors (IEMs) comprising Sh. Nand Lal Singh and Sh. R. Govindrajan has been appointed by CVC. Correspondence, if any, to the panel of IEMs be addressed to the following: Independent External Monitor C/o CGM (CS-P&S), Contract Services department Power Grid Corporation of India Limited, ‘Saudamini’, 3rd Floor, Plot No. – 2, Sector – 29, Gurgaon – 122001, Haryana E-mail IDs of IEMs: nlsingh3@gmail.com rgrvig@gmail.com |
|  | ITB 9.3 (o) | Supplementing ITB clause 9.3(o) with the following: …………………… Under the Integrity Pact Program (IPP), a panel of Independent External Monitors (IEMs) comprising Sh. Nand Lal Singh, Sh. Subodh Kumar Jaiswal and Sh. R. Govindrajan has been appointed by CVC. Correspondence, if any, to the panel of IEMs be addressed to the following: Independent External Monitor C/o CGM (CS-P&S), Contract Services department Power Grid Corporation of India Limited, ‘Saudamini’, 3rd Floor, Plot No. – 2, Sector – 29, Gurgaon – 122001, Haryana E-mail IDs of IEMs: nlsingh3@gmail.com subodhjaiswal22@gmail.com rgrvig@gmail.com | Supplementing ITB clause 9.3(o) with the following: …………………… Under the Integrity Pact Program (IPP), a panel of Independent External Monitors (IEMs) comprising Sh. Nand Lal Singh and Sh. R. Govindrajan has been appointed by CVC. Correspondence, if any, to the panel of IEMs be addressed to the following: Independent External Monitor C/o CGM (CS-P&S), Contract Services department Power Grid Corporation of India Limited, ‘Saudamini’, 3rd Floor, Plot No. – 2, Sector – 29, Gurgaon – 122001, Haryana E-mail IDs of IEMs: nlsingh3@gmail.com rgrvig@gmail.com |
|  | Section -VI (Forms and Procedures): 5. FORM OF CONTRACT AGREEMENT | ……………….……………. Article 6. Integrity Pact Under the Integrity Pact Program (IPP), a panel of Independent External Monitors (IEMs) comprising Sh. Nand Lal Singh, Sh. Subodh Kumar Jaiswal and Sh. R. Govindrajan has been appointed by CVC. Correspondence, if any, to the panel of IEMs be addressed to the following: Independent External Monitor C/o CGM (CS-P&S), Contract Services department Power Grid Corporation of India Limited, ‘Saudamini’, 3rd Floor, Plot No. – 2, Sector – 29, Gurgaon – 122001, Haryana E-mail IDs of IEMs: nlsingh3@gmail.com subodhjaiswal22@gmail.com rgrvig@gmail.com | ……………….……………. Article 6. Integrity Pact Under the Integrity Pact Program (IPP), a panel of Independent External Monitors (IEMs) comprising Sh. Nand Lal Singh and Sh. R. Govindrajan has been appointed by CVC. Correspondence, if any, to the panel of IEMs be addressed to the following: Independent External Monitor C/o CGM (CS-P&S), Contract Services department Power Grid Corporation of India Limited, ‘Saudamini’, 3rd Floor, Plot No. – 2, Sector – 29, Gurgaon – 122001, Haryana E-mail IDs of IEMs: nlsingh3@gmail.com rgrvig@gmail.com |