## Sheet1
Clarification No.–II to Bidding Document for Package – I : Unified Network Management System (U-NMS) for Central Sector & State Sector Communication in NER under Establishment of State of Art Unified Network Management System (U-NMS) for ISTS & State Utility Communication network in North Eastern Region (NER); Specification No.: CC-CS/1057-NER/CommEqp-4167/3/G4
S.No | Page Reference | Clause Reference | Clause Description | Earlier Query raised | PGCIL Earlier Response | Further Query Request with Justification | PGCIL Response
1 | 73 | Vol. II Part-B Section-1 1.2, 1.2.1 | Data Exchange Data Exchange with and National UNMS Centres The UNMS system shall acquire data of inter-regional links & cross-border links by exception calculated, manually entered and transfer time stamped SOE data from NEs & connected UNMS/NMS/EMS over SNMP, CORBA, XML, REST,SOAP,HTML, HTTP or any industry standard protocol. | Our understanding is that the propsoed U-NMS shall facilitate centralized supervision, operation & control of the NE Region and State level Communication system being used for Power System Operation & Monitoring and it will be connected to National U-NMS for central monitoring of the region. However, as per this clause, the proposed U-NMS system shall acquire the data of inter-regional and cross-border links, so does this means that the requirement here is that the proposed U-NMS will act as National U-NMS as well. Kindly confirm and share details as this would considerably impact the U-NMS sizing or ammend the clause accordingly. | The proposed regional U-NMS shall be exchanging data with National U-NMS for inter-regional links & cross border links to get the overall status of the regional communication network. | We understand that the proposed U-NMS will be integraed with National U-NMS and will acquire data for monitoring of its own regional & cross border links and not for other regions' cross border & inter-regional links. | Confirmed
2 | 13 | Vol. II Part-A Section-1 Point 1.7. e) | Import and Adaption of database & displays made by Employer/Owner for existing NMS system including import of historical data stored in existing servers for integration in new system. | Kindly confirm whether the required schemas and data will be provided by PGCIL to accomplish the historical data migration. | The data shall be fetched from existing NMS as prt of data acquisition. | We request to kindly confirm and share below details: 1.Whether the requried database and access to schemas etc. of existing NMS/EMS/NES is available with PGCIL so that the same can be considered for import & integration. 2. Size of data to be imported. 3. Retention period for data to be imported, whether 7 years or 12 months. | 1 . Existing MS/EMS/NES database to be prepared as part of data acquistion scope. 2. Size of data to be collected as part of site survey. 3. Retention period is specified in the relevant section of TS.
3 | 19 | Volume II Part A Section-1 1.9.2 . Xxv | After successful deployment of UNMS system, all data from Excel sheets and disparate sources shall be migrated to proposed UNMS system so that operations team can work efficiently. | Please share more details on data to be migrated from excel sheets and disparate sources to better assess the migration requirement and delivery plan. | Bidder to Comply TS
4 | 13 | Vol. II Part-A Section-1 Point 1.7. g) | Integration & Testing with new EMS/NMS/NEs coming up during implementation and AMC period of this Contract | Kindly share complete details of the existing as well as Future EMS/NMS/Nes etc. that are planned and will need to be integrated during implementiaton as well as during AMC as these details are required to properly size the solution. Kindly also confirm whether the 20 months delivery period is for integration of existing systems only, and the new NMS/EMS/NEs that come up during implementaton period will be integrated in addition to these 20 months and will not impact the project completion and signoff. | The sizing of the solution shall be done as per Appendix-G. | We request to kindly confirm and share below details: 1. The details provided in the TS Appendix for upcoming NMSs/EMS/NEs are final and shall be considered for integration 2. Any further NMS/EMS/NEs etc. other than these shall be considerd with separate CRs, commericals and the required licensing shall be procured by PGCIL 3. We understand that that New/upcoming national U-NMS/NMS/EMS/NEs will be excluded from the project delivery period of 20 Months and shall be integrated as and when ready and will not effect the project completion and signoff | 1. The sizing of the UNMS system shall be done as per Appendix G. The details provided in Appendix A is not exhaustive and shall be finalized during detail engineering. 2. The sizing shall be done as per Appendix G i.e. for 2000 NEs with expansion capability of 200%. Any upcoming NE/NMS during implementation and AMC period shall be integrated . 3. Confirmed
5 | 19 | Vol. II Part-A Section-1 1.9.2 xviii | Integration of existing equipment and with other planned equipment being procured by Employer/Owner in future. Contractor is responsible for integrating the complete system i.e. upcoming/future network equipment also. |  | Bidder to comply TS. If needed, Details in addition to TS may be collected by the Bidder on their own.
6 | 14 | Vol. II Part-A Section-1 Point 1.7. s) | Comprehensive Maintenance of the supplied system for seven (7) years including one (1) year defect liability period as per specification including future UNMS/NMS/EMS & NE Integrations, Database configurations, Maintaining Spare inventory etc. | Kinldy share details of planned Future UNMS/NMS/EMS & NEs that would be integrated to size the solution | The details are provided at Appendix-A. | We request to kindly confirm and share below details: 1. The details provided in TS Appendix A for upcoming NMEs/EMS/NEs are final and shall be considered for integration 2. Any further NMS/EMS/NEs etc. other than these shall be considered with separate CRs, Commericals and the required licensing shall be procured by PGCIL 3. We understand that that New/upcoming national U-NMS/NMS/EMS/NEs will be excluded from the project delivery period of 20 Months and shall be integrated as and when ready and will not effect the project completion and signoff | 1. The sizing of the UNMS system shall be done as per Appendix G. The details provided in Appendix A is not exhaustive and shall be finalized during detail engineering. 2. The sizing shall be done as per Appendix G i.e. for 2000 NEs with expansion capability of 200%. Any upcoming NE/NMS during implementation and AMC period shall be integrated . 3. Confirmed
7 | 19 | Vol. II Part-A Section-1 1.9.2 . Xxvi | Tie up with existing communication system provider for providing necessary system information of existing OEMs of Communication system for getting required information for seamless integration with U-NMS system as per requirements mentioned in different sections of Technical Specification. | We understand that the existing equipment like NMS/EMS/NEs etc. are covered under support contract and necessary support for integration will be faclitated by PGCIL. Kindly confirm and also suggest whether the current vendors of NMS/NEs are providing support & maintenance for their equipment. Kinldy confirm what kind of technical tie-up is envisaged, whether its AMC support of existing NMS/NEs or Integration Support with U-NMS or both , so that required commerical aspect can be ascertained | Tie up with existing communication system provider is required for getting necessary system information of existing OEMs of Communication system for seamless integration with U-NMS system. AMC of existing NMS/NEs is not in scope of bidder. | Since the existing NMS/EMS/Nes OEM AMC is taken care by PGCIL and required contracts may be in place for the same, we hereby request PGCIL to facilitate in establishing the communication with the existing OEM's for initiating the necessary discussion. | Teaming agreement needs to be done by bidder with existing OEMs as part of scope of work for seemless integration with U-NMS system.
8 | 14 | Vol. II Part-A Section-1 Point 1.7. l) | Integration of all the supplied equipments and existing system | We understand that required changes in existing systems and any required NBI Adapters/API for integration will be provided by the existing vendors (except 35 NE which will be directly integrated) and PGCIL will facilitate the same for integration with proposed U-NMS. | Bidder to comply TS. | Kindly confirm below details: 1. We understand that any kind of configuration at existing NMSs/EMS/NE's will be taken care by existing service provider of PGCIL and required support for NBI/API/Adapter development shall be facilitated by PGCIL. 2. The required database and access to schemas etc. of existing NMS/EMS/NE's are available with PGCIL for successfull integration with proposed U-NMS | 1. Bidder to comply TS wrt to seemless integration of supplied systems and existing system.
9 | 14 | Vol. II Part-A Section-1 Point 1.7. m) | The contractor’s scope shall include customization of its database, such as configuration of database, scan period and all other database parameters required to integrate existing system successfully. |  |  |  | 2.Existing MS/EMS/NES database to be prepared as part of data acquistion scope.
10 | 28 | Vol. II Part-A Section-2 2.2 | Project Schedule Completion schedule of the project is 20 months from the date award of contract agreement .Based upon this the bidder shall submit a preliminary project implementation schedule along with the bid. The detail project implementation schedule shall be submitted by the Contractor after award for Employer’s/Owner’s approval, which shall include at least the following activities: | Kindly share the details of the existing equipment Kindly also confirm whether the 20 months delivery period is for integration of existing systems only, and the new NMS/EMS/NEs that come up during implementaton period will be integrated in addition to these 20 months and will not impact the project completion and signoff. | Bidder to comply TS. | We understand that that integration of New/upcoming national U-NMs/NMS/EMS/NEs will be excluded from the project delivery period of 20 Months and will not effect the project completion and signoff, kindly confirm. | Confirmed
11 | 251 | Appendix-B | Project Implementation Schedule | Schedule for Server,SAN,TapeLibrary, Router,Switches, UPS delivery and deployment may also be incorporated. Please also update the supply and installation schedule. | Bidderr shall submit detailed Implementation schedule in the bid
12 | 13 | Volume II PART-A Technical Specification, Section 1.7 (g | Integration & Testing with new EMS/NMS/NEs coming up during implementation and AMC period of this Contract | Request PGCIL to consider the count of NMS/NE's that are implemented and in production at the time of notification of award of contract and when the same is integrated into the new U-NMS the project sign-off to be issued so that new NMS/NE's integration will continue in warranty / AMC. | Bidder to comply TS.
13 | 10 | Volume II PART-A Technical Specification, Section 1.4.1, B | ISTS Communication provided by Private Transmission Agencies | Please share the details of equipments/lines provided by private transmission agencies | Bidder to comply TS. If needed, Details in addition to TS may be collected by the Bidder on their own. | We request to kindly provide the details of private transmission agencies/systems to ascertain the integration efforts and necessary arrangemnts can be done for the same. | Bidder to comply TS. If needed, Details in addition to TS may be collected by the Bidder on their own.
14 | 14 | Vol. II Part-A Section-1 Point 1.7. n) | Shifting of existing system workstations and Installation of new system workstations at temporary location in parallel for intervening period. | We understand that the new workstations systems will be deployed at the existing or new locations without any temporary location. Kindly confirm Kindly share details related to shifting involved if any to ascertain the efforts related to cabling etc. | All supplied system shall be installed in existing or new location identified for the system, however, minor civil works may be required to be done by the bidder for installation of the system. | We understand that there will be no temporary implementation at any of the sites, kindly confirm and share below information: 1.Shifting of the systems from temporary location to permanent should not be considered under the project timelines as dismantling and re-deployments of the systems as per the ask can be momentous task. We further request that functional testing and commissioning should be considered even if systems are up and running at the Temporary Location. 2. Kindly confirm whether any shifting will be involved or not. And if yes, pls share the details of shifting location to ascertain the efforts. | Bidde to comply TS.
15 | 14 | Vol. II Part-A Section-1 Point 1.7. o) | Shifting and Installation of new system in UNMS Centre. This shall include all the services including cabling, interface modification and shifting or re-shifting of system required for intervening period and for final shifting to main UNMS Centre. Re-cabling for some or all equipments as required for final shifting shall also be in the scope of supplier | We understand that the new U-NMS is to be deployed at 02 lcoations and there is no shifting involved. Kindly confirm and share details related to shifting involved if any to ascertain the efforts related to cabling etc. | Please refer reply at sl. no. 24
16 | 16 | Volume II PART-A Technical Specification, Section 1.8.1 | Teaming Agreement of bidder with OEM | Please clarify that the teaming agreement should be submitted at time of acceptance of PO | Yes, the teaming agreement shall be submitted along with the bid. | Kindly confirm that teaming agreement is required between the bidder and NMS OEM only and not for rest of the Hardware OEM's etc. | Confirmed
17 | 59-60 | Volume II Part A Section-3 3.4.9.3 | Less than 99.99% Deduction of 2% of the apportioned price of the apportioned quarterly AMC for every 0.5% or part there of decrease in availability under 99.99%. (Maximum amount of deduction is limited to 100% of AMC charges) | Kindly cap the maximum penalty to 05% of Yearly AMC Charges | Bidder to Comply TS | We request to kindly cap the maximum penalty within 05% to 15% of the AMC Charges as per standards followed. | Bidder to Comply TS
18 | 147 | Volume II Part B Section-4 4.1.2 | Operating System The operating system of all the equipments of U-NMS system including network equipments shall be latest version. The operating system shall be hardened to provide robust security. In order to facilitate cyber security requirements including patch management, common operating system is preferable to be used by all server nodes within the U-NMS System. | We understand that open-source operating system, virtualization and database can be proposed, kindly confirm. | Bidder to Comply TS | Operating system,database details are not mentioned in the TS, so we would request that the bidder can propose open-source operating system, virtualization and databases that meet the requirements. Kinldy confirm. | Bidder to Comply TS
19 | 253 | Appendix-C | BoQ WAN Router for Server Location | Kinldy confirm quantity of WAN routers and connectivity architecture for U-NMS Routers as there are 06 Routers mentioned whereas its not matchig the Network Architecture provided in Appendix-K for MAIN & Backup control center. Pleas also share the details of existing sites and new sites architecure details as well. | Bidder to Comply TS | Kindly confirm that the quantity mentioned in Appendix C BoQ matches the TS and we can consider the same for supply. | Bidder to Comply TS