| S N | Clause | Provision of Bidding Documents | Bidder’s Query | POWERGRID's Reply |
| --- | --- | --- | --- | --- |
| 1 | ITB 2.1 in BDS in Vol-I of Bidding Document | …… …… Further, the firm has to be a ‘Class-I local supplier’ as defined under Public Procurement (Preference to Make in India) Order, 2017 issued by Department for promotion of Industry and Internal Trade (DPIIT), Ministry of Commerce and Industry, Government of India vide order dated 15/06/2017, its revision dated 04/06/2020 (PPP-MII Order) read in conjunction with ‘Public Procurement (Preference to Make in India) Order 2017- Notification of Telecom Products, Services or works‘ issued by Department of Telecommunications (DoT), vide notification dated 29/08/2018 (DoT Order) and subsequent modifications/amendments if any. Firms who are not ‘Class-I local supplier’ shall not be eligible to bid. The ‘Class-I local supplier’ shall give a self-certification in his bid in the given format, indicating the percentage of Local Content and certifying that the item offered meets the Local Content requirement for ‘Class –I local supplier’ and shall give details of the location(s) at which value addition is made. Further, in case of packages above Rs. 10 Cr, the ‘Class-I local supplier’ shall provide a certificate from statutory auditor or cost auditor of the company (in the case of companies) or from a practicing cost accountant or practicing chartered accountant (in respect of suppliers other than companies) giving the percentage of Local Content. Any false declaration regarding Local Content by the bidder shall be a transgression of Integrity Pact and action shall be taken in line with provisions of the Integrity Pact and in line with the provisions of the PPP-MII Order. Further, in case price reduction during e-RA, the ‘Class –I local supplier’ shall ensure that the item offered meets the Local Content requirement considering the revised prices. …… | Please clarify if Class I supplier are the OEM technology partner who can offer the solution to the Bidder. This does not imply the Bidder to be himself class I supplier. | Provisions of the bidding document are amply clear. |
| 2 | ITB 13.3 in BDS in Vol-I of Bidding Document | Any bid not accompanied by an acceptable bid security or Online Payment Acknowledgement towards Bid Security (along with the bid or subsequently pursuant to ITB Clause 21.1), except as exempted at 13.1 above, shall be rejected by the Employer as being nonresponsive, pursuant to ITB Sub-Clause 22.4. The bid security of a joint venture must be in the name of all the partners in the joint venture submitting the bid. | Central PSU may be exempted from submission of EMD | Please refer Amendment-II dt. 03/12/2020 in this regard. |
| 3 | GCC 18.3.3.24 in SCC in Vol-I of Bidding Document | In case of an accident at Site or adjacent thereto, the Contractor shall be responsible for payment of a sum as indicated below to be deposited with the Employer, which will be passed on by the Employer to such person or next to kith and kin of the deceased: a; Fatal injury or accident causing death; Rs. 15,00,000/- per person. b; Major injuries or accident causing 25% or more permanent disablement; Rs. 5,00,000/- per person. ……. | Kindly clarify if this needs to be deposited at what stage of the project. Considering that we are providing UNMS with Datacenter and working with Software, this clause may be kindly waived off. | Provisions of the bidding document is amply clear. |
| 5 | ITB Clause 29 in Vol-I of Bidding Document | 29. e-Reverse Auction (e-RA) 29.1 The electronic Reverse Auction (e-RA) shall be conducted for further reduction in the price in the manner as indicated herein below. …… | We request you to kindly delete this procedure. As per Industry Standard Practice, Quality and Cost Based Selection (QCBS) or Lowest Cost evaluation is being followed . Also, we would like to emphasis that LCBS is a proven selection method wherein bidder’s put their best effort to optimise their quote without any compromise to RFP functionality, in order to win and perform in an open competitive environment. Therefore e-reverse option is not in practice in many similar Govt System Integration project. | Provisions of the bidding document shall prevail. |
| 6 | GCC 18.7 in Vol-I of Bidding Document | Watching and Lighting The Contractor shall provide and maintain at its own expense all lighting, fencing, and watching when and where necessary for the proper execution and the protection of the Facilities, or for the safety of the owners and occupiers of adjacent property and for the safety of the public. | We understand since this project only applicable for indoor activities. This support shall be provided by PGCIL. Kindly confirm | Provisions of the bidding document shall prevail. |
| 7 | GCC 18.5 in Vol-I of Bidding Document | Emergency Work If, by reason of an emergency arising in connection with and during the execution of the Contract, any protective or remedial work is necessary as a matter of urgency to prevent damage to the Facilities, the Contractor shall immediately carry out such work. …… …… | Contractor work shall be limited to Contractor's expertise and 1% of CV. Also same shall be paid to Contractor at actual. Please confirm | Provisions of the bidding document shall prevail |
| 8 | GCC 9.2.2 in SCC in Vol-I of Bidding document | The security shall be in the Form of unconditional Bank Guarantee attached hereto in Section VI - Sample Forms and Procedures. The security shall be discharged after completion of the facilities or relevant part thereof corresponding to which advance has been drawn. - Procedure for effective reduction in the Advance Payment Security The Advance Payment Security shall be allowed to be reduced every six (06) months after First Running Account Bill/Stage payment under the Contract if the validity of the Bank Guarantee is more than one year. The cumulative amount of reduction shall be allowed upto full value of the Bank Guarantee upon adjustment of the corresponding advance and certification to this effect by the Employer’s representative. It should be clearly understood that reduction in the value of advance Bank Guarantee shall not in any way dilute the Contractor's responsibility and liabilities under the Contract including in respect of the Facilities for which reduction in the value of security is allowed | PROPOSED CLAUSE The security shall be in the Form of unconditional Bank Guarantee attached hereto in Section VI - Sample Forms and Procedures. The security shall be discharged after completion of the facilities or relevant part thereof. - Procedure for effective reduction in the Advance Payment Security The Advance Payment Security shall be allowed to be reduced every six (06) months after First Running Account Bill/Stage payment under the Contract if the validity of the Bank Guarantee is more than one year. It should be clearly understood that reduction in the value of advance Bank Guarantee shall not in any way dilute the Contractor's responsibility and liabilities under the Contract including in respect of the Facilities for which reduction in the value of security is allowed. | Provisions of the bidding document shall prevail |
| 9 | GCC 12.3 in Vol-I of Bidding document | The obligation of a party under GCC Sub-Clauses 12.1 and 12.2 above, however, shall not apply to that information which (a) now or hereafter enters the public domain through no fault of that party (b) can be proven to have been possessed by that party at the time of disclosure and which was not previously obtained, directly or indirectly, from the other party hereto (c) otherwise lawfully becomes available to that party from a third party that has no obligation of confidentiality. | PROPOSED CLAUSE The obligation of a party under GCC Sub-Clauses 12.1 and 12.2 above, however, shall not apply to that information which (a) now or hereafter enters the public domain through no fault of that party (b) can be proven to have been possessed by that party at the time of disclosure and which was not previously obtained, directly or indirectly, from the other party hereto (c) otherwise lawfully becomes available to that party from a third party that has no obligation of confidentiality, provided such third party is not, to the receiving party's knowledge, in breach of any obligation to confidentiality relating to such information;. (d) Either the Employer or the Contractor may disclose Confidential Information of the other party if the receiving party is required to do so by any ruling of a governmental or regulatory authority or court or by mandatory law, provided that written notice of such ruling is given without undue delay to the party disclosing such Confidential Information so as to give such party an opportunity to intervene. Confidential Information which is disclosed in such way must be marked "Confidential" | Provisions of the bidding document shall prevail |
| 10 | GCC 12.5 in Vol-I of Bidding document | The provisions of this GCC Clause 12 shall survive termination, for whatever reason, of the Contract. | PROPOSED CLAUSE The provisions of this GCC Clause 12 shall survive termination for a period of one year, for whatever reason, of the Contract | Provisions of the bidding document shall prevail |
| 11 | GCC 18.3.1.2 in Vol-I of Bidding document | The Contractor shall keep the Employer indemnified in case any action is taken against the Employer by the competent authority on account of contravention of any of the provisions of any Act or rules made thereunder, regulations or notifications including amendments | The Contractor shall keep the Employer indemnified in case any action is taken against the Employer by the competent authority on account of contravention of any of the provisions of any Act or rules made thereunder, regulations or notifications including amendments occurring solely due to the acts or omissions of the Contractor (PROPOSED CLAUSE) | Provisions of the bidding document shall prevail |
| 12 | GCC 18.4 in Vol-I of Bidding document | Opportunities for Other Contractors 18.4.1 The Contractor shall, upon written request from the Employer or the Project Manager, give all reasonable opportunities for carrying out the work to any other contractors employed by the Employer on or near the Site. ……. | The Section should be deleted as the selection for contractor should be the prerogative of the bidder only. | Provisions of the bidding document shall prevail |
| 13 | GCC 18.5 in Vol-I of Bidding document | Emergency Work If, by reason of an emergency arising in connection with and during the execution of the Contract, any protective or remedial work is necessary as a matter of urgency to prevent damage to the Facilities, the Contractor shall immediately carry out such work. If the Contractor is unable or unwilling to do such work immediately, the Employer may do or cause such work to be done as the Employer may determine is necessary in order to prevent damage to the Facilities. In such event the Employer shall, as soon as practicable after the occurrence of any such emergency, notify the Contractor in writing of such emergency, the work done and the reasons therefor. If the work done or caused to be done by the Employer is work that the Contractor was liable to do at its own expense under the Contract, the reasonable costs incurred by the Employer in connection therewith shall be paid by the Contractor to the Employer. In case such work is not in the scope of the Contractor, the cost of such remedial work shall be borne by the Employer. | PROPOSED CLAUSE If, by reason of an emergency arising in connection with and during the execution of the Contract, any protective or remedial work is necessary as a matter of urgency to prevent damage to the Facilities, the Contractor shall immediately carry out such work. If the Contractor is unable or unwilling to do such work immediately, the Employer may do or cause such work to be done as the Employer may determine is necessary in order to prevent damage to the Facilities. In such event the Employer shall, as soon as practicable after the occurrence of any such emergency, notify the Contractor in writing of such emergency, the work done and the reasons therefor. If the work done or caused to be done by the Employer is work that the Contractor was liable to do at its own expense under the Contract solely due to the gross negligence or willful misconduct of the Contractor, the reasonable costs incurred by the Employer in connection therewith shall be paid by the Contractor to the Employer based on actual and proven grounds. In case such work is not in the scope of the Contractor or defects not occurring solely due to the gross negligence or willful misconduct of the Contractor, the cost of such remedial work shall be borne by the Employer. | Provisions of the bidding document shall prevail |
| 14 | GCC Clause 21.2 in Vol-I of Bidding document | Completion Time Guarantee …… If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to half percent (0.5%) of the Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each week or part thereof which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed). The Employer may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the Contractor. The payment or deduction of such damages shall not relieve the Contractor from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract. | If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities solely for its own gross negligence or willful misconduct, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to half percent (0.5%) per week of the unpaid portion of the Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each week or part thereof which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of unpaid portion of the Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed). The Employer may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the Contractor. The payment or deduction of such damages shall not relieve the Contractor from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract. (PROPOSED CLAUSE) | Provisions of the bidding document shall prevail |
| 15 | GCC Clause 22 in Vol-I of Bidding document | Defect Liability ……. The Contractor shall not be responsible for the repair, replacement or making good of any defect or of any damage to the Facilities arising out of or resulting from any of the following causes: a) improper operation or maintenance of the Facilities by the Employer (b) operation of the Facilities outside specifications provided in the Contract (c) normal wear and tear. | ADDITION of point d. (d) Any defects arising not solely due to the gross negligence or wilful misconduct by the Contractor or its subcontractor. | Provisions of the bidding document shall prevail |
| 16 | GCC Clause 22.7 in Vol-I of Bidding document | Defect Liability ……. If the Contractor fails to commence the work necessary to remedy such defect or any damage to the Facilities caused by such defect within a reasonable time (which shall in no event be considered to be less than fifteen (15) days), the Employer may, following notice to the Contractor, proceed to do such work, and the reasonable costs incurred by the Employer in connection therewith shall be paid to the Employer by the Contractor or may be deducted by the Employer from any monies due the Contractor or claimed under the Performance Security. | PROPOSED CLAUSE If the Contractor fails to commence the work necessary to remedy such defect or any damage to the Facilities caused by such defect within a reasonable time (which shall in no event be considered to be less than fifteen (15) days) and not giving justified reasons for such failure of commencement, the Employer may, following notice to the Contractor, proceed to do such work, and the reasonable costs incurred by the Employer in connection therewith shall be paid to the Employer by the Contractor or may be deducted by the Employer from any monies due the Contractor or claimed under the Performance Security. | Provisions of the bidding document shall prevail |
| 17 | GCC 23.2 in Vol-I of Bidding document | Functional Guarantees ….. If, for reasons attributable to the Contractor, the minimum level of the Functional Guarantees specified in the Technical Specifications are not met either in whole or in part, the Contractor shall at its cost and expense make such changes, modifications and/or additions to the Plant or any part thereof as may be necessary to meet at least the minimum level of such Guarantees. The Contractor shall notify the Employer upon completion of the necessary changes, modifications and / or additions, and shall request the Employer to repeat the Guarantee Test until the minimum level of the Guarantees has been met. If the Contractor eventually fails to meet the minimum level of Functional Guarantees, the Employer may consider termination of the Contract pursuant to GCC Sub-Clause 36.2.2 and recover the payments already made to the Contractor. | If, for reasons solely attributable to the Contractor, the minimum level of the Functional Guarantees specified in the Technical Specifications are not met either in whole or in part, the Contractor shall at its cost and expense make such changes, modifications and/or additions to the Plant or any part thereof as may be necessary to meet at least the minimum level of such Guarantees. The Contractor shall notify the Employer upon completion of the necessary changes, modifications and / or additions, and shall request the Employer to repeat the Guarantee Test until the minimum level of the Guarantees has been met. If the Contractor eventually fails to meet the minimum level of Functional Guarantees solely for its own gross negligence or wilful misconduct even after reasonable time was provided by the Employer to rectify such breach, the Employer may consider termination of the Contract pursuant to GCC Sub-Clause 36.2.2 and recover the payments already made to the Contractor. (PROPOSED CLAUSE) | Provisions of the bidding document shall prevail |
| 18 | GCC 23.3 in Vol-I of Bidding document | Functional Guarantees ….. If, for reasons attributable to the Contractor, the Functional Guarantees specified in the Technical Specifications are not attained either in whole or in part, but the minimum level of the Functional Guarantees specified in the Technical Specifications is met, the Contractor shall, at the Contractor’s option, either - make such changes, modifications and/or additions to the Facilities or any part thereof that are necessary to attain the Functional Guarantees at its cost and expense within a mutually agreed time and shall request the Employer to repeat the Guarantee Test, or - pay liquidated damages to the Employer in respect of the failure to meet the Functional Guarantees in accordance with the provisions in the SCC | PROPOSED CLAUSE If, for reasons solely attributable to the Contractor’s gross negligence or willful misconduct, the Functional Guarantees specified in the Technical Specifications are not attained either in whole or in part, but the minimum level of the Functional Guarantees specified in the Technical Specifications is met, the Contractor shall, at the Contractor’s option, either (a) make such changes, modifications and/or additions to the Facilities or any part thereof that are necessary to attain the Functional Guarantees at its cost and expense within a mutually agreed time and shall request the Employer to repeat the Guarantee Test, or (b) pay liquidated damages to the Employer in respect of the failure to meet the Functional Guarantees in accordance with the provisions in the SCC. | Provisions of the bidding document shall prevail |
| 19 | GCC 24.2 in Vol-I of Bidding document | Equipment Performance Guarantees…. If the guarantees specified in Appendix – 8 (Guarantees, Liquidated Damages for Non – Performance) to the Contract Agreement are not established, then the Employer shall, at the Employer’s discretion either (a) reject the equipment, or (b) accept the equipment after assessing liquidated damages in accordance with the provision in the SCC against the Contractor and such amounts shall be deducted from the Contract Price or otherwise recovered from the Contractor. | PROPOSED CLAUSE If the guarantees specified in Appendix – 8 (Guarantees, Liquidated Damages for Non – Performance) to the Contract Agreement are not established, then the Employer shall, at the Employer’s discretion either (a) reject the equipment based on valid grounds and giving reasonable time to the Contractor rectify such breach, or (b) accept the equipment after assessing liquidated damages in accordance with the provision in the SCC against the Contractor and such amounts shall be deducted from the Contract Price or otherwise recovered from the Contractor. | Provisions of the bidding document shall prevail |
| 20 | GCC clause 25.1 in Vol-I of Bidding document | Patent Indemnity ….. The Contractor shall, subject to the Employer‟s compliance with GCC Sub-Clause 25.2, indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney‟s fees and expenses, which the Employer may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright or other intellectual property right registered or otherwise existing at the date of the Contract by reason of: (a) the installation of the Facilities by the Contractor or the use of the Facilities in the country where the Site is located; and (b) the sale of the products produced by the Facilities in any country. Such indemnity shall not cover any use of the Facilities or any part thereof other than for the purpose indicated by or to be reasonably inferred from the Contract, any infringement resulting from the use of the Facilities or any part thereof, or any products produced thereby in association or combination with any other equipment, plant or materials not supplied by the Contractor, pursuant to the Contract Agreement. | PROPOSED CLAUSE The Contractor shall, subject to the Employer’s compliance with GCC Sub-Clause 25.2, indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, which the Employer may suffer as a result of any infringement alleged infringement of any patent, utility model, registered design, trademark, copyright or other intellectual property right registered or otherwise existing at the date of the Contract arising solely out of the actions of the Contractor by reason of: (a) the installation of the Facilities by the Contractor or the use of the Facilities in the country where the Site is located; and (b) the sale of the products produced by the Facilities in any country. Such indemnity shall not cover any use of the Facilities or any part thereof other than for the purpose indicated by or to be reasonably inferred from the Contract, any infringement resulting from the use of the Facilities or any part thereof, or any products produced thereby in association or combination with any other equipment, plant or materials not supplied by the Contractor, pursuant to the Contract Agreement | Provisions of the bidding document shall prevail |
| 21 | GCC clause 25.3 in Vol-I of Bidding document | Patent Indemnity ….. The Employer shall indemnify and hold harmless the Contractor and its employees, officers and Subcontractors from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney‟s fees and expenses, which the Contractor may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright or other intellectual property right registered or otherwise existing at the date of the Contract arising out of or in connection with any design, data, drawing, specification, or other documents or materials provided or designed by or on behalf of the Employer. | PROPOSED CLAUSE The Employer shall indemnify and hold harmless the Contractor and its employees, officers and Subcontractors from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’ fees and expenses, which the Contractor may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright or other intellectual property right registered or otherwise existing at the date of the Contract arising out of or in connection with any design, data, drawing, specification, or other documents or materials provided or designed by or on behalf of the Employer. | Provisions of the bidding document shall prevail |
| 22 | GCC 26 in Vol-I of Bidding document | Limitation of Liability 26.1 Except in cases of gross negligence or willful misconduct, - the Contractor and the Employer shall not be liable to the other party for any indirect or consequential loss or damage, loss of use, loss of production, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the Contractor to pay liquidated damages to the Employer and - the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed the total Contract Price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment, or to any obligation of the Contractor to indemnify the Employer with respect to patent infringement. | PROPOSED CLAUSE (a)the Contractor and the Employer shall not be liable to the other party for any indirect or consequential loss or damage, loss of use, remote, punitive, special, loss of production, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the Contractor to pay liquidated damages to the Employer and (b) the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed the total unpaid portion of the Contract Price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment, or to any obligation of the Contractor to indemnify the Employer with respect to patent infringement, material breach due to gross negligence or willful misconduct. | Provisions of the bidding document shall prevail |
| 23 | GCC 29.1 in Vol-I of Bidding document | Loss of or Damage to Property; Accident or Injury to Workers; Indemnification….. The Contractor shall indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney‟s fees and expenses, in respect of the death or injury of any person or loss of or damage to any property (other than the Facilities whether accepted or not), arising in connection with the supply and installation of the Facilities and by reason of the negligence of the Contractor or its Subcontractors, or their employees, officers or agents, except any injury, death or property damage caused by the negligence of the Employer, its contractors, employees, officers or agents. | PROPOSED CLAUSE The Contractor shall indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, in respect of the death or injury of any person or loss of or damage to any property (other than the Facilities whether accepted or not), arising in connection with the supply and installation of the Facilities and solely by reason of the gross negligence of the Contractor or its Subcontractors, or their employees, officers or agents, except any injury, death or property damage caused by the negligence of the Employer, its contractors, employees, officers or agents. | Provisions of the bidding document shall prevail |
| 24 | GCC 32.1 in Vol-I of Bidding document | Force Majeure… “Force Majeure” shall mean any event beyond the reasonable control of the Employer or of the Contractor, as the case may be, and which is unavoidable notwithstanding the reasonable care of the party affected, and shall include, without limitation, the following: (a) war, hostilities or warlike operations (whether war be declared or not), invasion, act of foreign enemy and civil war, (b) rebellion, revolution, insurrection, mutiny, usurpation of government, conspiracy, riot and civil commotion, (c) earthquake, landslide, volcanic activity, flood or cyclone, or other inclement weather condition, nuclear and pressure waves or other natural or physical disaster, | Force Majeure” shall mean any event beyond the reasonable control of the Employer or of the Contractor, as the case may be, and which is unavoidable notwithstanding the reasonable care of the party affected, and shall include, without limitation, the following: (a) war, hostilities or warlike operations (whether war be declared or not), invasion, act of foreign enemy and civil war, (b) rebellion, revolution, insurrection, mutiny, usurpation of government, conspiracy, riot and civil commotion, (c) earthquake, landslide, volcanic activity, rains, flood or cyclone, or other inclement weather condition, nuclear and pressure waves or other natural or physical disaster. | Provisions of the bidding document shall prevail |
| 25 | GCC 36.1 in Vol-I of Bidding document | Termination…. 36.1 Termination for Employer’s Convenience 36.1.1 The Employer may at any time terminate the Contract for any reason by giving the Contractor a notice of termination that refers to this GCC Sub-Clause 36.1. ….. | be deleted or be limited to O&M period. | Provisions of the bidding document shall prevail |
| 26 | GCC 36.2.2 in Vol-I of bidding document | 36.2 Termination for Contractor’s Default …. 36.2.2 If the Contractor (a) has abandoned or repudiated the Contract (b) has without valid reason failed to commence work on the Facilities promptly or has suspended (other than pursuant to GCC Sub-Clause 35.2) the progress of Contract performance for more than twenty-eight (28) days after receiving a written instruction from the Employer to proceed (c) persistently fails to execute the Contract in accordance with the Contract or persistently neglects to carry out its obligations under the Contract without just cause ….. | To be deleted | Provisions of the bidding document shall prevail |
| 27 | GCC clause 39.2 in Vol-I of Bidding document | 39. Arbitration …… Sole Arbitration The sole Arbitrator shall be chosen from a panel of empaneled Arbitrators maintained by POWERGRID. The same shall comprise of retired Judges and retired Senior executives of PSUs other than POWERGRID. Further, the choice of sole Arbitrator shall be governed by the amount of claim in the following manner: …… | Kindly delete the Sole arbitration clause. All the dispute shall be settle by Three member arbitral tribunal. | Provisions of the bidding document shall prevail |
| 28 |  |  | We understand that Civil works is not part of the scope of the contractor/bidder. If yes, Please provide the details .OR Kindly delete this clause. | Provisions of the bidding document is amply clear |
| 29 | - |  | General Assignment Clause In order to have better working capital for the project we propose an Assignment clause as below to be included in the Payment Schedule, which shall allow us to factor the bill with financing institution, and therefore enable us to participate in the Tender. Assignment Clause (new Clause proposed) : “The Contractor shall not, without the express prior written consent of the Employer, assign to any third party the Contract or any part thereof, or any right, benefit, obligation or interest therein or there under, except that the Contractor shall be entitled to assign either absolutely or by way of charge any monies due and payable to it or that may become due and payable to it under the Contract to any Financial Institution(s) or Bank(s) or NBFC(s). In the event the Contractor assigns the monies due and payable to it or that may become due and payable to it, under the Contract, to any Financial Institution(s) or Bank(s) or NBFC(s), the Employer shall acknowledge the intimation letter it may receive from such financial institution(s) or Bank(s) or NBFC (s). If the Employer does not reply within 15 days of the receipt of the intimation letter, it can be considered as “acknowledged by the Employer”. Furthermore the Employer will provide an indicative date by when the funds will be released to the Contractor as a measure of comfort for the decisions of Financial Institution(s) or Bank(s) or NBFC(s)”. | Provisions of the bidding document shall prevail |
| 30 | GCC 22.8.1 in Vol-I of Bidding document | Defect Liability…… At the end of the Defect Liability Period, the Contractor's Liability ceases except for latent defects. The Contractor's liability for latent defects warranty shall be limited to period of ten (10) years from the end of Defect Liability Period. For the purpose of this clause, the latent defects shall be the defects inherently lying within the material or arising out of design deficiency, which do not manifest themselves during the Defect Liability Period defined in this GCC Clause 22, but later. | As the period of DLP and AMC is 7 years after TOC. So please clarify about this 10 years period. | Provisions of the bidding document shall prevail |
| 31 | GCC 3.3 in Vol-I of Bidding document | The supply of Mandatory Spare Parts, if any, shall be included in the Contract. Beside the aforesaid Mandatory Spares parts, the Contractor shall ensure the availability of spare parts required for the operation and maintenance of the Facilities to the Employer for a minimum period of 15 years from Completion of the Facilities. The Contractor shall carry sufficient inventories to ensure an ex-stock supply of consumable spares for the plant and equipment. If so desired by the Employer, the Contractor shall submit the specifications, price and the terms and conditions relating to the supply thereof for such spares identified by the Employer with validity period of 6 months within 30 days of receipt of request from Employer for its consideration and placement of order. | As per contractor understanding, mandatory spares are the minimum spares which contractor will consider for the maintenance period of DLP and AMC. It will be contractor's responsibility to decide the number of spares against each equipment. | Provisions of the bidding document are amply clear. |
| 32 | GCC 20.1.5.2 in Vol-I of Bidding document | If within twenty one (21) days after receipt of the Contractor's notice, the Project Manager fails to issue the Taking Over Certificate or fails to inform the Contractor in writing of the justifiable reasons why the Project Manager has not issued the Taking Over Certificate, the Facilities or the relevant part thereof shall be deemed to have been Taken Over as at the date of the Contractor's said notice. | As the DLP period will be started after OAC (Operational Acceptance Certificate) so in case of any delay + 21 days being mentioned to release TOC by Project manager of Employer to verify the documents, who will maintain the network during this period. This period can be 21 days or more. Please clarify. | Provisions of the bidding document are amply clear. |
| 33 | GCC 20.2.2.5 in Vol-I of Bidding document | If within twenty one (21) days after receipt of the Contractor's notice, the Project Manager fails to issue the Operational Acceptance Certificate or fails to inform the Contractor in writing of the justifiable reasons why the Project Manager has not issued the Operational Acceptance Certificate, the Facilities or the relevant part thereof shall be deemed to have been accepted as at the date of the Contractor's said notice. | As the DLP period will be started after OAC (Operational Acceptance Certificate) so in case of any delay + 21 days being mentioned to release OAC by Project manager of Employer to verify the documents, who will maintain the network during this period. This period can be 21 days or more. Please clarify. | Provisions of the bidding document are amply clear. |
| 34 | ITB clause 35.1 in Vol-I of Bidding document | Within twenty-eight (28) days after receipt of the Notification of Award, the successful Bidder shall furnish the performance security for 10% (Ten percent) of the contract price plus additional performance securities, if any, in line with the requirement of Qualification Requirements, in the amount given in the BDS and in the form provided in Section VI, Sample Forms and Procedures, of the Bidding Documents. The performance security of a joint venture shall be in the name of joint venture. | Request you to kindly amend the clause as below: Within twenty-eight (28) days after receipt of the Notification of Award, the successful Bidder shall furnish the performance security for 10% (Ten percent) of the CAPEX contract price plus additional performance securities, if any, in line with the requirement of Qualification Requirements, in the amount given in the BDS and in the form provided in Section VI, Sample Forms and Procedures, of the Bidding Documents. The performance security of a joint venture shall be in the name of joint venture. | Provisions of the bidding document shall prevail. Further, please refer Amendment-III dt. 04/12/2020 in this regard. |
| 35 | ITB clause 35.1 in Vol-I of Bidding document | Within twenty-eight (28) days after receipt of the Notification of Award, the successful Bidder shall furnish the performance security for 10% (Ten percent) of the contract price plus additional performance securities, if any, in line with the requirement of Qualification Requirements, in the amount given in the BDS and in the form provided in Section VI, Sample Forms and Procedures, of the Bidding Documents. The performance security of a joint venture shall be in the name of joint venture. | Request you to kindly amend the clause as below: The Contractor shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten percent (10%) of the CAPEX Contract Price, with a validity upto ninety (90) days beyond the Defect Liability Period. The same shall be extended by the Contractor time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. | Provisions of the bidding document shall prevail. Further, please refer Amendment-III dt. 04/12/2020 in this regard. |
| 36 | GCC 9.3.1 in Vol-I of Bidding document | The Contractor shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten percent (10%) of the Contract Price, with a validity upto ninety (90) days beyond the Defect Liability Period. The same shall be extended by the Contractor time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. | Request you to kindly amend the clause as below: The Contractor shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten percent (10%) of the CAPEX Contract Price, with a validity upto ninety (90) days beyond the Defect Liability Period. The same shall be extended by the Contractor time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. | Provisions of the bidding document shall prevail. Further, please refer Amendment-III dt. 04/12/2020 in this regard. |
| 37 | GCC 9.3.1 in Vol-I of Bidding | The Contractor shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten percent (10%) of the Contract Price (including Maintenance charges during Defect Liability Period and AMC charges after Defect Liability Period), with a validity upto ninety (90) days beyond the Defect liability Period. The same shall be extended by the Contractor from time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. | Request you to kindly amend the clause as below: The Contractor shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten percent (10%) of the Contract Price (including excluding Maintenance charges during Defect Liability Period and AMC charges after Defect Liability Period), with a validity upto ninety (90) days beyond the Defect liability Period. The same shall be extended by the Contractor from time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. | Provisions of the bidding document shall prevail. Further, please refer Amendment-III dt. 04/12/2020 in this regard. |
| 38 | GCC 21.2 in Vol-I of Bidding | If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to half percent (0.5%) of the Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each week or part thereof which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed). The Employer may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the Contractor. The payment or deduction of such damages shall not relieve the Contractor from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract. | We request that the clause is amended as follows to maintain a balanced risk approach on both sides to ensure discipline in execution and at the same time prevent cost loading: "If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to half percent (0.5%) of the Capex of the undelivered supplies and/or delayed services for the reasons not attributable to the Contractor Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each week or part thereof which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Capex Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed)." | Provisions of the bidding document shall prevail. |
| 39 | Appendix-1 (TERMS AND PROCEDURES OF PAYMENT) in Section-VI in Vol-I of Bidding document | …… 1.1 A Interest Bearing Advance (Optional*): Ten percent (10%) of the Ex-works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid as an interest bearing initial advance after signing the Contract Agreement and on submission of (a) Proforma invoice(s), (b) Advance Bank Guarantee for 110% (one hundred ten percent) of the amount of Advance, in line with GCC Clause 9.2, (c) Performance Securities in line with GCC Clause 9.3 and (d) Detailed PERT Network/Bar chart and its approval by the Employer. ……. | Request you to kindly allow interest free advance to avoid any form of cost loading. | Provisions of the bidding document shall prevail. |
| 40 | Appendix-1 (TERMS AND PROCEDURES OF PAYMENT) in Section-VI in Vol-I of Bidding document | 1.3 …. It is the Employer’s understanding that as per extant provisions, on the charges for supply of services related to Inland transportation, In-transit insurance, loading and unloading by the Contractor to the Employer, GST is not payable. The Contractor is, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account. | We understand that since the main Contractor will not be a registered as a Goods Transport Agency, GST will not be under Reverse Charge and shall have to be borne by the Employer. Please confirm | Provisions of the bidding document are amply clear. |
| 41 | GCC 10.4 in Vol-I of Bidding document | ….. It is the Employer‟s understanding that as per extant provisions, on the charges for supply of services related to Inland transportation, In-transit insurance, loading and unloading by the Contractor to the Employer, GST is not payable. The Contractor is, however, advised to check the position from their own sources. If payable, the same shall be to the Contractor’s account and Employer shall not reimburse any GST on this account. | We understand that since the main Contractor will not be a registered as a Goods Transport Agency, GST will not be under Reverse Charge and shall have to be borne by the Employer. Please confirm | Provisions of the bidding document are amply clear. |
| 42 | ITB Clause 11.4 in Vol-I of the Bidding document | …… It is the Employer’s understanding that as per extant provisions, on the charges for supply of services related to Inland transportation, In-transit insurance, loading and unloading by the Bidder to the Employer, GST is not payable. The Bidder is, however, advised to check the position from their own sources. If payable, the same shall be to the Bidder’s account and Employer shall not reimburse any GST on this account. | We understand that since the main Contractor will not be a registered as a Goods Transport Agency, GST will not be under Reverse Charge and shall have to be borne by the Employer. Please confirm | Provisions of the bidding document are amply clear. |
| 43 | ITB Clause 11.4 in BDS in Vol-I of the Bidding document | …..It is the Employer’s understanding that as per extant provisions, on the charges for supply of services related to Inland transportation, In-transit insurance, loading and unloading by the Bidder to the Employer, GST is not payable. The Bidder is, however, advised to check the position from their own sources. If payable, the same shall be to the Bidder’s account and Employer shall not reimburse any GST on this account. …… | We understand that since the main Contractor will not be a registered as a Goods Transport Agency, GST will not be under Reverse Charge and shall have to be borne by the Employer. Please confirm | Provisions of the bidding document are amply clear. |
| 44 | Appendix-1 (TERMS AND PROCEDURES OF PAYMENT) in Section-VI in Vol-I of Bidding document | 1.6 Maintenance Charges during Defect Liability Period Maintenance Charges during Defect Liability Period shall be paid at the end of Defect Liability Period on furnishing GST invoice(s) for the Annual Maintenance Charges (AMC) and Performance Security(ies) in line with GCC Clause 9.3 and on certification by the Employer in line with provisions of Technical Specifications. | Request you to kindly make amed the clasue as below: Maintenance Charges during Defect Liability Period shall be paid quarterly during the at the end of Defect Liability Period on furnishing GST invoice(s) for the Annual Maintenance Charges (AMC) and Performance Security(ies) in line with GCC Clause 9.3 and on certification by the Employer in line with provisions of Technical Specifications. | Provisions of the bidding document shall prevail. |
| 45 | Appendix-1 (TERMS AND PROCEDURES OF PAYMENT) in Section-VI in Vol-I of Bidding document | D Final Payment Balance fifteen percent (15%) of the Ex-works price component of the Main Equipment shall be paid within 30 days of Operational Acceptance (on successful completion of system availability tests) and proof of submission of the required no. of reproducibles, O&M manuals, approved drawings, data sheets, test reports, pamphlets and manual of spares, maintenance & testing equipment etc. | Request you to kindly allow release of this 15% on installation against submission of bank guarantee of equivalent amount. This bank Guarantee shall be valid for till 30 days beyond Operational Acceptance/ Partial Acceptance, whichever is earlier. | Provisions of the bidding document shall prevail. |
| 46 | Appendix-1 (TERMS AND PROCEDURES OF PAYMENT) in Section-VI in Vol-I of Bidding document | 1.4 Supply of Services Portion: (a) Eighty five percent (85%) of the installation charges shall be paid on pro-rata basis after installation at site and on certification by the Employer. ……. (b) Balance fifteen percent (15%) shall be paid within 30 days of Operational Acceptance alongwith the corresponding final payment for supply portion mentioned at Clause C (a) above. | Request you to kindly allow release of this 15% on installation against submission of bank guarantee of equivalent amount. This bank Guarantee shall be valid for till 30 days beyond Operational Acceptance/ Partial Acceptance, whichever is earlier. | Provisions of the bidding document shall prevail. |
| 47 | GCC Clause 20.1.2.8 in Vol-I of Bidding document | In the event that the Contractor is unable to proceed with the Precommissioning of the Facilities pursuant to Sub-Clause 20.1.2 for reasons attributable to the Employer either on account of non-availability of other facilities under the responsibilities of other contractor(s), or for reasons beyond the Employer's control, the following provisions shall apply: When the Contractor is notified by the Project Manager that he will be unable to proceed with the activities and obligations pursuant to above GCC Sub-Clause 20.1.2.8, the Contractor shall be entitled to the following: ….. …. | Since there is a dependence on other parties for integration of the UNMS system with the existing systems/sub-systems, we request that the clause is amended as follows: "In the event that the Contractor is unable to proceed with the Pre-commissioning of the Facilities pursuant to Sub-Clause 20.1.2 for reasons attributable to the Employer either on account of non-availability of other facilities under the responsibilities of other contractor(s), or for reasons beyond the Contractor's Employer's control, the following provisions shall apply: When the Contractor is notified by the Project Manager that he will be unable to proceed with the activities and obligations pursuant to above GCC Sub-Clause 20.1.2.8, the Contractor shall be entitled to the following:---------" | Provisions of the bidding document shall prevail. |
| 48 | GCC Clause 33.1.1 in Vol-I of Bidding document | Subject to GCC Sub-Clauses 33.2.5 and 33.2.7, the Employer shall have the right to propose, and subsequently require, that the Project Manager order the Contractor from time to time during the performance of the Contract to make any change, modification, addition or deletion to, in or from the Facilities (hereinafter called “Change”), provided that such Change falls within the general scope of the Facilities and does not constitute unrelated work and that it is technically practicable, taking into account both the state of advancement of the Facilities and the technical compatibility of the Change envisaged with the nature of the Facilities as specified in the Contract. | Since the Contractor will be procuring the supplies from its vendors basis the quantities mentioned in the Schedule of Requirements (SOR), we request that the variation in the quantity is capped and the clause is amended as follows, to prevent cost loading in case the quantities are revised significantly: "Subject to GCC Sub-Clauses 33.2.5 and 33.2.7, the Employer shall have the right to propose, and subsequently require, that the Project Manager order the Contractor from time to time during the performance of the Contract to make any change, modification, addition or deletion to, in or from the Facilities (hereinafter called “Change”), provided that such Change falls within the general scope of the Facilities (i.e. limited to +/- 20% of the individual SOR quantities) and does not constitute unrelated work and that it is technically practicable, taking into account both the state of advancement of the Facilities and the technical compatibility of the Change envisaged with the nature of the Facilities as specified in the Contract." | Provisions of the bidding document shall prevail. |
| 49 | GCC 33.2.5 in Vol-I of Bidding document | The Employer shall issue the Contractor with a Change Order pursuant to GCC Sub-Clause 33.2 by way of amendment to the Contract or in any other manner deemed appropriate. Even if the Employer and the Contractor cannot reach agreement on the price for the Change, an equitable adjustment to the Time for Completion, or any other matters related to the Change Proposal, the Employer may nevertheless instruct the Contractor to proceed with the Change by issue of a “Pending Agreement Change Order” (“Pending Agreement Amendment”). | In order to expedite the execution, we request that the clause is amended as follows: "The Employer shall issue the Contractor with a Change Order pursuant to GCC Sub-Clause 33.2 by way of amendment to the Contract or in any other manner deemed appropriate no later than 15 days of evaluation submitted by the Contractor. Even if the Employer and the Contractor cannot reach agreement on the price for the Change, an equitable adjustment to the Time for Completion, or any other matters related to the Change Proposal, the Employer may nevertheless instruct the Contractor to proceed with the Change by issue of a “Pending Agreement Change Order” (“Pending Agreement Amendment”)." | Provisions of the bidding document shall prevail. |
| 50 | ITB Clause 2.1 in BDS (Section-III) in Vol-I of Bidding document | ….. Further, the firm has to be a ‘Class-I local supplier’ as defined under Public Procurement (Preference to Make in India) Order, 2017 issued by Department for promotion of Industry and Internal Trade (DPIIT), Ministry of Commerce and Industry, Government of India vide order dated 15/06/2017, its revision dated 04/06/2020 (PPP-MII Order) read in conjunction with ‘Public Procurement (Preference to Make in India) Order 2017- Notification of Telecom Products, Services or works‘ issued by Department of Telecommunications (DoT), vide notification dated 29/08/2018 (DoT Order) and subsequent modifications/amendments if any. Firms who are not ‘Class-I local supplier’ shall not be eligible to bid. …… | Please clarify if Class I supplier are the OEM technology partner who can offer the solution to the Bidder. This does not imply the Bidder to be himself class I supplier. | Provisions of the bidding document are amply clear. |
| 51 | GCC Clause 18.3.3.24 in Vol-I of Bidding document | If the Contractor does not take adequate safety precautions and/or fails to comply with the Safety Rules as prescribed by the Employer or under the applicable law for the safety of the equipment and plant or for the safety of personnel or the Contractor does not prevent hazardous conditions which cause injury to his own employees or employees of other Contractors or Employer‟s employees or any other person who are at Site or adjacent thereto, then the Contractor shall be responsible for payment of a sum as indicated below to be deposited with the Employer, which will be passed on by the Employer to such person or next to kith and kin of the deceased: | Kindly clarify if this needs to be deposited at what stage of the project. Considering that we are providing UNMS with Datacenter and working with Software, this clause may be kindly waived off. | Provisions of the bidding document shall prevail. |
| 52 | ITB Clause 9.3.d(ii) in Vol-I of Bidding document | a list giving full particulars, including available sources, of all spare parts, special tools, etc., necessary for the proper and continuing functioning of the facilities for a period of Fifteen (15) years following completion of facilities in accordance with provisions of contract; and | You are requested to kindly amend the duration as standard terms of IT equipment lifecycle which is usually 5-6 years. | Provisions of the bidding document shall prevail. |
| 53 | ITB Clause 9.3 (e) in Vol-I of Bidding document | The Employer reserves the right to delete any proposed Subcontractor from the list prior to award of contract, and after discussion between the Employer and the Contractor, the corresponding Appendix to the form of Contract Agreement shall be completed, listing the approved Subcontractors for each item concerned. | This clause should be applicable during the period of contract, if the employer/owner is not satisfy with performance of sub-contractor. Deleting or rejecting the subcontractor before award of contract will impact the overall construct of the bid for the bidder. You are requested to kindly remove or amend this clause. | Provisions of the bidding document shall prevail. |
| 54 | ITB Clause 9 in BDS in Vol-I of Bidding document | For this package, Bid from Joint Venture is not permitted | Kindly Clarify that consortium is allowed or not. | Provisions of the bidding document are amply clear. |
| 55 | GCC 9.3.1 in SCC in Vol-I of Bidding document | The Contractor shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten percent (10%) of the Contract Price (including Maintenance charges during Defect Liability Period and AMC charges after Defect Liability Period), with a validity upto ninety (90) days beyond the Defect liability Period. The same shall be extended by the Contractor from time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. Apart from Performance Security(ies) as mentioned above, the contractor is required to arrange additional Performance Security(ies), for various equipment, if applicable, as per Technical Specifications. The above additional Performance Securities shall be submitted before release of first dispatch payment of respective equipment. The said security(ies) shall be required to be extended from time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. Further, Contractor shall within 28 days, after Defect Liability Period, provide Contract Performance Guarantee in the amount equivalent to Two Percent (2%) of the Total Contract Price to cover the contractor’s obligations under Maintenance Period as per the provisions in the Technical Specification, Vol-II, with a validity upto ninety (90) days beyond the AMC Period, as per Form - 20 of Section – VI: Sample Forms and Procedures. The said security(ies) shall be required to be extended from time to time till ninety (90) days beyond completion period of Annual Maintenance Contract as may be required under the Contract. | Ideally the Performance Security shall be covered in 10% of contract value. You are requested to kindly remove the additional Performance security and 2% under Maintenance as well. | Further, please refer Amendment-III dt. 04/12/2020 in this regard. |
| 56 | GCC 18.3.3.17 in SCC in Vol-I of Bidding document | …… In case, the Contractor fails to deploy Qualified Safety Officer(s)/Safety Supervisor(s) /Safety Steward(s) under each Contract, as specified in the Safety Plan, then the Contractor shall be responsible for payment of a sum of Rs. 15,00,000/- per quarter or part thereof, on a pro-rata basis, till the Safety Officer(s)/ Safety Supervisor(s) /Safety Steward(s)) is deployed, to be deposited with the Employer, which will be retained in the Safety Corpus Fund pursuant to GCC Sub-Clause 18.3.3.26 ……. | We understand that this is related to accidents happening due to the actions of the contractor. Any accident happening due to employer/owner or his contractors is not the responsibility of the bidder/contractor. Kindly confirm the same. | Provisions of the bidding document are amply clear. |
| 57 | GCC 18.3.3.25 in SCC in Vol-I of Bidding document | Notwithstanding above, the Contractor shall also be responsible for payment of sum as indicated below additionally which shall be deposited in Safety Corpus Fund pursuant to GCC Sub-Clause 18.3.3.26: a.; Upon 1st Fatal Accident; 1% of the Contract price as awarded, limited to Rs. 50,00,000/-. b.; Upon 2nd Fatal Accident; 1.5% of the Contract price as awarded, limited to Rs. 75,00,000/-. c.; Upon 3rd Fatal Accident; 2% of the Contract price as awarded, limited to Rs. 1,00,00,000/-. d.; Re-occurrence of Fatal Accident even after 3rd Fatal Accident; 2% of the Contract price as awarded, limited to Rs. 1,00,00,000/- per fatal accident. For the purpose of calculation of the aforesaid amounts, ‘Contract price, as awarded’, shall mean the total Contract Price for both Supply of Goods and Services for the works/facilities as per the originally awarded Contract/Notification/ Letter of Award (where contract has not been signed) exclusive of any taxes & duties additionally payable/reimbursable by POWERGRID or any change/adjustment due to Price Variation or subsequent amendments to the Contract or Notification/Letter of Award (where contract has not been signed). …. | We understand that this is related to accidents happening due to the actions of the contractor. Any accident happening due to employer/owner or his contractors is not the responsibility of the bidder/contractor. Kindly confirm the same. | Provisions of the bidding document are amply clear. |
| 58 | GCC 3.3 in Vol-I of Bidding document | The supply of Mandatory Spare Parts, if any, shall be included in the Contract. Beside the aforesaid Mandatory Spares parts, the Contractor shall ensure the availability of spare parts required for the operation and maintenance of the Facilities to the Employer for a minimum period of 15 years from Completion of the Facilities. The Contractor shall carry sufficient inventories to ensure an ex-stock supply of consumable spares for the plant and equipment. If so desired by the Employer, the Contractor shall submit the specifications, price and the terms and conditions relating to the supply thereof for such spares identified by the Employer with validity period of 6 months within 30 days of receipt of request from Employer for its consideration and placement of order. | Generally the lifecycle of IT product is 5 years and beyond the EOS date, the OEM supports the equipment up to 5 years. Accordingly the availability of spares is maximum up to 10 years only. Kindly amend the clause accordingly. | Provisions of the bidding document shall prevail. |
| 59 | GCC 3.4 in Vol-I of Bidding document | The Contractor shall guarantee that in the event of termination of production of spare parts by the Contractor or his Sub-Contractor: - The Contractor shall send advance notification to the Employer of the pending termination, with 2 (two) years time to permit the Employer to procure needed requirements, and - Following such termination, the Contractor shall furnish at no cost to the Employer the blueprints, drawings and specification of the spare parts, if requested. | Blueprints, drawings of products are proprietary of an OEM and same will not be shared by OEM. Kindly remove this from mentioned clause. | Provisions of the bidding document shall prevail. |
| 60 | GCC 21.2 in Vol-I of Bidding document | If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to half percent (0.5%) of the Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each week or part thereof which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed). …… | Penalty should be applicable only on the value of pending works and not on the whole contract value. Kindly amend this clause. | Provisions of the bidding document shall prevail. |
| 61 | GCC 22.8.1 in Vol-I of Bidding document | At the end of the Defect Liability Period, the Contractor's Liability ceases except for latent defects. The Contractor's liability for latent defects warranty shall be limited to period of ten (10) years from the end of Defect Liability Period. For the purpose of this clause, the latent defects shall be the defects inherently lying within the material or arising out of design deficiency, which do not manifest themselves during the Defect Liability Period defined in this GCC Clause 22, but later. | This clause is contradictory to contract period i.e. <Duration>. Kindly the correct the specified duration in this clause referring the contract duration. | Provisions of the bidding document shall prevail. |
| 62 | GCC 12.5 in Vol-I of Bidding document | 12. Confidential Information 12.1 The Employer and the Contractor shall keep confidential and shall not, without the written consent of the other party hereto, divulge to any third party any documents, data or other information furnished directly or indirectly by the other party hereto in connection with the Contract, whether such information has been furnished prior to, during or following termination of the Contract. Notwithstanding the above, the Contractor may furnish to its Subcontractor(s) such documents, data and other information it receives from the Employer to the extent required for the Subcontractor(s) to perform its work under the Contract, in which event the Contractor shall obtain from such Subcontractor(s) an undertaking of confidentiality similar to that imposed on the Contractor under this GCC Clause 12. ….. 12.5 The provisions of this GCC Clause 12 shall survive termination, for whatever reason, of the Contract. | requests the Confidentiality obligation to survive the termination and shall continue for a period of three (03) years thereafter | Provisions of the bidding document shall prevail. |
| 63 | GCC 21.2 in Vol-I of Bidding document | If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to half percent (0.5%) of the Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each week or part thereof which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed). The Employer may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the Contractor. The payment or deduction of such damages shall not relieve the Contractor from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract. | requests that the Liquidated Damages shall apply only when the delay is solely caused by bidder. | Provisions of the bidding document shall prevail. |
| 64 | GCC 26.1 (b) in Vol-I of Bidding document | 26. Limitation of Liability 26.1 Except in cases of gross negligence or willful misconduct, ….. (b) the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed the total Contract Price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment, or to any obligation of the Contractor to indemnify the Employer with respect to patent infringement. | requests the below modification in the clause: “the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed the total Contract Price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment, or to any obligation of the Contractor to indemnify the Employer with respect to patent infringement.” | Provisions of the bidding document shall prevail. |
| 65 | GCC 35 in Vol-I of Bidding document | 35. Suspension 35.1 The Employer may request the Project Manager, by notice to the Contractor, to order the Contractor to suspend performance of any or all of its obligations under the Contract. Such notice shall specify the obligation of which performance is to be suspended, the effective date of the suspension and the reasons therefor. The Contractor shall thereupon suspend performance of such obligation (except those obligations necessary for the care or preservation of the Facilities) until ordered in writing to resume such performance by the Project Manager. ….. | requests the that the Suspension shall be exercised by the Employer only after mutual agreement with contractor and in the event if Suspension is invoked, Employer shall be liable to pay contractor for the cost incurred by contractor during the Suspension Period. | Provisions of the bidding document shall prevail. |
| 66 | GCC 36 in Vol-I of Bidding document | 36. Termination 36.1 Termination for Employers Convenience 36.1.1 The Employer may at any time terminate the Contract for any reason by giving the Contractor a notice of termination that refers to this GCC Sub-Clause 36.1. | request mutual rights for termination. Termination for Convenience upon 90 days of notice; Termination for default after 30 days of Cure Period; | Provisions of the bidding document shall prevail. |
| 67 | GCC 36.2.2 in Vol-I of Bidding document | 36.2.2 If the Contractor (a) has abandoned or repudiated the Contract ….. - refuses or is unable to provide sufficient materials, services or labor to execute and complete the Facilities in the manner specified in the program furnished under GCC Sub-Clause 14.2 at rates of progress that give reasonable assurance to the Employer that the Contractor can attain Completion of the Facilities by the Time for Completion as extended, then the Employer may, without prejudice to any other rights it may possess under the Contract, give a notice to the Contractor stating the nature of the default and requiring the Contractor to remedy the same. If the Contractor fails to remedy or to take steps to remedy the same within fourteen (14) days of its receipt of such notice, then the Employer may terminate the Contract forthwith by giving a notice of termination to the Contractor that refers to this GCC Sub-Clause 36.2. | requests the Cure period of 30 days as against proposed 14 days by the Employer. | Provisions of the bidding document shall prevail. |
| 68 | GCC 39 in Vol-I of Bidding document | 39. Arbitration 39.1 All disputes or differences in respect of which the decision, if any, of the Project Manager and/or the Head of the Implementing Authority has not become final or binding as aforesaid shall be settled by arbitration in the manner provided herein below: 39.2 The arbitration shall be conducted by a sole arbitrator in case the amount of claim is less than Rs. 25 Crore and by three member arbitral tribunal in case the amount of claim is greater than Rs. 25 Crore. ….. | requests that the appointment of Arbitrator shall mutually discussed and agreed by the Parties in accordance with the Arbitration and Conciliation Act, 1996. | Provisions of the bidding document shall prevail. |
| 69 | - | Additional Proposal – Deemed Acceptance of Invoice | requests that the “Employer shall within seven (7) days from the date of receipt of the invoice notify contractor if there is any dispute in the invoice, failing which the invoice shall be deemed to be accepted by Customer.” | Provisions of the bidding document shall prevail. |
| 70 |  | Additional Proposal – Deemed Acceptance of Work/Deliverables | request that the “Deliverables shall be deemed to have been accepted by the Employer after seven (7) working days of delivery thereof unless the Employer satisfactorily demonstrates any material failure or deficiency in the Deliverables within the said period of seven (7) days.” | Provisions of the bidding document shall prevail. |
| 71 |  | Additional Proposal – Non-Solicitation | requests that the “Employer agrees, during the term of the Agreement and for a period of one (1) year following its termination, not to solicit or hire for employment any officer, employee, agent of contractor.” | Provisions of the bidding document shall prevail. |
| 72 | ITB Clause 28 and Clause 28.1 in BDS in Vol-I of Bidding document | 28. Purchase/ Domestic Preference 28.1 Purchase Preference as admissible under the policy of Government of India in vogue will be allowed to Central Public Sector Enterprises in evaluation and comparison of bids. Supplementing Sub Clause ITB 28.1 No purchase preference is presently applicable for the Plant and Equipment to be supplied under the Contract. Add a new sub clause 28.2 as under: No margin of domestic preference will be allowed in evaluation and comparison of bids. | Kindly state the current Policy applicable to Central Public Sector Enterprises. Is it Price preference or reservation of Quota or both. | Provisions of the bidding document are amply clear. |
| 73 | ITB Clause 29 in Vol-I of Bidding document | 29. e-Reverse Auction (e-RA) 29.1 The electronic Reverse Auction (e-RA) shall be conducted for further reduction in the price in the manner as indicated herein below. …… …… | Kindly explain the process that would be followed in e-Reverse Auction (e-RA), to protect the interest of those Bids/Products that qualify under Public Procurement (Preference to Make in India) Order, 2017 issued by Department for promotion of Industry and Internal Trade (DPIIT), Ministry of Commerce and Industry, Government of India vide order dated 15/06/2017, its revision dated 04/06/2020 (PPP-MII Order). | Provisions of the bidding document shall prevail. |
| 74 | ITB Clause 2.1 in BDS in Vol-I of Bidding document | ….. …. Further, the firm has to be a ‘Class-I local supplier’ as defined under Public Procurement (Preference to Make in India) Order, 2017 issued by Department for promotion of Industry and Internal Trade (DPIIT), Ministry of Commerce and Industry, Government of India vide order dated 15/06/2017, its revision dated 04/06/2020 (PPP-MII Order) read in conjunction with ‘Public Procurement (Preference to Make in India) Order 2017- Notification of Telecom Products, Services or works‘ issued by Department of Telecommunications (DoT), vide notification dated 29/08/2018 (DoT Order) and subsequent modifications/amendments if any. ….. ….. | Kindly explain the process that would be followed to protect the interest of those Bids/Products that qualify under Public Procurement (Preference to Make in India) Order, 2017 issued by Department for promotion of Industry and Internal Trade (DPIIT), Ministry of Commerce and Industry, Government of India vide order dated 15/06/2017, its revision dated 04/06/2020 (PPP-MII Order), when the Tender is a Turnkey Tender, where Supply and Services of different types are required, in varying quantities. The Tender calls for the Supply of Software, Hardware & Services. The Main theme of the Project is Network Management System (NMS). The Hardware is mainly required to run the Software or store the data or protect the data. Hence, would the whole Project be considered as a NMS as notified under "Sl No 23. Network Management systems (NMS) with its various derivatives", of Gazette Notification dated 29th August 2018. | Provisions of the bidding document shall prevail. |