|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No.** | **Clause ref.** | **Existing Provision** | **Amendment Provision** |
| 1. | Clause No. 3.2, IFB, Section-I | The completion period for the subject Package shall be **17 (Seventeen) Months** as specified in ITB Sub-Clause 24.1(c). | The completion period for the subject Package shall be as specified in ITB Sub-Clause 24.1(c):   | **Sl.** | **Description** | **Duration in Months from the date of Notification of Award** | | --- | --- | --- | | Taking Over by the Employer upon successful Completion of **220kV AIS (New) Substation Package SS 107T; Spec. No. CC/T/W-AIS/DOM/A02/25/04124,** shall be as per following: | | | | **1.** | **(A) Laying of downstream Transmission network from upcoming 400/220 kV Grid Substation Siot, Rajouri (ISTS)**  a) Establishment of 220/132kV GSS at Rajouri - II  b) Establishment of 220/132/33kV GSS at at Akhnoor-II (Domana) | **27 months** | | **2.** | **(B) Construction of Grid Sub Station at Baghthali, Kathua along with LILO of 220 kV S/C Sarna-Hiranagar Line**  a) Establishment of 220/66kV GSS at Baghthali, Kathua | **21 months** | |