| Sl. No. | Clause Ref. No. | Existing provision | Amended as |
| --- | --- | --- | --- |
|  | Clause No. 3.2, IFB section-I | The completion period for the subject Package shall be 17 (Seventeen) months. | The completion period for the subject Package shall be as mentioned below: Sl. No.; Activities; Duration in months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of:. 1; Pre-Bid Tie up for 220 kV Transformer Package TR-47T under Intra-State Transmission System for “Execution of System strengthening/ upgradation works and Intra-State Transmission System Projects by creation/ augmentation of Grid Stations and laying of Transmission Lines in the State of J&K” through Tariff Based Competitive Bidding (TBCB) route. Spec. No.: CC/T/W-TR/DOM/A04/25/03972. - 4 x 53.33 MVA, 220/33 kV, 1-phase Power Transformer [with 2 LV windings] at 220/33 kV GIS Grid-Sub Station at Sallar - 2X50 MVA, 132/33 kV, 3-Phase Power Transformer at 220/132kV GIS GSS at Katra-II - 2X50 MVA, 132/33 kV, 3-Phase Power Transformer at 220/132/33kV GSS at at Akhnoor-II (Domana); 27 months. - 4x53.33 MVA, 220/66/11 kV, 1- Phase Power Transformer at 220/66/11 kV Grid Substation at Baghthali, Kathua - 3x53.33 MVA, 220/66/11 kV, 1-Phase Power Transformer at 220/66/11 kV Grid Substation at Baghthali, Kathua; 21 months. |