| S N | Clause | Provision of Bidding Documents | Bidder’s Query | POWERGRID's Reply |
| --- | --- | --- | --- | --- |
| 1 | GCC 1.1 (ee) in SCC in Vol.I of bidding document | Sl. No.; Activities; Duration in months from the effective date of Contract. 1; Tower Package TW 01 for Navsari (PG) – Bhestan 220 kV D/C Line under Western Region System Strengthening Scheme (WRSS) – 22 Spec. No.: CC-CS/979-WR2/TW-4026/3/G4; 7 (Seven Months). | During walkover survey, we observed that the above subject proposed transmission line shall have following crossings: (i) Ahmadabad - Mumbai bullet train – 1 No. (ii) Bhusawal – Ahmadabad Double Track Railway line – 1 No. (iii) National Highways (Mumbai-A’bad NH-48 & Dhule-Surat NH-53) – 2 Nos. (iv) Live Power line crossings – 6 Nos. In addition to above said 10 crossings, the contractor needs to design and install 2 monopole towers in this line. Time required for making proposals for above said crossings, taking their approvals from the respective authorities and physical construction of this transmission line within a span of 7 months (and that too including monsoon) is almost impossible for any contractor. Considering above said practical difficulties, we request Power Grid to amend the project completion period to minimum 15 Months from the date issue of NOA. | The provisions of the Bidding Documents shall remain unchanged |