| Sl. No. | Clause Ref. No. | Existing provision | Bidder's Query/Comment | POWERGRID Reply |
| --- | --- | --- | --- | --- |
|  | ITB 24.1(C) | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-12-BULK for 10x500 MVA, 400/220/33kV 3-Ph Transformers Under " Bulk Procurement of 765kV & 400kV class Transformers and Reactors of various capacities under Lot-6" Spec. No.: CC/NT/W-TR/DOM/A04/25/10879; Remark (Indicative Period in Months from Award). Unit-1; 21 (Twenty-One Months); Engineering: 0-8 months Dispatch: 16-18 months Rcpt at site:17-19 months Erection & Ready for Commissioning:18-21 months (1st-5th) 5 units by 21 months. Unit-2; 21 (Twenty-One Months). Unit-3; 21 (Twenty-One Months). Unit-4; 21 (Twenty-One Months). Unit-5; 21 (Twenty-One Months). Unit-6; 24 (Twenty-Four Months); Engineering: 0-10 months Dispatch: 19-21 months Rcpt at site:20-22 months Erection & Ready for Commissioning:21-24 months (6th-10th) 5 units by 24 months. Unit-7; 24 (Twenty-Four Months). Unit-8; 24 (Twenty-Four Months). Unit-9; 24 (Twenty-Four Months). Unit-10; 24 (Twenty-Four Months). Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/ equipment/ material/ services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformers. | Delivery: Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-12-BULK for 10x500 MVA, 400/220/33kV 3-Ph Transformers Under " Bulk Procurement of 765kV & 400kV class Transformers and Reactors of various capacities under Lot-6"Spec. No.: CC/NT/W-TR/DOM/A04/25/10879 Unit-1; 33 Months; Engineering: 0-8 Months Dispatch: 28-30 Months Receipt at site: 29-31 Months Erection & Ready for Commissioning: 30-33 Months (1st -5th) 5 units by 33 Months. Unit-2; 33 Months. Unit-3; 33 Months. Unit-4; 33 Months. Unit-5; 33 Months. Unit-6; 36 Months; Engineering: 0-10 Months Dispatch: 31-33 Months Receipt at site: 32-34 Months Erection & Ready for Commissioning: 33-36 Months (6th -7th) 5 units by 36 Months. Unit-7; 36 Months. Unit-8; 36 Months. Unit-9; 36 Months. Unit-10; 36 Months. | Completion Schedule of the units shall as per Provisions of Bidding Documents. |
|  | GCC 1.1(e) & 1.1 (ee) | Supplementing Sub-Clause GCC 1.1(ee) The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-12-BULK for 10x500 MVA, 400/220/33kV 3-Ph Transformers Under " Bulk Procurement of 765kV & 400kV class Transformers and Reactors of various capacities under Lot-6" Spec. No.: CC/NT/W-TR/DOM/A04/25/10879; Remark (Indicative Period in Months from Award). Unit-1; 21 (Twenty-One Months); Engineering: 0-8 months Dispatch: 16-18 months Rcpt at site:17-19 months Erection & Ready for Commissioning:18-21 months (1st-5th) 5 units by 21 months. Unit-2; 21 (Twenty-One Months). Unit-3; 21 (Twenty-One Months). Unit-4; 21 (Twenty-One Months). Unit-5; 21 (Twenty-One Months). Unit-6; 24 (Twenty-Four Months); Engineering: 0-10 months Dispatch: 19-21 months Rcpt at site:20-22 months Erection & Ready for Commissioning:21-24 months (6th-10th) 5 units by 24 months. Note: The Unit mentioned above includes the aforesaid Transformer (including Insulating Oil) and any other item/equipment/material/services (as per BoQ/Price Schedules) to be supplied along with the said Transformer. The said item/ equipment/ material/ services (as per BoQ/Price Schedules) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformers. | Delivery: Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-12-BULK for 10x500 MVA, 400/220/33kV 3-Ph Transformers Under " Bulk Procurement of 765kV & 400kV class Transformers and Reactors of various capacities under Lot-6"Spec. No.: CC/NT/W-TR/DOM/A04/25/10879 Unit-1; 33 Months; Engineering: 0-8 Months Dispatch: 28-30 Months Receipt at site: 29-31 Months Erection & Ready for Commissioning: 30-33 Months (1st -5th) 5 units by 33 Months. Unit-2; 33 Months. Unit-3; 33 Months. Unit-4; 33 Months. Unit-5; 33 Months. Unit-6; 36 Months; Engineering: 0-10 Months Dispatch: 31-33 Months Receipt at site: 32-34 Months Erection & Ready for Commissioning: 33-36 Months (6th -7th) 5 units by 36 Months. Unit-7; 36 Months. Unit-8; 36 Months. Unit-9; 36 Months. Unit-10; 36 Months. | Completion Schedule of the units shall as per Provisions of Bidding Documents. |