| Sl. No | Clause Ref. No. | Existing provision | Amended as |
| --- | --- | --- | --- |
|  | ITB 24.1 (c), Section-III, BDS, Vol.-1 | The Time for Completion shall be as under: Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of. Package OPGW-04: OPGW Supply & Installation Package for various transmission lines pan India locations under BULK IMPLMENTATION (Supply + Erection) for OPGW and Communication Equipment. Specification No: CC/NT/W-OPGW/DOM/A00/24/13348; 24 months (Twenty-Four Months). Note: Instructions for manufacturing clearance and actual delivery destination shall be informed to the contractor during execution stage. | (1) For execution of works under the scope of this package in the event of emergence of requirement, one or more Lot wise Implementation Instructions shall be provided by Employer to contractor within 24 Months from the date of issuance of Notification of Award. (2) Lot wise Implementation Instructions shall consist of manufacturing clearance, details of transmission line/substation such as voltage level, link name, route length and actual delivery destination for implementation with OPGW based communication system. (3) Bill of Quantities for OPGW works i.e. BoQ (tentative) based on the BPS shall be issued link-wise to the contractor along with Lot wise Implementation Instructions. (4) Lot wise Implementation Instruction may envisage requirements for one or more OPGW link (from FODP to FODP) for transmission lines. (5) Time for Completion for establishment of each OPGW Link under the scope of this package shall be 12 months from date of issuance of its Lot wise Implementation Instructions. (6) In case of urgency expressed by employer, the above Time for Completion for OPGW Link, if any, may be reduced and shall be finalised with contractor for implementation of works accordingly. However, Time for Completion for the purpose of LD for such OPGW Link shall be 12 months from date of issuance of its Implementation Instructions. Employer shall provide the priority of OPGW Link within the Implementation Instruction. All possible efforts to be made by contractor for timely completion. |
|  | GCC 1.1(e) & 1.1(ee), SCC, Section-V, Vol.-1 | Supplementing Sub-Clause GCC 1.1(e) & 1.1 (ee) The Time for Completion shall be as under : Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of. Package OPGW-04: OPGW Supply & Installation Package for various transmission lines pan India locations under BULK IMPLMENTATION (Supply + Erection) for OPGW and Communication Equipment. Specification No: CC/NT/W-OPGW/DOM/A00/24/13348; 24 months (Twenty-Four Months). Note: Instructions for manufacturing clearance and actual delivery destination shall be informed to the contractor during execution stage. | Supplementing Sub-Clause GCC 1.1(e) & 1.1 (ee) (1) For execution of works under the scope of this package in the event of emergence of requirement, one or more Lot wise Implementation Instructions shall be provided by Employer to contractor within 24 Months from the date of issuance of Notification of Award. (2) Lot wise Implementation Instructions shall consist of manufacturing clearance, details of transmission line/substation such as voltage level, link name, route length and actual delivery destination for implementation with OPGW based communication system. (3) Bill of Quantities for OPGW works i.e. BoQ (tentative) based on the BPS shall be issued link-wise to the contractor along with Lot wise Implementation Instructions. (4) Lot wise Implementation Instruction may envisage requirements for one or more OPGW link (from FODP to FODP) for transmission lines. (5) Time for Completion for establishment of each OPGW Link under the scope of this package shall be 12 months from date of issuance of its Lot wise Implementation Instructions. (6) In case of urgency expressed by employer, the above Time for Completion for OPGW Link, if any, may be reduced and shall be finalised with contractor for implementation of works accordingly. However, Time for Completion for the purpose of LD for such OPGW Link shall be 12 months from date of issuance of its Implementation Instructions. Employer shall provide the priority of OPGW Link within the Implementation Instruction. All possible efforts to be made by contractor for timely completion. |
|  | GCC 21.1, SCC, Section-V, Vol.-1 | Supplementing the Clause GCC 21.1 with the following: The Time for Completion shall be as under : Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of. Package OPGW-04: OPGW Supply & Installation Package for various transmission lines pan India locations under BULK IMPLMENTATION (Supply + Erection) for OPGW and Communication Equipment. Specification No: CC/NT/W-OPGW/DOM/A00/24/13348; 24 months (Twenty-Four Months). Note: Instructions for manufacturing clearance and actual delivery destination shall be informed to the contractor during execution stage. | Supplementing the Clause GCC 21.1 with the following: (1) For execution of works under the scope of this package in the event of emergence of requirement, one or more Lot wise Implementation Instructions shall be provided by Employer to contractor within 24 Months from the date of issuance of Notification of Award. (2) Lot wise Implementation Instructions shall consist of manufacturing clearance, details of transmission line/substation such as voltage level, link name, route length and actual delivery destination for implementation with OPGW based communication system. (3) Bill of Quantities for OPGW works i.e. BoQ (tentative) based on the BPS shall be issued link-wise to the contractor along with Lot wise Implementation Instructions. (4) Lot wise Implementation Instruction may envisage requirements for one or more OPGW link (from FODP to FODP) for transmission lines. (5) Time for Completion for establishment of each OPGW Link under the scope of this package shall be 12 months from date of issuance of its Lot wise Implementation Instructions. (6) In case of urgency expressed by employer, the above Time for Completion for OPGW Link, if any, may be reduced and shall be finalised with contractor for implementation of works accordingly. However, Time for Completion for the purpose of LD for such OPGW Link shall be 12 months from date of issuance of its Implementation Instructions. Employer shall provide the priority of OPGW Link within the Implementation Instruction. All possible efforts to be made by contractor for timely completion. (7) Liquidated Damages as per GCC Clause 21.0 shall be governed OPGW link-wise. |
|  | First para, Appendix-4 (TIME SCHEDULE), Section-VI, Vol.-1 | 1. The Project Completion Schedule shall be as follows: Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of. Package OPGW-04: OPGW Supply & Installation Package for various transmission lines pan India locations under BULK IMPLMENTATION (Supply + Erection) for OPGW and Communication Equipment. Specification No: CC/NT/W-OPGW/DOM/A00/24/13348; 24 months (Twenty-Four Months). Note: Instructions for manufacturing clearance and actual delivery destination shall be informed to the contractor during execution stage. 1.1 The activity(ies) under the Contractor’s programme for Project Completion shall be in the form of a master network (MNW) and shall identify the various activities like design, engineering, manufacturing, supply, installation, factory testing, transportation to site, site testing and commissioning, trial operation and Taking Over etc. of the Facilities or specific part thereof (where specific parts are specified in SCC). The network shall conform to the above Project Completion Schedule. This master network will be discussed and agreed before Award in line with above, engineering drawing and data submission schedule shall also be discussed and finalised before Award. Liquidated damages for delay in successful Completion of the Facilities or specific part thereof (where specific parts are specified in SCC) and Operational Acceptance at rates specified in Clause 21 of GCC shall be applicable beyond the date specified above. | 1. The Project Completion Schedule shall be as follows: (1) For execution of works under the scope of this package in the event of emergence of requirement, one or more Lot wise Implementation Instructions shall be provided by Employer to contractor within 24 Months from the date of issuance of Notification of Award. (2) Lot wise Implementation Instructions shall consist of manufacturing clearance, details of transmission line/substation such as voltage level, link name, route length and actual delivery destination for implementation with OPGW based communication system. (3) Bill of Quantities for OPGW works i.e. BoQ (tentative) based on the BPS shall be issued link-wise to the contractor along with Lot wise Implementation Instructions. (4) Lot wise Implementation Instruction may envisage requirements for one or more OPGW link (from FODP to FODP) for transmission lines. (5) Time for Completion for establishment of each OPGW Link under the scope of this package shall be 12 months from date of issuance of its Lot wise Implementation Instructions. (6) In case of urgency expressed by employer, the above Time for Completion for OPGW Link, if any, may be reduced and shall be finalised with contractor for implementation of works accordingly. However, Time for Completion for the purpose of LD for such OPGW Link shall be 12 months from date of issuance of its Implementation Instructions. Employer shall provide the priority of OPGW Link within the Implementation Instruction. All possible efforts to be made by contractor for timely completion. 1.1 The activity(ies) under the Contractor’s programme for Project Completion shall be in the form of a master network (MNW) and shall identify the various activities like design, engineering, manufacturing, supply, installation, factory testing, transportation to site, site testing and commissioning, trial operation and Taking Over etc. of the Facilities or specific part thereof (where specific parts are specified in SCC). The network shall conform to the above Project Completion Schedule. This master network will be discussed and agreed before issuance of respective Lot wise Implementation Instruction(s) in line with above, engineering drawing and data submission schedule shall also be discussed and finalised before issuance of respective Lot wise Implementation Instruction(s). Liquidated damages for delay in successful Completion of the Facilities or specific part thereof (where specific parts are specified in SCC) and Operational Acceptance at rates specified in Clause 21 of GCC shall be applicable OPGW Link wise beyond the period specified in its Implementation Instructions issued for such OPGW Link. |
|  | GCC 1.1 (n) | “Effective Date” means the date of Notification of Award from which the Time for Completion shall be determined. | Replace GCC 1.1 (n) with the following: “Effective Date” means the date of Lot wise Implementation Instruction(s) from which the Time for Completion for respective Lot wise Implementation Instruction(s) shall be determined. |
|  | GCC 1.1 (ff) |  | Add Sub-Clause GCC 1.1(ff) “Implementation Instruction” means the official notice issued from time to time by the Employer notifying the Contractor for execution of works in Lot(s) based on requirement. Such Lot wise Implementation Instruction shall become the integral part of the Contract Agreement. |
|  | GCC 1.1 (p) | “Facilities” means the Plant and Equipment to be supplied and installed, as well as all the Installation Services to be carried out by the Contractor under the Contract. | Replace GCC 1.1 (p) with the following: “Facilities” means the Plant and Equipment to be supplied and installed, as well as all the Installation Services to be carried out by the Contractor for an OPGW link i.e. from FODP to FODP under the Lot wise Implementation Instruction issued under the Contract. |
|  | Form 4(a), 4(b) Form of ‘Notification of Award of Contract’, section-VI, Vol-I of Bidding Documents | The schedule for Taking Over/Completion of Facilities by the Employer upon successful completion of the …… (insert name of Package alongwith name of the Project) …. shall be … (indicate the completion schedule) …. months from the date of issue of this Notification of Award for all contractual purposes. | The schedule for Taking Over/Completion of Facilities by the Employer upon successful completion of the …… (insert name of Package alongwith name of the Project) …. shall be as per following for all contractual purposes. (1) For execution of works under the scope of this package in the event of emergence of requirement, one or more Lot wise Implementation Instructions shall be provided by Employer to contractor within 24 Months from the date of issuance of Notification of Award. (2) Lot wise Implementation Instructions shall consist of manufacturing clearance, details of transmission line/substation such as voltage level, link name, route length and actual delivery destination for implementation with OPGW based communication system. (3) Bill of Quantities for OPGW works i.e. BoQ (tentative) based on the BPS shall be issued link-wise to the contractor along with Lot wise Implementation Instructions. (4) Lot wise Implementation Instruction may envisage requirements for one or more OPGW link (from FODP to FODP) for transmission lines. (5) Time for Completion for establishment of each OPGW Link under the scope of this package shall be 12 months from date of issuance of its Lot wise Implementation Instructions. (6) In case of urgency expressed by employer, the above Time for Completion for OPGW Link, if any, may be reduced and shall be finalised with contractor for implementation of works accordingly. However, Time for Completion for the purpose of LD for such OPGW Link shall be 12 months from date of issuance of its Implementation Instructions. Employer shall provide the priority of OPGW Link within the Implementation Instruction. All possible efforts to be made by contractor for timely completion. |
|  | Samples Forms and Procedure, Terms and Procedures of Payment, Appendix 1, Clause 1.1 D | 1.1 Supply of Goods Portion: ………………………………….. ………………………………….. D. Final Payment Balance 15% (Fifteen Percent) of the Total Ex-Works Price Component (including Spares) shall be paid as indicated below: i) 7.5% (Seven and Half percent) of the Total Ex-Works Price Component (including Spares) on completion of successful testing and commissioning of each node. ii) 7.5% (Seven and Half percent) of the Total Ex-Works Price Component (including Spares) on completion of successful commissioning of the entire system and issuance of Taking Over Certificate (TOC). …………………………………….. ……………………………………. | 1.1 Supply of Goods Portion: ………………………………….. ………………………………….. D. Final Payment Balance 15% (Fifteen Percent) of the Total Ex-Works Price Component (including Spares) shall be paid as indicated below: i) 7.5% (Seven and Half percent) of the Total Ex-Works Price Component (including Spares) on completion of successful testing and commissioning of each OPGW link (from FODP to FODP). ii) 7.5% (Seven and Half percent) of the Total Ex-Works Price Component (including Spares) on completion of successful commissioning of all the OPGW link(s) in Lot wise Implementation Instruction and issuance of Taking Over Certificate (TOC). …………………………………….. ……………………………………. |
|  | First Envelope Bid Form & Attachment, Volume-3 | In view of the above, existing MS excel file (namely ‘First_Envelope_and_Bid_Forms OPGW-04’) containing 1st Envelope Bid form & Attachments is stand replaced with revised excel file (namely ‘First_Envelope_and_Bid_Forms OPGW-04_rev01’), which is attached herewith. Bidder is requested to consider revised excel file only. |  |

***