SECTION – V

SPECIAL CONDITIONS OF CONTRACT (SCC)

Dragging, packing, loading, transportation, unloading and dragging to final position on plinth including transit cum erection insurance of 765KV 80MVAr 1 Ph ABB make cold spare Reactor from POWERGRID 765KV Bhadla-2 Substation, NR-1 Rajasthan to 765KV Srikakulam Substation SR-1, Andhra Pradesh

SPECIAL CONDITIONS OF CONTRACT (SCC)

The following bid specific data for the Goods/Services to be procured shall amend and/or supplement the provisions in the General Conditions of Contract (GCC)

| Sl. No. | GCC Clause Ref. No. | Amendment/Supplement to GCC |
| --- | --- | --- |
|  | GCC 1.1(o) & (w) | Supplementing Sub-Clause GCC 1.1(o) The Owner/Purchser/Employer is: Power Grid Corporation of India Limited, Northern Region Transmission System–I, Regional Headquarter, SCO Bay No. 5 to 10, Sector 16A, Faridabad-121002, Haryana Kind Attn.: Ch. Mgr.(C&M) Telephone Nos.: +91-(0)011-26867148 Mobile: +91-9910081391, 70270001979 Email Address: ashwani.mishra@powergrid.in sandeep.singh@powergrid.in |
|  | GCC 1.1 (e) | Supplementing Sub-Clause GCC 1.1(ee) Time for Completion: Sl. No.; Activities; Duration from the effective date of Contract. 1; Dragging, packing, loading, transportation, unloading and dragging to final position on plinth including transit cum erection insurance of 765KV 80MVAr 1 Ph ABB make cold spare Reactor from POWERGRID 765KV Bhadla-2 Substation, NR-1 Rajasthan to 765KV Srikakulam Substation SR-1, Andhra Pradesh; 60 (Thirty) Days. |
|  | General | Addition/ Deletion / Substitutions to the different section of the Bidding Documents - The words ‘Bid’ or ‘Offer’ shall have the same meaning as the word ‘Tender’. These words have been used interchangeably and shall carry the same meaning. - The words ‘Bidding Documents’ or ‘NIT Documents’ shall have the same meaning as the words ‘Tender Documents’. These words / expressions have been used interchangeably and shall carry the same meaning. The word ‘Notice Inviting Tender’ shall have the same meaning as the word ‘Invitation for Bids’. These works have been used interchangeably and shall carry the same meaning. |
|  | GCC 2.9 | Deleted as Not Applicable. |
|  | GCC 3.6 | Add new GCC clause 3.6 The work shall be strictly carried out as per POWERGRID’s Technical Specifications for the subject package & as per terms & conditions mentioned in the bidding documents inter-alia including drawings provided by POWERGRID, if any, to the successful Bidder. The Contractor at his cost shall arrange, secure and maintain all insurance as may be pertinent to the works and obligatory in terms of law against all perils and the responsibility to maintain adequate insurance coverage at all time during the period of contract shall be of the Contractor alone. The Contractor’s failure in this regard shall not relieve him of any of his contractual responsibilities and obligations. The perils required to be covered under the insurance shall include all risks, but not limited to fire and allied risks, miscellaneous accidents, workmen compensation risks, loss or damage in transit, theft, pilferage, riot and strikes and malicious damages, civil commotions, weather conditions, accidents of all kinds et. The Contractor shall be responsible for the safety and security of employees of the Contractor and his sub-contractors throughout execution of the works. All costs on account of insurance liabilities covered under the Contract will be on Contractor’s account and will be included in the Contract Price. Materials and components not specifically stated in the various documents forming part of the Contract but which are necessary for completion of works shall be deemed to be included in the scope. All such materials and components shall be arranged and transported by the Contractor at his cost and expense. |
|  | GCC 4 | Replace the para with the following: 4. Time for Commencement and Completion 4.1 Time for Completion is the essence of Contract. The Contractor shall commence work on the Facilities from the Effective Date of Contract and without prejudice to GCC Sub-Clause 21.2 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified in the corresponding Appendix – 4 (Time Schedule) to the Contract Agreement. 4.2 The Contractor shall attain Completion of the Facilities (or of a part where a separate time for Completion of such part is specified in the Contract) within the time stated under Time for Completion or within such extended time to which the Contractor shall be entitled under GCC Clause 34 hereof |
|  | GCC 9.2 | Stands deleted as Advance is not admissible under the subject package |
|  | GCC 9.3.1 | Replace Sub-Clause GCC 9.3.1 The Supplier shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten Percent (10%) of the Contract Price, with a validity upto ninety (90) days beyond the Defect Liability Period. The same shall be extended by the Supplier time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. Apart from the Supplier‟s performance security, the Supplier shall be required to arrange additional performance securities, as specified in SCC, within twenty-eight (28) days of the notification of award in favour of the Purchaser in the form acceptable to the Purchaser. |
|  | GCC 9.3.1.2 (b) | Replace the Clause reference GCC 9.3.1.1 appearing in second line with Clause GCC 9.3.1.2(a) |
|  | GCC 9.3.1.2 (d) | Replace Sub-Clause GCC 9.3.1.2(d) In case the Contractor fails to submit the performance security within 90 days of the Notification of Award, the Employer, without prejudice to any other rights or remedies it may possess under the Contract, may consider the bid submitted by the Contractor in future packages as non-responsive in line with ITB 13.6 and/or may terminate the Contract forthwith pursuant to GCC Clause 36. |
|  | GCC 9.3.2 | Replace the existing provision with the following: The performance security shall, at the contractor’s option, be in the form of a crossed bank draft/pay order /banker certified cheque in favour of Employer as stipulated in SCC or in the Form of unconditional Bank Guarantee attached hereto in the Section VI - Sample Forms and Procedures. Alternatively, if performance security is to be submitted in favor of POWERGRID, the same can be submitted as online payment through POWERGRID ONLINE PAYMENT UTILITY- https://epay.powergrid.in, a link of which is provided on the POWERGRID website www.powergridindia.com. While making online payment towards performance security, the bidder shall choose Segment as “Suppliers” and fill in details as follows: Payment Category; Performance Security. Sub-category; Performance Security Payment–NR1. Name of Depositor; Name of the Contractor. Vendor Code, if applicable; POWERGRID vendor code of the Contractor. Payment Remarks; Performance Security for Dragging, packing, loading, transportation, unloading and dragging to final position on plinth including transit cum erection insurance of 765KV 80MVAr 1 Ph ABB make cold spare Reactor from POWERGRID 765KV Bhadla-2 Substation, NR-1 Rajasthan to 765KV Srikakulam Substation SR-1, Andhra Pradesh. The copy of ‘Online Payment Acknowledgement – Suppliers’ generated subsequent to the payment shall be submitted by the Contractor. The online payment facility shall be for payment in Indian Rupees only. No interest shall be payable by the Employer/Owner on the Performance Security.. |
|  | GCC 9.3.5 | Add the new GCC sub-clause 9.3.5 as per following: During execution of contract the Contractor, after submission of Performance Security in form of a crossed bank draft/pay order /banker certified cheque, may opt to furnish the Performance Security in form of bank guarantee for the same amount and as per same terms of the Contract. On acceptance by the Employer of Performance Security submitted in the form of Bank Guarantee following receipt of confirmation from the issuing Bank, the said amount shall be refunded. |
|  | GCC 9.4 | Supplementing GCC Clause 9.4 with the following The contractor has the option to submit BG (towards Advance Payment Security and Performance Security) using SFMS Platform. The Account details of POWERGRID for the purpose of Bank Guarantee (towards Advance Payment Security and Performance Security) to be issued using SFMS Platform are as given below: Name of the Bank and Address; IFSC Code; POWERGRID Current A/c No.. State Bank of India, 4th & 5th Floor, Parsvnath Capital Tower, Bhai Veer Singh Marg, Gole Market, New Delhi - 110001; SBIN0017313; 10813608670. ICICI Bank, Unit No. 01, Solitaire Plaza, DLF Phase III, M.G. Road, Gurugram; ICIC0002451; 000705002702. Note: Any one of the above account details can be used for the issuance of Bank Guarantee using SFMS Platform. In case of Bank Guarantee (towards Advance Payment Security and Performance Security) verification through SFMS facility of ICICI Bank, the applicant has to provide a unique identifier of POWERGRID to the issuing bank. This unique identifier needs to be incorporated by the issuing bank in Field 7037of the IFIN 760 COV/ IFIN 767 COV while transmitting these messages to the Beneficiary Bank through SFMS. The unique identifier of POWERGRID is PGCIL50948846. In addition to the above, the Bank Guarantee (towards Advance Payment Security and Performance Security) should be submitted in the Physical form as specified in GCC Clause 9. |
|  | GCC 10.7 | Supplement GCC Clause 10.7 with the following: All charges on account of GST on materials obtained for the works from any source shall be borne by the Contractor. The liability of the Employer shall be limited to reimbursement of GST on the supply of goods/services made by the Contractor. The Input Tax Credit (ITC) available, if any, under GST as per the relevant Government laws wherever applicable has, however, been taken into account by the Contractor. |
|  | GCC 17.1 | Replace the existing GCC clause 17.1 with the following: Subject to GCC Sub-Clause 10.2, the Contractor shall manufacture or procure and transport all the Plant and Equipment in an expeditious and orderly manner to the Site. |
|  | GCC 18.1.3 | Replace GCC 18.1.3 (a) with following: - The Contractor shall provide and employ on the Site in the installation of the Facilities such skilled, semi-skilled and unskilled labor as is necessary for the proper and timely execution of the Contract. Labour having “Recognition of Prior Learning”(RPL) Certification (under Pradhan Mantri Kaushal Vikas Yojana(PMKVY)) can also be employed by the Contractor. The Contractor is encouraged to use local labor preferably from weaker sections of society particularly SC & ST persons, that has the necessary skills. |
|  | GCC 18.3.1.4 (a) | Replace GCC 18.3.1.4 (a) with the following: (a) Employee’s Compensation Act 1923: The Act provides for compensation in case of injury by accident arising out of and during the course of employment. |
|  | GCC 18.3.3 | Replace GCC 18.3.3. with the following: Appendix-II to SCC. |
|  | GCC 19.1 | Supplementing Sub-Clause GCC 19.1 The various field and laboratory tests involved as per the Quality Plan/ Technical Specifications/ directions of Engineer-in-charge are to be carried out by the successful Bidder (contractor) at his own cost and no additional payment shall be considered on this account. The Bidders should take into account his aspect while submitting their offers. |
|  | GCC 21 | Replace the existing provision with the following: 21.1 The contractor gurantees that it shall attain completion of the facilities (or a part for which a separate time for completion is specified in the SCC) with in the time for completion specified in the SCC pursuant to GCC sub clause 4.2 or within such extended time to which the contractor supplier shall be entitled under GCC clause 34 hereof. 21.2 If the contractor fails to comply with the time for completion in accordance with clause GCC 21 for the whole of the facilities (or a part for which a separate time of completion is agreed) then the contractor shall pay to the employer a sum equivalent to 0.05% (Zero point Zero Five percent) of the contract price payable thereon for the whole of the facilities ( or a part for which a separate time of completion is agreed) as liquidated damages for such default and not as penalty, without prejudice to the purchasers other remedies under the contract, for each Day which shall elapse between the relevant time for completion and the date stated in the Taking over certificate of the whiole of the works ( or a part for which separate time for completion is agreed) subject to the limit of Five Percent (5%) of contract price payable thereon for the whole of the facilities (or a part for which separate time of completion is agreed). The parties agree that the sum specified above is not a penalty but a genuine preestimate of the loss/damage which will be suffered by the purchaser for default on the part of the contractor and said amount will be payable without proof of actual loss or damage caused by such default. The purchaser may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the contractor. The payment or deduction of such damages shall not relieve the contractor from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract. 21.3 No Bonus will be given for earlier completion of the delivery of Goods. |
|  | GCC 22.1 | Replace GCC clause 22.1 Defect liability period shall be Nil from the date of operational acceptance/issuance of taking over certificate (TOC) pertaining to workmanship defect of erection |
|  | GCC 23 | Supplementing GCC clause 23 Deleted as Liquidated Damages for Non-Performance of Equipment are not applicable. Bidder shall confirm the guaranteed performance or efficiency of the equipments in response to the Technical Specifications. |
|  | GCC 30.1(a) (I) (ii) | Replace the existing Provision GCC 28.1(a) (I) (ii) as below: Transit Insurance Policy for indigenous equipment Similarly, Transit Insurance Policy shall be taken wherein only inland transit is involved for the movement of Plant and Equipment including mandatory Spares supplied from within India. The policy shall cover movement of Plant and Equipment including mandatory Spares from the manufacturer’s works to the project’s warehouse at final destination site. Inland Transit Clause (ITC) ‘A’ along with Strike Riots & Civil Commotion (SRCC) extension cover shall be taken. |
|  | GCC Clause 33.3 | Replace GCC Clause 33.3 with the following: Quantity Variation: During execution of the contract, POWERGRID reserves the right to increase or decrease the quantity of individual item upto any extent. The overall limit of Quantity variation in the contract shall be upto (+/-) 25% (Twenty Five Percent) of the Contract Price and there will not be any variation limit for individual items of the Contract. Thus, individual items may vary up to any extent. In case the overall contract price varies by more than above limit, all such items where executed quantity has varied by more than above quantity variation limit will be identified. The rates for all such items for the quantity in variance of above limit shall be determined as per Clause No. 33.0 of GCC. |
|  | General | Risk and Cost During the period of construction and also during defect liability period, if the contractor fails to rectify any defect pointed out to him, the same shall be got done by POWERGRID at the risk and cost of contractor and recovered from the Contract Performance Guarantee or any other amount payable to the Contractor. |
|  | General | Price Basis: All prices shall remain firm till the entire duration of contract, or any extension thereof, and no price variation shall be payable. |
|  | General | STATUTORY REQUIREMENTS: All statutory requirements interalia including requisite insurances and Labour license (if applicable) as per Govt. of India laws, by-laws etc shall be complied by the contractor during the currency of the contract.. |
|  | GCC 39.6 | Replace the existing Provision GCC 39.6 as below: 39.6 Notwithstanding the above, in case the contractor is a Central Public Sector Enterprise (CPSE)/Government Organization or Department then the dispute or difference between the Employer and the Contractor shall be settled through Administrative Mechanism for Resolution of CPSEs Disputes (AMRCD) as mentioned in DPE OM No. 4(1)/2013-DPE(GM)/FTS-1835 dated 22.05.2018. The decision through AMRCD will be final and binding on all the concerned. 39.7 During settlement of disputes and arbitration proceedings, both parties shall be obliged to carry out their respective obligations under the contract. |
|  | Appendix-I to SCC | Enclosed herewith |
|  | Appendix-II to SCC | Enclosed herewith |

----- End of Section-V (SCC) ----