## Clarification Sheet_21Mar2023
Clarification No.-III dated 27/03/2023 to the Bidding Documents for Substation Extension Package SS-106 for (a) Extn. of 220kV Bhuj PS, (b) Extn. of 400/220kV Satna (PG) S/S, (c) Extn. of 220kV Panchkula (Barwala) (PG) S/S, (d) Extn. of 400/220kV Ludhiana (PG) S/S, (e) Extn. of 400/220kV Moga (PG) S/S, (f) Extn. of 220kV Bikaner-II PS and (g) Extn. of 400kV Kurnool New S/S under various schemes; Spec. No.: CC/NT/W-AIS/DOM/A06/23/00409
SN | Substation | Clause No. | Description | Bidder's Queries | Powergrid response
Extension of 220 kV Bhuj Substation:
|  | - | - | Bhuj Substation–Foundation Bolt Quantity in BPS is missing. Kindly Provide the Quantity. | Foundations of Isolator, CT, CVT, LA and BPI are existing. Only Foundation of CB is to be construted. Foundation bolt of CB is part of CB structure which is in contractor's scope. Bidder may quote as per BPS.
Extension of 400/220 kV Satna (PG) Substation:
|  | - | - | In Rev 1 Amendment, Annexure S is not attached. Please provide the details of SAS Upgradation of 400 KV Satna Substation. | Refer Amenment No II
|  | - | - | 400 KV Satna Substation: Bus Bar Protection Augmentation Line item is missing in BPS. Please advise in which line item its prices should be covered. | Associated Clause at Section-Project to be referred. Supply of minor components may be included in respective Service item in BPS for Augmentation of 400kV&220kV Bus Bar Protection system (Aug. 500MVA 400/220kV ICT-4 Satna (PG)) Bidder to quote accordingly.
|  | - | - | Satna Substation – We understand all existing BCU in Satna Substation in working condition. So Its integration with SAS system would be compatible. Any assistance required for BCU Integration , shall be provided by PGCIL. | See ammendment-I already published on 17 March 2023.
|  | - | - | In case ICD files required , Shall be Provided by PGCIL. | Confirmed.
|  | - | - | Satna Substation site visit is required to consider input for SAS upgradation work as mentioned in Amendment | Query is not clear.
Extension of 400/220 kV Satna (PG) Substation:
|  | - | - | In S.No.1 of Amendment No-I dated 17/03/2023, it is mentioned of “The detailed scope of SAS upgradation is attached as Annexure-S” but it is not attached with the amendment. Please provide the same. | Refer Amenment No II