Annexure-1 to SCC

TERMS AND PROCEDURES OF PAYMENT

In accordance with the provisions of GCC Clause 8 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules.  Payments will be made in the currencies quoted by the Bidder unless otherwise agreed between the parties. The Contractor may make applications for payment in respect of part deliveries as work proceeds.

1.	TERMS OF PAYMENT

# In addition to the Conditions stipulated under GCC Clause 8, the following terms & Conditions will apply. Any payment under the Contract shall be released only after completion of following activities

1.2	Supply of Services Portion: Price Component for Installation (including Civil Works)

# Any payment under the Contract shall be released only after completion of following activities

- Unconditional acceptance of Letter of award of Rate Contract.

- Submission of Performance Security or Confirmation of deduction of Security Deposit from running Bills

A.	Survey

Payment for survey shall be paid on pro-rata basis on completion of survey and approval of the same by the Employer.

B	Progressive Payment

B1.	Eighty Percent  (80%) (excluding the price component for survey) shall be paid on completion of the each of the items of Erection activity and on successful completion of quality check point involved in Installation, submission of the details of items, components, raw materials, services etc. procured/availed from MSEs, if any, for the preceding 6 months, in respect of all the contracts in the respective executing Region of POWERGRID as per format enclosed at Section VI, Forms, Volume-I of the bidding documents and certification by Employer’s representative and on submission of GST invoice.

B2.	Ten percent (10%) of total Installation price component excluding the price component for survey) shall be paid in three equal parts, each on physical construction of 1/3rd of the Transmission Line section including liquidation of defects/deficiencies on the line section and certification of the same by Employer’s representative and on submission of GST invoice.

C.	Final Payment

C1.	5% (five percent) of the erection price component (excluding the price component for survey) shall be paid after successful commissioning of the transmission line.

C2.	5% (five percent) of the erection price component (excluding the price component for survey) shall be paid after issuance of Taking Over Certificate.

However, in case, for any reason solely attributable to the Employer, the commissioning of line is delayed beyond 120 days of successful completion of final checking and testing of line for the purpose of commissioning as defined in Technical Specification, Volume-II of the Bidding Documents, the balance 10% payment shall be released against an unconditional & irrevocable bank guarantee of equivalent amount initially valid till 6 months from the readiness of transmission line for commissioning and charging at rated voltage, to be extended till 90 days beyond actual commissioning & taking over.

1.2.1	‘Commissioning’ for the purpose of payments shall mean satisfactory completion of all supplies, erection, commissioning checks and successful completion of all site tests and charging of the transmission line at rated voltage as per the Contract and to the satisfaction/approval of the Employer.

1.3	Training Charges- Not applicable.

Training Charges shall be paid on successful completion of training and on approval of the same by the Employer and on furnishing GST invoice for the Training Charges.

1.4	Payment towards Price adjustment

Any variation in Contract price due to price adjustment provision of Appendix-2 shall be effected on presentation of debit note/credit note, as prescribed under the GST law, supported by calculations as per formulae specified therein along with documentary evidence for different indices applicable for Price Adjustment.

1.5.1	Any increase in Contract price due to price adjustment provision shall be payable as follows:

Supply of Services Portion:

90% (ninety percent) of the price adjustment amount for the respective billing period shall be paid after certification by Employer’s representative for quantum of work done in the said billing period and issuance of Debit Note, as prescribed under the GST law, by the Contractor. Balance 10% (ten percent) of the price adjustment amount shall be paid alongwith the final payment.

Any interest on GST payable due to increase in Contract price due to price adjustment shall be to the Contractor’s account and Employer shall not reimburse any amount on this account.

1.5.2	For any reduction in Contract Price due to price adjustment provisions the Contractor shall issue ‘Credit note’, as prescribed under the GST law.  Further, the reduction in Contract Price shall be effected by recovering 100% of the reduction amount along with applicable GST, if any charged earlier, from Contractor’s invoices falling immediately due for payment or any other payments.

1.5.3	In case negative PV invoice is submitted by the contractor after the specified timeline as per the contract, interest shall be charged on said amount less provisional amount withheld on this account, if any, for the period elapsed beyond the specified timeline and date of submission of PV bill by the contractor. Rate of Interest shall be equal to one year MCLR rate [One Year Tenor rate p.a] published by State Bank of India as applicable on the last date of specified timeline. Further, the amount of interest worked out on negative PV shall be recovered from Contractor’s invoices falling immediately due for payment or any other payments under the contract.

1.6	Payment towards Taxes and Duties

Taxes and duties applicable as per Indian Tax laws, concerning Supply of Goods and Services in respect of transaction between the Employer and the Contractor, shall be reimbursed by the Employer as follows:

(a)  In case of Installation, the GST shall be reimbursed along with Progressive payment on completion of Erection activity.

(b)  	100% GST reimbursable on account of increase in Contract price due to price adjustment shall be reimbursed along with the 90% payment of the Price adjustment amount.

All GST payment shall be against GST invoices/debit notes raised by the Contractor as specified under the GST Act and related Rules, Notifications, etc as notified by the Government in this regard. In the event that the Contractor fails to provide the invoice/debit note in the form and manner prescribed under the GST Act and Rules, the Employer shall not be liable to make any payment against such invoice/debit note. Payment towards taxes & duties shall be released by the Employer directly to the Contractor.

2.	PAYMENT PROCEDURES

2.1	Method of Payment

The Employer shall make payments promptly within thirty (30) days of submission of an invoice/claim by the Contractor, complete in all respects and supported by the requisite documents and fulfillment of stipulated conditions, if any.

All payments to be made directly to the Contractor shall be made by the Employer though electronic payment mechanism (e-payment) for which necessary details shall be tied up during execution of the Contract. However, a request for payment to be released through cheque shall be considered on case to case basis and merit of the same.

2.1.1	POWERGRID is registered on TReDS (Trade Receivables Discounting System) platforms namely i.e. RXIL (Receivable Exchange of India Limited ), M1-xchange (Mynd Solutions Private Limited), Invoicemart (A.TReDS Limited) and C2TReDS (C2FO Factoring Solutions Private Limited) and the facility of the same may be availed by Micro, Small and Medium Enterprises (MSMEs) for payment.

Note:	Pro-rata shall refer to functionally complete part(s) of the facilities, for which unit rates are identified in the contract.

2.2	Bill Tracking System

Prior to submission of bills in physical form, the Contractor shall submit its bills using POWERGRID’s Vendor Bill Tracking System as per procedure detailed herein below. Further, the Contractor may also track the status of its bills using POWERGRID’s ‘On-line Vendor Bill Tracking System’. To use this system the Contractor is required to get itself registered once online at POWERGRID’s ERP Portal with the link URL (https://etender.powergrid.in). Once registered, the Contractor   may track status of bills submitted, passed and paid by POWERGRID’s Corporate Centre and Regional Office(s) under this Contract and other Contracts awarded on it by POWERGRID by following the method detailed herein below:

- Once registered, the Contractor can log-in to POWERGRID’s Vendor Bill Tracking System (BTS) with Vendor Log-In ID and Password.

- After login as at (a) above, Contractor is required to make the entry on POWERGRID’s ERP Portal under the tab “Submit New Invoice” and shall fill all details along with the MSE status. Upon submission, a 16 digit unique BTS number will be generated and the Contractor will receive an automated e-mail forwarding the unique BTS number.

- The physical bills alongwith printed copy of e-mail received from BTS (unique BTS number) shall be submitted by the Contractor.

- On receipt of physical bill, concerned POWERGRID’s official shall online acknowledge the receipt of bill. This action will trigger an automated mail to the Contractor intimating that the physical copy of the bill has been received and is under verification / processing. However, on receipt of incomplete bill and/or non-receipt of physical bill by POWERGRID official, the incomplete bills/ digital entry in BTS (as the case may be) shall be returned to the Contractor by POWERGRID, which can be viewed under the tab “Invoice Returned”.

- The day the payment is made, a mail stating the “Bill number, net payment amount and details of the bank from where the payment has been made” will be sent to the Contractor.

- The status of Bill submitted by the Contractor can be checked through the BTS number under tab “Invoice Submitted”.

Price Variation and Quantity variation shall continue to be governed by the unit price quoted by the bidder.