Annexure-2 to SCC

PRICE ADJUSTMENT

1.0	General

1.1	Prices for work and materials covered under the scope of this Specification shall be furnished by the bidder in the manner specified in the Bid Form & Price Schedules. The bidder shall quote base prices for the installation (including civil works) price component of the equipment/materials. These price components for certain equipment/ materials, as specified, shall be subject to price adjustment to reflect changes in the cost of labour and material components as per the provisions given below:

1.2	The Price Components for tower accessories such as danger plate, number plate, phase plate, anti-climbing device, span marker, bird guards, pipe & counterpoise earthing and all other items not specifically mentioned below shall remain firm and no price adjustment shall be applicable for the price components of these items.

1.3	Other Charges viz. inland transportation, inland insurance, type test charges (if any), survey, soil investigation & painting of towers etc., shall be firm and no price variation shall be payable for these components.

2.0	Installation (including Civil Works) Price Component

The formula for calculation of the monthly price adjustments for Installation [including civil works but excluding survey, soil investigation and aviation signal for river crossing towers(if any)] price component shall be as under:

A.	Installation Price Component [including Civil Works but excluding ‘Supply & Placement of Reinforcement Steel’, ‘Concreting’, Survey, Soil investigation, item M15 (1:2:4) and Plum Concrete under Protection of tower footing, aviation requirements and installation of OPGW joint box]

ER1  	=	ER0 [0.20 + 0.24 x (A1/A0) + 0.56 x (L1/L0)] - ER0

Where,

ER1 	=	Price adjustment amount payable on Installation price component (excluding supply & placement of steel and concreting) for each billing.

ER0	=	Value of erection work done (excluding supply & placement of steel and concreting) in billing period as established by Contract.

A	=	Wholesale Price Index Number for `HSD’(Individual Commodity) (monthly)  (Base: 2011-12=100), as published by Office of Economic Advisor, Ministry of Commerce & Industry(www.eaindustry.nic.in)

L	=	Indian field labour index – namely All India average consumer price index for Industrial Workers (monthly)  (Base: 2016= 100), as published by Labour Bureau, Shimla, Government of India (www.labourbureau.nic.in).

B.	Supply and Placement of Reinforcement Steel

ER1	=	ER0 [0.20 + 0.09 x (A1/A0) + 0.04 x (L1/L0) + 0.67 x (B1/B0)] – ER0

Where,

ER1	=	Price adjustment amount payable on price components of Supply and Placement of Steel.

ER0	=	Value of supply & placement of steel in billing period as established by Contract.

A	=	Wholesale Price Index Number for `HSD’(Individual Commodity) (monthly)  (Base: 2011-12=100), as published by Office of Economic Advisor, Ministry of Commerce & Industry(www.eaindustry.nic.in).

B 	=	Wholesale Price Index Number for   `Manufacture of Basic Metals’(Group Item) (monthly)  (Base: 2011-12=100), as published by Office of Economic Advisor, Ministry of Commerce & Industry(www.eaindustry.nic.in).

L	=	Indian field labour index – namely All India average consumer price index for Industrial Workers (monthly) (Base: 2016= 100), as published by Labour Bureau, Shimla, Government of India (www.labourbureau.nic.in).

C.	Concreting

ER1	=	ER0 [0.20 + 0.22 x (A1/A0) + 0.09 x (L1/L0) + 0.29 x (B1/B0) + 0.20 x (C1/C0)] – ER0

Where,

ER1	=	Price adjustment amount payable on price components of concreting.

ER0	=	Value of concreting in billing period as established by Contract.

A	=	Wholesale Price Index Number for `HSD’(Individual Commodity) (monthly)  (Base: 2011-12=100), as published by Office of Economic Advisor, Ministry of Commerce & Industry(www.eaindustry.nic.in).

L	=	Indian field labour index – namely All India average consumer price index for Industrial Workers (monthly) (Base: 2016= 100), as published by Labour Bureau, Shimla, Government of India (www.labourbureau.nic.in).

B	=	Wholesale Price Index Number for `Manufacture of cement, lime and plaster’(Group Item) (monthly)  (Base: 2011-12=100), as published by Office of Economic Advisor, Ministry of Commerce & Industry (www.eaindustry.nic.in).

C	=	Wholesale Price Index Number for `Cutting, shaping and finishing of stone’(Group Item) (monthly) (Base: 2011-12=100), as published by Office of Economic Advisor, Ministry of Commerce & Industry(www.eaindustry.nic.in).

2.1	i)	Subscript 'o' will correspond to thirty (30) days prior to date of opening of Bids.

ii)	Subscript '1' will correspond to the month of billing.

2.2	The total price adjustment amount for Installation (including civil works) price component shall not be subject to any ceiling whatsoever.

3.0	The above price adjustment provision shall be invoked by either party subject to the following further conditions:

a)	For the purpose of Price Adjustment on Installation price component, the Billing period shall mean the billing period as per Contract time schedule i.e., the agreed Bar Chart or actual period, whichever is earlier. The Billing period for various Installation activities will be as per agreed Installation Bar Chart indicating monthly schedule of Installation activities for completion of works. However, when the Employer’s specific approval for advancement of installation activities has been obtained in such case the said advanced date shall be treated as the schedule date of installation activities for the purpose of working out the price adjustment payable.

No price increase shall be allowed beyond the original Installation dates unless specifically stated in the Time Extension Letter, if any, issued by the Employer.  The Employer will, however, be entitled to any decrease in the Contract Price which may be caused due to lower price adjustment amount in case of Installation beyond the original Installation dates. Therefore, in case of Installation beyond the original Installation dates, the liability of the Employer shall be limited to the lower of the price adjustment amount which may work out either on schedule date or actual date of Installation.

b)		In case of non-publication of applicable indices on a particular date, which happens to be the applicable date for Price Adjustment purposes, the published indices prevailing immediately prior to the particular date shall be applicable.

c)		If the Price Adjustment amount works out to be positive, the same is payable to the Contractor by the Employer and if it works out to be negative, the same is to be recovered by the Employer from the Contractor.

d)	The Contractor shall promptly submit price adjustment invoices for the supplies made/work done, positively within three (3) months from the date of shipment/ work done, whether it is positive or negative.