| Sl. No. | Clause Ref. No. | Existing provision in the Bidding Documents | Amended as |
| --- | --- | --- | --- |
|  | Volume-I: Condition of Contract |  |  |
|  | Package name | 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 6x315MVA 400/220/33kV 3-Ph Transformer & 1x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).” | 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 5x315MVA 400/220/33kV 3-Ph Transformer & 2x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).” |
|  | IFB Cl 3.0, Vol-I | POWERGRID, therefore, invites bids from eligible bidders for the following package for this Bulk Procurement on Domestic Competitive Bidding basis under secured e-procurement procedure: 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 6x 315MVA 400/220/33kV 3-Ph Transformer & 1x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).” ………………………………. | POWERGRID, therefore, invites bids from eligible bidders for the following package for this Bulk Procurement on Domestic Competitive Bidding basis under secured e-procurement procedure: 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 5x 315MVA 400/220/33kV 3-Ph Transformer & 2x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).” ………………………………. |
|  | IFB Cl 3.1, Vol-I | The broad scope of work covered under the subject package shall include: Design, Engineering, Manufacture, testing at Manufacturer’s works, supply, transportation, unloading and delivery at site, insurance & Storage. erection, testing & commissioning at site for the Transformers, including insulating oil, Bushings, all fittings, accessories including Online-Drying System (ODS), Marshaling box (MB), Cooler Control Cabinet (CCC) as applicable for each Autotransformer, foundation bolts and cables as per technical specification & BPS, for the following: - 12 nos. 500 MVA, 400/220/33kV 3- Ph Transformers - 6 nos. 315 MVA, 400/220/33kV 3- Ph Transformers - 1 No. 315 MVA, 400/132/33kV 3- Ph Transformers - Insulating oil for the above Transformers as per BPS. The above scope of work is indicative, and the detailed scope of work is given in the Technical Specification (Volume-II) of the Bidding Documents. | The broad scope of work covered under the subject package shall include: Design, Engineering, Manufacture, testing at Manufacturer’s works, supply, transportation, unloading and delivery at site, insurance & Storage. erection, testing & commissioning at site for the Transformers, including insulating oil, Bushings, all fittings, accessories including Online-Drying System (ODS), Marshaling box (MB), Cooler Control Cabinet (CCC) as applicable for each Autotransformer, foundation bolts and cables as per technical specification & BPS, for the following: - 12 nos. 500 MVA, 400/220/33kV 3- Ph Transformers - 5 nos. 315 MVA, 400/220/33kV 3- Ph Transformers - 2 No. 315 MVA, 400/132/33kV 3- Ph Transformers - Insulating oil for the above Transformers as per BPS. The above scope of work is indicative, and the detailed scope of work is given in the Technical Specification (Volume-II) of the Bidding Documents. |
|  | ITB 24.1(c) of BDS, Vol-I | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 6x 315MVA 400/220/33kV 3-Ph Transformer & 1x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).” Spec. No.: CC/NT/W-TR/DOM/A00/25/11539; Remark (Indicative Period in Months from Award). Unit-1; 21 (Twenty-One Months); Engineering: 0-8 months Dispatch: 17-18 months Rcpt at site:18-19 months Erection & Ready for Commissioning:19-21 months (1st-4th) 4 units by 21 months. Unit-2; 21 (Twenty-One Months). ………; ……………... ……………………………………………… | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 5x 315MVA 400/220/33kV 3-Ph Transformer & 2x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).” Spec. No.: CC/NT/W-TR/DOM/A00/25/11539; Remark (Indicative Period in Months from Award). Unit-1; 21 (Twenty-One Months); Engineering: 0-8 months Dispatch: 17-18 months Rcpt at site:18-19 months Erection & Ready for Commissioning:19-21 months (1st-4th) 4 units by 21 months. Unit-2; 21 (Twenty-One Months). ………; ……………... ……………………………………………… |
|  | Annexure-A (BDS), Vol-I | QR for 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 6x 315MVA 400/220/33kV 3-Ph Transformer & 1x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).”; Spec. No.: CC/NT/W-TR/DOM/A00/25/11539 ……………………………………….. | QR for 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 5x 315MVA 400/220/33kV 3-Ph Transformer & 2x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).”; Spec. No.: CC/NT/W-TR/DOM/A00/25/11539 ……………………………………….. |
|  | GCC 1.1(e) & 1.1(ee) of SCC, Vol-I | Supplementing Sub-Clause GCC 1.1(ee) The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 6x 315MVA 400/220/33kV 3-Ph Transformer & 1x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).” Spec. No.: CC/NT/W-TR/DOM/A00/25/11539; Remark (Indicative Period in Months from Award). Unit-1; 21 (Twenty-One Months); Engineering: 0-8 months Dispatch: 17-18 months Rcpt at site:18-19 months Erection & Ready for Commissioning:19-21 months (1st-4th) 4 units by 21 months. Unit-2; 21 (Twenty-One Months). ………; ……………... …………………………………………… | Supplementing Sub-Clause GCC 1.1(ee) The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 5x 315MVA 400/220/33kV 3-Ph Transformer & 2x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).” Spec. No.: CC/NT/W-TR/DOM/A00/25/11539; Remark (Indicative Period in Months from Award). Unit-1; 21 (Twenty-One Months); Engineering: 0-8 months Dispatch: 17-18 months Rcpt at site:18-19 months Erection & Ready for Commissioning:19-21 months (1st-4th) 4 units by 21 months. Unit-2; 21 (Twenty-One Months). ………; ……………... ……………………………… |
|  | GCC 21.1 of SCC, Vol-I | Supplementing the Clause GCC 21.1 with the following: Time for Completion: Sl. No.; Description; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 6x 315MVA 400/220/33kV 3-Ph Transformer & 1x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).” Spec. No.: CC/NT/W-TR/DOM/A00/25/11539; Remark (Indicative Period in Months from Award). Unit-1; 21 (Twenty-One Months); Engineering: 0-8 months Dispatch: 17-18 months Rcpt at site:18-19 months Erection & Ready for Commissioning:19-21 months (1st-4th) 4 units by 21 months. Unit-2; 21 (Twenty-One Months). ………; ……………... …………………………………………. | Supplementing the Clause GCC 21.1 with the following: Time for Completion: Sl. No.; Description; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 5x 315MVA 400/220/33kV 3-Ph Transformer & 2x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).” Spec. No.: CC/NT/W-TR/DOM/A00/25/11539; Remark (Indicative Period in Months from Award). Unit-1; 21 (Twenty-One Months); Engineering: 0-8 months Dispatch: 17-18 months Rcpt at site:18-19 months Erection & Ready for Commissioning:19-21 months (1st-4th) 4 units by 21 months. Unit-2; 21 (Twenty-One Months). ………; ……………... …………………………… |
|  | Appendix-4, Section-VI : Samples Forms and Procedures, Vol-I | - The Project Completion Schedule shall be as follows: Sl. No.; Description; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 6x 315MVA 400/220/33kV 3-Ph Transformer & 1x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).” Spec. No.: CC/NT/W-TR/DOM/A00/25/11539; Remark (Indicative Period in Months from Award). Unit-1; 21 (Twenty-One Months); Engineering: 0-8 months Dispatch: 17-18 months Rcpt at site:18-19 months Erection & Ready for Commissioning:19-21 months (1st-4th) 4 units by 21 months. Unit-2; 21 (Twenty-One Months). ………; ……………... ……………………….. | - The Project Completion Schedule shall be as follows: Sl. No.; Description; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of Following elements of the 400kV Transformer Package 4TR-15-BULK(AM) for 12 x 500 MVA 400/220/33kV 3-Ph Transformers, 5x 315MVA 400/220/33kV 3-Ph Transformer & 2x315MVA 400/132/33kV 3-Ph Transformers under “Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).” Spec. No.: CC/NT/W-TR/DOM/A00/25/11539; Remark (Indicative Period in Months from Award). Unit-1; 21 (Twenty-One Months); Engineering: 0-8 months Dispatch: 17-18 months Rcpt at site:18-19 months Erection & Ready for Commissioning:19-21 months (1st-4th) 4 units by 21 months. Unit-2; 21 (Twenty-One Months). ………; ……………... …………………. |
|  | Volume-II: Technical Specification |  |  |
|  | Section Project | SECTION PROJECT -REV-00 | SECTION PROJECT -REV-01 (ATTACHED HEREWITH) |
|  | Volume-III: Bid Forms and Price Schedule |  |  |
|  | Schedule- 1, Price schedule, Vol-III | Sr. No; Activity Desc.; MATERIAL CODE; Item Description; Unit; Qty. 01; SUPPLY; 1000004798; 500MVA, 400KV/220/33 KV, 3- phase Autotransformer excluding insulating oil; EA; 12. 02; SUPPLY; 1000013986; Insulating Oil for 500MVA, 400KV/220/33 KV, 3-phase Autotransformer; SET; 12. 03; SUPPLY; 1000001972; 315MVA, 400KV/220/33 KV, 3- phase Autotransformer excluding Insulating Oil); EA; 6. 04; SUPPLY; 1000013981; Insulating oil for 315MVA, 400KV/220/33 KV, 3-phase Autotransformer; SET; 6. 05; SUPPLY; 1000034073; 315MVA,400/132/33KV, 3-PHASE AUTOTRANSFORMER EXCLUDING INSULATING OIL; EA; 1. 06; SUPPLY; 1000034075; INSULATING OIL FOR 315MVA, 400KV/132/33 KV, 3-PHASE AUTOTRANSFORMER; SET; 1. | Sr. No; Activity Desc.; MATERIAL CODE; Item Description; Unit; Qty. 01; SUPPLY; 1000004798; 500MVA, 400KV/220/33 KV, 3- phase Autotransformer excluding insulating oil; EA; 12. 02; SUPPLY; 1000013986; Insulating Oil for 500MVA, 400KV/220/33 KV, 3-phase Autotransformer; SET; 12. 03; SUPPLY; 1000001972; 315MVA, 400KV/220/33 KV, 3- phase Autotransformer excluding Insulating Oil); EA; 5. 04; SUPPLY; 1000013981; Insulating oil for 315MVA, 400KV/220/33 KV, 3-phase Autotransformer; SET; 5. 05; SUPPLY; 1000034073; 315MVA,400/132/33KV, 3-PHASE AUTOTRANSFORMER EXCLUDING INSULATING OIL; EA; 2. 06; SUPPLY; 1000034075; INSULATING OIL FOR 315MVA, 400KV/132/33 KV, 3-PHASE AUTOTRANSFORMER; SET; 2. |
|  | Schedule- 3, Price schedule, Vol-III | Sr. No; Activity Desc.; MATERIAL CODE; Item Description; Unit; Qty. 01; SERVICE; 100000015; 500MVA, 400KV/220/33 KV, 3- phase Autotransformer excluding insulating oil; EA; 12. 02; SERVICE; 100001910; Insulating Oil for 500MVA, 400KV/220/33 KV, 3-phase Autotransformer; SET; 12. 03; SERVICE; 100000016; 315MVA, 400KV/220/33 KV, 3- phase Autotransformer excluding Insulating Oil); EA; 6. 04; SERVICE; 100001911; Insulating oil for 315MVA, 400KV/220/33 KV, 3-phase Autotransformer; SET; 6. 05; SERVICE; 100004303; 315MVA, 400/132/33 KV, 3-phase Autotransformer excluding Insulating Oil; EA; 1. 06; SERVICE; 100004304; Insulating oil for 315MVA, 400KV/132/33 KV, 3-phase Autotransformer; SET; 1. | Sr. No; Activity Desc.; MATERIAL CODE; Item Description; Unit; Qty. 01; SERVICE; 100000015; 500MVA, 400KV/220/33 KV, 3- phase Autotransformer excluding insulating oil; EA; 12. 02; SERVICE; 100001910; Insulating Oil for 500MVA, 400KV/220/33 KV, 3-phase Autotransformer; SET; 12. 03; SERVICE; 100000016; 315MVA, 400KV/220/33 KV, 3- phase Autotransformer excluding Insulating Oil); EA; 5. 04; SERVICE; 100001911; Insulating oil for 315MVA, 400KV/220/33 KV, 3-phase Autotransformer; SET; 5. 05; SERVICE; 100004303; 315MVA, 400/132/33 KV, 3-phase Autotransformer excluding Insulating Oil; EA; 2. 06; SERVICE; 100004304; Insulating oil for 315MVA, 400KV/132/33 KV, 3-phase Autotransformer; SET; 2. |
|  | Attachments to First Envelope and Bid Forms, Vol-III | In view of the above change in the package name, the Attachments to First Envelope and Bid Forms (Attachments‑8, 20, 21, 22, 25, 27, 29 & 30) have been revised and are attached herewith. Bidders are requested to consider the revised attachments for bid preparation and submission. |  |
|  | First Envelope and Bid Forms, Vol-III | In view of the above amendments, First Envelope and Bid Forms_rev01’ excel stand revised as ‘First Envelope and Bid Forms_rev02’. Note- Bidders are requested to consider the revised excel ‘First Envelope and Bid Forms_rev02’ for bid preparation/submission. It may be noted that while submitting the bid, Bidders are required to change the excel file name from ‘First Envelope and Bid Forms_rev02’ to ‘First Envelope and Bid Forms’. As per the provisions of the portal, it is mandatory to upload the excel file titled ‘First Envelope and Bid Forms’ (Bidders may refer user manuals at the portal https://etender.powergrid.in regarding submission of bid). |  |
|  | Price Schedule, Vol-III | In view of the above amendments, ‘Price_schedule’ excel stand revised as ‘Price_schedule_rev01’. Note- Bidders are requested to consider the revised excel ‘Price_schedule_rev01’ for bid preparation/submission. It may be noted that while submitting the bid, Bidders are requested to keep the excel file name as ‘Price_Schedule_rev01’. (Bidders may refer user manuals at the portal https://etender.powergrid.in regarding submission of bid). |  |