## PBQ-SS01
Clarifications-II dated 22/01/2022 for Substation Package SS01 for (i) Construction of 2 nos. of 765kV line bays at Sikar II for Sikar II – Bhadla II 765kV D/c line; (ii) Construction of 2 nos. of 765kV line bays at Bhadla II for Sikar II – Bhadla II 765kV D/c line associated with Transmission Scheme for evacuation of power from Solar Energy Zones in Rajasthan (8.1 GW) under phase II –Part E through tariff based competitive bidding (TBCB) route. Specification No: TBCB/765KV/Phase-II/Rajasthan Part-E/SS01/G7/R
S.NO. | CLAUSE REF NO. | Clause Description | Bidder's Queries | POWERGRID's Reply
1 | EXTN OF 765KV BAYS AT SIKAR-II PS | Existing Fire Fighting System | In the absence any clear input for tapping point we understand that bidder can assume tapping point shall be made available by the customer at a distance of 20 Mtr from the present scope of Line reactors. Kindly confirm. | As, Sikar-II (New) S/S is under development, the requisite detail is not yet finalised at Sikar-II S/S. The same shall be provided during detailed engineering. Bidder to quote accordingly as per BPS. No Price implication shall be admissible in this account.
2 | EXTN OF 765KV BAYS AT BHADLA-II PS | Existing Fire Fighting System | In the absence any clear input for tapping point we understand that bidder can assume tapping point shall be made available by the customer at a distance of 20 Mtr from the present scope of Line reactors. Kindly confirm. | As, Badla -II S/S is under development, the requisite detail is not yet finalised. The same shall be provided during detailed engineering. Bidder to quote accordingly as per BPS. No Price implication shall be admissible in this account.
3 | 2.1, Note-1, Page no 3 of 20 Section Project | Sikar-II PS: The spare unit of 765kV, 1x110 MVAR Reactor proposed to be provided at Sikar-II PS under ‘Transmission system strengthening for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under Phase II-Part-C’ shall be utilized as common spare for 6x110 MVAR Switchable Line Reactors | Noted, However Kindly provide us make of single phase breaker for switching the spare reactor to check the compatibility for successful implementation of spare switching scheme. | The requisite detail shall be provided during detailed engineering.
4 | 2.1, Note-1, Page no 3 of 20 Section Project | Sikar-II: The spare unit of 765kV, 1x110 MVAR Reactor proposed to be provided at Sikar-II PS under ‘Transmission system strengthening for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under Phase II-Part-C’ shall be utilized as common spare for 6x110 MVAR Switchable Line Reactors | Kindly provide the distance of spare reactor's 765KV AUX BUS & Spare neutral bus from the present scope allotted bays of this package. Accordingly Lot items r estimation to connected reactor's Aux bus & neutral bus to Spare reactor Aux bus & Neutral bus quantifying can possible. Incase data is not avaiable as on date, bidder will consider that present scope reactor Aux bus & neutral bus is adjucent to to spare reactor bay. Incase during detail engnineering stage Spare reactor bay is not adjucent to the present scope bays, Addtional cost occered due to Interconnection BOQ will metually discussed. | As, Sikar-II (New) S/S is under development, the requisite detail is not yet finalised at Sikar-II S/S. The same shall be provided during detailed engineering. Bidder to quote as per TS Section Project clause Clause 2.1 note i) & BPS. No Price implication shall be admissible in this account.
5 | 2.1, Note-II, Page no 3 of 20 Section Project | Installation of Line reactors banks under present scope at Bhadla-II S/S shall be such that same is suitable for 1-ph unit switching whenever the separate spare 1-ph unit is provided in future. All associated switching 1-ph isolators, circuit breakers suitable for 1-ph switching, 765kV and neutral Auxiliary buses and other associated equipment & scheme shall be provided for Line reactor banks at Bhadla-II S/S under present scope of work. | Kindly provide the distance of spare reactor's 765KV AUX BUS & Spare neutral bus from the present scope allotted bays of this package. Accordingly Lot items r estimation to connected reactor's Aux bus & neutral bus to Spare reactor Aux bus & Neutral bus quantifying can possible. Incase data is not avaiable as on date, bidder will consider that present scope reactor Aux bus & neutral bus is adjucent to to spare reactor bay. Incase during detail engnineering stage Spare reactor bay is not adjucent to the present scope bays, Addtional cost occered due to Interconnection BOQ will metually discussed. | The requisite detail shall be provided during detailed engineering. For estimation please refer BPS and TS Section Project Clause 2.1 note ii) and GA tender drawing. No Price implication shall be admissible in this account.
6 | General |  | Kindly furnish approximate distance of tapping point from the present scope for estimation of piping. | The requisite detail is yet to be finalised and same sahll be provided during detiled engineering.
7 | 15.0 Civil Works Rev 11A_With Correction Slip, Extn. of 765kV Sikar II PS | Excavation and backfill of foundation | Since, site is not available presently and assessment of soil parameter by site visit is not possible, whereas BPS is mentioning excavation item as "all type of soil including rock", we request to amend the excavation item by spiliting in two different items which covers for soil and weathered rock in one item and a separate item for Hard Rock by chiseling or blasting. this will help us to put appropriate & optimized costig. | Hard Rock requiring blasting is not currently envisaged. Bidder to quote as per BPS
8 | 15.0 Civil Works Rev 11A_With Correction Slip, Extension of 765kV Bhadla-II S/s | Excavation and backfill of foundation | Since, soil investigation report of Bhadla SS has not been shared, and assessment of soil parameter by site visit is not possible, whereas BPS is mentioning excavation item as "all type of soil including rock", we request to amend the excavation item by spiliting in two different items which covers for soil and weathered rock in one item and a separate item for Hard Rock by chiseling or blasting. this will help us to put appropriate & optimized costig. | Hard Rock requiring blasting is not currently envisaged. Bidder to quote as per BPS