SECTION – V

SPECIAL CONDITIONS OF CONTRACT (SCC)

SPECIAL CONDITIONS OF CONTRACT (SCC)

The following bid specific data for the Plant and Equipment to be procured shall amend and/or supplement the provisions in the General Conditions of Contract (GCC)

| Sl. No. | GCC Clause Ref. No. | Amendment/Supplement to GCC |
| --- | --- | --- |
|  | GCC 1.1(o) | Supplementing Sub-Clause GCC 1.1(o) Power Grid Corporation of India Limited, `Saudamini’, Plot No.-2, Sector-29, Gurgaon (Haryana) - 122001. Kind Attn.: Sr. General Manager/ Ch. Manager (CS-G2) Telephone Nos.: +91-124-282-2336/2377 Mobile: +91- 9910378043/9650089825 Fax Nos.:- 0091-(0)124-2571831 Email: rkrohilla@powergridindia.com pankajjangid@powergridindia.com |
|  | GCC 1.1(w) | Supplementing Sub-Clause GCC 1.1(w) The Owner is: Power Grid Corporation of India Limited, `Saudamini’, Plot No.-2, Sector-29, Gurgaon (Haryana) - 122001. Kind Attn.: Sr. General Manager/ Ch. Manager (CS-G2) Telephone Nos.: +91-124-282-2336/2377 Mobile: +91- 9910378043/9650089825 Fax Nos.:- 0091-(0)124-2571831 Email: rkrohilla@powergridindia.com pankajjangid@powergridindia.com |
|  | GCC 1.1 (ee) | Supplementing Sub-Clause GCC 1.1(ee) Time for Completion: Sl. No.; Activities; Duration in months from the effective date of Contract. 1; Diversion/Modification of following existing POWERGRID Transmission Lines (including supply of Conductor, Earthwire/OPGW, Composite Insulator, hardware fittings and accessories for conductor & earthwire/ OPGW) under MSRDC consultancy work under following divisions of NMSCEWL (SPV of MSRDC):. Nagpur Division. 765kV S/C Seoni-Wardha Transmission Line CKT-I. 765kV S/C Seoni-Wardha Transmission Line CKT-II. Amravati Division. 400 kV D/C Wardha-Akola Transmission Line.; 11 (Eleven Months). Aurangabad Division. 400KV D/C (Quad) Wardha -Aurangabad transmission line (Upgradable to1200KV). 765KV D/C (Hexa) Wardha - Aurangabad Transmission line –I. 765KV D/C (Hexa) Wardha - Aurangabad Transmission Line-II. 400KV D/C Quad Aurangabad – Boisar Transmission line. 400KV D/C (Twin) Akola – Aurangabad Transmission line.; 14 (Fourteen Months). Specification No: CC-CS/968-WR1/TWT-3995/3/G2 |
|  | GCC 4 | Replace Clause 4.0 with the following 4 Time for Commencement and Completion 4.1 Time for Completion is the essence of Contract. The Contractor shall commence work on the Facilities from the Effective Date of Contract and without prejudice to GCC Sub-Clause 21.2 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified in the corresponding Appendix – 4 (Time Schedule) to the Contract Agreement. - The Contractor shall attain Completion of the Facilities (or of a part where a separate time for Completion of such part is specified in the Contract) within the time stated under Time for Completion or within such extended time to which the Contractor shall be entitled under GCC Clause 34 hereof. |
|  | GCC 5.1.1 | Add the following at the end of the paragraph: In case of contract on Joint Venture, subject to Employer’s prior approval, the partner who does not have experience in relevant area of EPC work, may undertake EPC work execution up to 25% of the total scope of the work in the Contract under hand holding/supervision of the partner having relevant experience. Similarly, if the partner of a Joint Venture who has only the experience to a specified extent, say 25%, such partner may also be permitted to execute up to 50% of the relevant scope of work. For this purpose, however, the Joint Venture agreement delineating the responsibilities and obligations of each partner shall be amended, as required based on request of Joint Venture during execution of the Contract. This shall, however, be subject to assessment that may be carried out by the Employer, if required. |
|  | GCC 5.7 | Adding New sub cluase GCC 5.7 Vide Notification dated 8th May 2017 by Ministry of Steel has published “Policy for providing preference to Domestically Manufactured Iron & Steel Products in Government Procurement”. The Contractor shall comply with the guidelines specified in the policy including subsequent amendments/ modifications, if any. Accordingly, the Contractor shall be required to provide a value- addition certificate on half-yearly basis (Sep 30 and Mar 31), duly certified by the Statutory Auditors of the Domestic Manufacturer, that the claims of value-addition made for the product during the preceding 6 months are in accordance with the Policy. Such certificate shall be filed within 60 days of commencement of each half year, to the respective executing Region of POWERGRID and shall continue to be filed till the completion of supply of the said products. Further, if the Domestic manufacturer from whom the Contractor had proposed to source the Iron & Steel products is changed during execution of the Contract, the Contractor shall furnish (i) authorization certificate, if applicable, (ii) affidavit of self-certification and (iii) value- addition certificate from the new Domestic manufacturer. Violation to minimum prescribed domestic value addition or misrepresentation of facts by the bidder in this regard shall be dealt in line with provisions of the Integrity Pact. |
|  | GCC 8.3 | Add new sub-clause 8.3: 8.3 All payments to be made out of the funds received from Nagpur Mumbai Super Communication Expressway (NMSCEWL) (an SPV of Maharashtra State Road Development Corporation Limited (MSRDC)). |
|  | GCC 9.3.1 | Supplementing Sub-Clause GCC 9.3.1 The Contractor shall arrange additional Performance Security(ies), if applicable, as per Clause no. 4 of Joint Deed of Undertaking mentioned at Sl. No. 20 of Section – VI : Sample Forms and Procedures. The said security(ies) shall be required to be extended time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. |
|  | GCC 9.3.1.2 (b) | Replace the Clause reference GCC 9.3.1.1(b) appearing in second line with Clause GCC 9.3.1.2(a). |
|  | GCC 9.3.2 | Replace Sub-Clause GCC 9.3.2 The performance security shall, at the contractor’s option, be in the form of a crossed bank draft/pay order /banker certified cheque in favour of Employer as stipulated in SCC in the Form of unconditional Bank Guarantee attached hereto in the Section VI - Sample Forms and Procedures. Alternatively, if performance security is to be submitted in favor of POWERGRID, the same can be submitted as online payment through POWERGRID ONLINE PAYMENT UTILITY- https://epay.powergrid.in, a link of which is provided on the POWERGRID website www.powergridindia.com. While making online payment towards performance security, the bidder shall choose Segment as “Suppliers” and fill in details as follows: Payment Category; Performance Security. Sub-category; Performance Security Payment–CC@. Name of Depositor; Name of the Contractor/Collaborator/Tower manufacturer/Licensor etc.. Vendor Code, if applicable; POWERGRID vendor code of the Contractor Collaborator/Tower manufacturer/Licensor etc., if existing. Payment Remarks; Performance Security for ………….. [enter the name of the contract and last four digits of the CA number]. The copy of ‘Online Payment Acknowledgement – Suppliers’ generated subsequent to the payment shall be submitted by the Contractor. The online payment facility shall be for payment in Indian Rupees only. |
|  | GCC 9.3.5 | Adding New Sub-Clause GCC 9.3.5 No interest shall be payable by the Owner on the performance Security. |
|  | GCC 9.3.6 | Adding New Sub-Clause GCC 9.3.6 During execution of contract the Contractor, after submission of Performance Security in form of a crossed bank draft/pay order /banker certified cheque/ online payment through POWERGRID ONLINE PAYMENT UTILITY, may opt to furnish the Performance Security in form of bank guarantee for the same amount and as per same terms of the Contract. On acceptance by the Employer/Owner of Performance Security submitted in the form of Bank Guarantee following receipt of confirmation from the issuing Bank, the said amount shall be refunded. |
|  | GCC 9.4 | Supplementing GCC Clause 9.4 with the following The contractor has the option to submit BG (towards Advance Payment Security and Performance Security) using SFMS Platform. The Account details of POWERGRID for the purpose of Bank Guarantee (towards Advance Payment Security and Performance Security) to be issued using SFMS Platform are as given below: Name of the Bank and Address; IFSC Code; POWERGRID Current A/c No.. State Bank of India, 4th & 5th Floor, Parsvnath Capital Tower, Bhai Veer Singh Marg, Gole Market, New Delhi - 110001; SBIN0017313; 10813608670. ICICI Bank, Unit No. 01, Solitaire Plaza, DLF Phase III, M.G. Road, Gurugram; ICIC0002451; 000705002702. Note: Any one of the above account details can be used for the issuance of Bank Guarantee using SFMS Platform. In case of Bank Guarantee (towards Advance Payment Security and Performance Security) verification through SFMS facility of ICICI Bank, the applicant has to provide a unique identifier of POWERGRID to the issuing bank. This unique identifier needs to be incorporated by the issuing bank in Field 7037of the IFIN 760 COV/ IFIN 767 COV while transmitting these messages to the Beneficiary Bank through SFMS. The unique identifier of POWERGRID is PGCIL50948846. In addition to the above, the Bank Guarantee (towards Advance Payment Security and Performance Security) should be submitted in the Physical form as specified in GCC Clause 9. |
|  | GCC 10.6 | Replace the existing provision with the following: The Statutory deduction (eg. TDS under Income Tax/GST Acts, BOCW CEss etc.) applicable to this Project shall be done by POWERGRID on behalf of NMSCEWL from the Contractor’s Invoices/Payments and shall be deposited with the relevenat tax authorities using TAN/TIN/GSTIN of NMSCEWL. Challans and other relevant documents shall be forwarded to NMSCEWL for information, filling of returns, issue of certificates to contrtactors etc. |
|  | GCC 10.9 | Replace the existing provision with the following: While raising invoice/proforma invoice for Supply of Goods, Contactor shall bill and ship to Nagpur Mumbai Super Communication Expressway Limited (NMSCEWL) (an SPV of Maharashtra State Road Development Corporation Limited (MSRDC)) in the State/UT where the Goods or part thereof is to be Supplied and to mention GSTIN of NMSCEWL (an SPV of MSRDC) in the same state/UT. In case of Supply of Services, the Contractor shall invoice the NMSCEWL (an SPV of MSRDC) using the GSTIN of NMSCEWL (an SPV of MSRDC) in the state/UT in which the service or part thereof is to be rendered. |
|  | GCC 15.3 | Replace the existing provision with the following: For items or parts of the Facilities not specified in the corresponding Appendix (List of Approved Subcontractors) to the Contract Agreement for Supply of Goods Contract(s), the Contractor may employ such Subcontractors as it may select, at its discretion. |
|  | GCC 18.1.3 (a) | Replace GCC Clause 18.1.3 (a) with the followings: - The Contractor shall provide and employ on the Site in the installation of the Facilities such skilled, semi-skilled and unskilled labor as is necessary for the proper and timely execution of the Contract. Labour having “Recognition of Prior Learning”(RPL) Certification (under Pradhan Mantri Kaushal Vikas Yojana (PMKVY)) can also be employed by the Contractor. The Contractor is encouraged to use local labor preferably from weaker sections of society particularly SC & ST persons, that has the necessary skills. |
|  | GCC 20.2.1 | Deleted as Guarantee Tests are not applicable |
|  | GCC 20.2.2.1 (II) | Deleted as Functional Guarantees are not applicable |
|  | GCC 23 | Deleted as Functional Guarantees are not applicable |
|  | GCC 24 | Deleted as Liquidated Damages for Non-Performance of Equipment are not applicable |
|  | GCC 30.1(a) (I) (ii) | Replace GCC 30.1(a) (I) (ii) with the following: Transit Insurance Policy for indigenous equipment Similarly, Transit Insurance Policy shall be taken wherein only inland transit is involved for the movement of Plant and Equipment including mandatory Spares supplied from within India. The policy shall cover movement of Plant and Equipment including mandatory Spares from the manufacturer’s works to the project’s warehouse at final destination site. Inland Transit Clause (ITC) ‘A’ along with Strike Riots & Civil Commotion (SRCC) extension cover shall be taken. |
|  | GCC 33.2.2 | Deleted as not applicable |
|  | GCC 33.2.3 | Supplementing Sub-Clause GCC 33.2.3 Percentage for the Change Proposal under this Clause shall be limited to Fifteen (15) percent. |
|  | GCC 39.6 | Replace Clause GCC 39.6 and addition of clause 39.7 39.6 Notwithstanding the above, in case the contractor is a Central Public Sector Enterprise (CPSE)/Government Organization or Department then the dispute or difference between the Employer and the Contractor shall be settled through Administrative Mechanism for Resolution of CPSEs Disputes (AMRCD) as mentioned in DPE OM No. 4(1)/2013-DPE(GM)/FTS-1835 dated 22.05.2018. The decision through AMRCD will be final and binding on all the concerned. 39.7 During settlement of disputes and arbitration proceedings,both parties shall be obliged to carry out their respective obligations under the contract. |
|  | Appendix-I to SCC | Enclosed herewith |

----- End of Section-V (SCC) ----