| Sl. no | Clause no w.r.t specification | Description as given in specification | Comments/ Clarifications | POWERGRID’s Reply |
| --- | --- | --- | --- | --- |
|  | Appendix-I (Terms of payment), Section-IV, Vol-I of bidding documents | Supply Portion: A1. Interest Bearing initial Advance (Optional*): Ten percent (10%) of the Ex-works price component of Main Equipment/Materials (including Mandatory Spares) …………… A2. Interest Bearing Engineering Advance (Optional**): Further advance of Ten percent (10%) of the Ex-works price component of Main Equipment/Materials (including Mandatory Spares)……………….. | We request POWERGRID to provide 10% initial interest free advance of total contract value. The following terms of payments are proposed for consideration of POWERGRID Supply: 10% Interest free advance Payment. 70% against dispatch of equipments/items. 10% on receipt of equipments on site. Balance 10% on successful commissioning. Mandatory Spares, Taxes & Duties and F&I : 100% on dispatch CIVIL and ETC. 10% Interest free advance Payment. 80% progressive Payment Balance 10% on successful commissioning. | Provisions of bidding documents remain unchanged. |
|  | Appendix-I (Terms of payment), Section-IV, Vol-I of bidding documents | The Employer shall make payments promptly within thirty (30) days of submission of an invoice/claim by the Contractor, complete in all respects and supported by the requisite documents and fulfillment of stipulated conditions, if any. All the payment shall be released to the Contractor directly. | For all progressive payments, POWERGRID is requested to please consider mode of payment as site Letter of credit also. | Provisions of bidding documents remain unchanged. |
|  | ITB clause 24.1 (C), BDS, Section-III, Vol-I of bidding documents | The Time for Completion shall be 11-14 months from the date of Notification of Award | POWERGRID is requested to consider completion schedule of at least 18 months for all Three (3) sites considering supply & ETC of Transformers is also included in the tender scope. Kindly confirm | Provisions of bidding documents remain unchanged. |
|  | General | - | POWERGRID is requested to please confirm that present tender has not been called against any risk purchase and any litigation is not pending/ongoing with any party in this regard. | Bidders are requested to quote as per provisions of bidding documents which are amply clear |
|  | Appendix-8 Guarantees, Liquidated Damages for Non Performance | -- | We understand that there is no Loss Capitalization for Power Transformer in this Project. Please confirm our understanding. | Bidders are requested to refer the provisions of ITB Clause 27.5 which are amply clear. |
|  | Attach 12_Price Adjustment Data | - | Please include Price variation for 220KV HV POWER CABLE considering the volatile market & continuous increase in copper & Aluminum prices. | Bidders are requested to refer the provisions of Appendix-2, Price Adjustment which are amply clear. |
|  | GCC clause 30.1, b, V & 30.8, Section-V, Vol-I of bidding documents |  | In addition to GCC clause 30.1, b, V, regarding the cost of insurance premium to be reimbursed by purchaser to the Contractor for all Owner Supplied equipment & materials (OSM), Please also clarify/eloborate on scope of warrantee/defect liability to contractor for such items. | Provisions of bidding documents are amply clear. |