SECTION – IV

GENERAL CONDITIONS OF CONTRACT (GCC)

TABLE OF CLAUSES

# Preamble

- Definitions and Interpretation	1

  - Definitions	1

  - Interpretation	5

- Subject Matter of Contract	8

- Scope of Facilities	8

- Time for Commencement and Completion	10

- Contractor’s Responsibilities	10

- Employer’s Responsibilities	11

- Payment	12

- Contract Price	12

- Terms of Payment	13

- Securities	13

- Taxes and Duties	16

- Intellectual Property	18

- Copy Right	18

- Confidential Information	19

- Execution of the Facilities	20

- Representatives	20

- Work Program	22

- Subcontracting	24

- Design and Engineering	24

- Plant and Equipment	27

- Installation	30

- Test and Inspection	47

- Completion of the Facilities and Operational Acceptance	49

- Guarantees and Liabilities	55

- Completion Time Guarantee	55

- Defect Liability	56

- Functional Guarantees	58

- Equipment Performance Guarantees	59

- Patent Indemnity	60

- Limitation of Liability	61

- Risk Distribution	62

- Transfer of Ownership	62

- Care of Facilities	62

- Loss of or Damage to Property; Accident or Injury to Workers; Indemnification	63

- Insurance	64

- Change in Laws and Regulations	70

- Force Majeure	71

- Change in Contract Elements	71

- Change in the Facilities	71

- Extension of Time for Completion	74

- Suspension	75

- Termination	76

- Assignment	82

- Resolution of Disputes	82

- Settlement of Disputes	82

- Arbitration	83

GENERAL CONDITIONS OF CONTRACT (GCC)

Preamble

This Section (Section –IV) of the Bidding Documents [named as General Conditions of Contract (GCC)] provides all the rights and obligations of the parties under the Contract. This Section contains provisions that are to be used unchanged unless Section – V [named as Special Conditions of Contract (SCC)] states otherwise as any changes in GCC or any complementary information that may be needed has been shown in SCC. If there is a conflict between the provisions of Section – IV & Section – V, the provisions of Section – V shall prevail.

# Definitions and Interpretation

# Definitions

    - The  following  words  and  expressions  shall  have  the  meanings hereby assigned to them:

      - “Contract” means the Contract Agreement entered into between the Employer and the Contractor together with the Contract Documents referred to therein.

      - “Contract Documents” means the documents listed in Clause

1.1 of Article 1 (Contract Documents) of the Form of Contract Agreement (including any amendments thereto).

      - “Contract Price” means the sum specified in Clause 2.1 of Article 2 (Contract Price) of the Contract Agreement, subject to such additions or deductions therefrom, as may be made pursuant to the Contract. For the purpose of Liquidated Damages and Contract Performance Guarantee, the “Contract Price” means the sum specified in Clause 2.1 of Article 2 (Contract Price) of the Contract Agreement.

      - “Contractor” means the firms whose bid to perform the Contract has been accepted by the Employer and is named in the Contract Agreement, and includes the legal successors or permitted assigns of the Contractor.

      - “Contractor’s Equipment” means all plant, facilities, equipment, machinery, tools, apparatus, appliances or things of every kind required in or for installation, completion and maintenance of Facilities that are to be provided by the Contractor, but does not include Plant and Equipment, or other things intended to form or forming part of the Facilities.

      - “Contractor’s Representative” means any person nominated by the Contractor and approved by the Employer in the manner provided in GCC Sub-Clause 13.2 (Contractor’s Representative and Construction Manager) hereof to perform the duties delegated by the Contractor.

      - “Day” means calendar day of the Gregorian Calendar.

      - “Effective Date” means the date of Notification of Award from which the Time for Completion shall be determined.

      - “Employer” means the firm/corporation/ government entity, named in the SCC, who is responsible for getting the Facilities implemented.  The  Employer  may  be  Owner  himself  or  an

agency  appointed  by  the  Owner  and  shall  include  the  legal successors or permitted assigns of the Employer.

      - “GCC” means the General Conditions of Contract hereof.

      - “Month” means calendar month of the Gregorian Calendar.

      - “Notification of Award” means the official notice issued by the Employer notifying the Contractor that his bid has been accepted.

      - “Owner”	means	the	firm/corporation/government	entity,

named in the SCC, who has decided to set up the Facilities and

shall includes the legal successors or permitted assigns of the Owner.

      - “Plant and Equipment” means permanent plant, equipment, machinery, apparatus, articles and things of all kinds to be provided and incorporated in the Facilities by the Contractor under the Contract (including the spare parts to be supplied by the Contractor under GCC Sub-Clause 3.3 hereof), but does not include Contractor’s Equipment.

      - “Project Manager” means the person appointed by the Employer in the manner provided in GCC Sub-Clause 13.1 hereof to perform the duties delegated by the Employer.

(aa)  “SCC” means the Special Conditions of Contract.

(bb) “Site” means the land and other places upon which the Facilities are to be installed, and such other land or places as may be specified in the Contract as forming part of the Site.

(cc) “Subcontractor”/”vendor”/”sub-vendor” means  firms/ corporations/government entities to whom execution of any part of the Facilities, including preparation of any design or supply of any Plant and Equipment, is sub-contracted directly or indirectly by the Contractor with the consent of the Employer in writing, and includes its legal successors or permitted assigns.

(dd) “Taking Over” means the Employer’s written acceptance of the Facilities under the Contract, after successful Trial – Operation for the specified period in accordance with the Contract, as provided in GCC Sub-Clause 20.1.5.

(ee) “Time for Completion” means the time within which Completion of the Facilities is to be attained in accordance with the specifications, as a whole (or of a part of the Facilities where a separate Time for Completion of such part has  been prescribed in the SCC) and “Taking Over” by the Employer is to be attained.

# Interpretation

    - Contract

    - The Contract to be entered into with the successful Bidder shall be for providing all services i.e. inland transportation for delivery at site, In-transit insurance, unloading, handling at site and any other services specified in the Contract Documents.

    - The Contract will be signed in two originals and the Contractor shall be provided with one signed original and the rest will be retained by the Employer.

  - Contract Documents

All documents forming part of the Contract (and all parts thereof) are intended to be correlative, complementary and mutually explanatory, subject to Article 1.2 (Order of Precedence) of the Contract Agreement. The Contract shall be read as a whole.

  - Language

The ruling language of the Contract and the language for communications shall be English.

  - Singular and Plural

The singular shall include the plural and the plural the singular, except where the context otherwise requires.

  - Headings

The headings and marginal notes in the General Conditions of Contract are included for ease of reference, and shall neither constitute a part of the Contract nor affect its interpretation.

  - Entire Agreement

Subject to GCC Sub-Clause 12.4 hereof, the Contract constitutes the entire agreement between the Employer and Contractor with respect to the subject matter of Contract and supersedes all communications, negotiations and agreements (whether written or oral) of parties with respect thereto made prior to the date of Contract.

  - Amendment

No amendment or other variation of the Contract shall be effective unless it is in writing, is dated, expressly refers to the Contract, and is signed by a duly authorized representative of each party hereto.

  - Independent Contractor

The Contractor shall be an independent contractor performing the Contract. The Contract does not create any agency, partnership, joint venture or other joint relationship between the parties hereto.

Subject to the provisions of the Contract, the Contractor shall be solely responsible for the manner in which the Contract is performed. All employees, representatives or Subcontractors engaged by the Contractor in connection with the performance of the Contract shall be under the complete control of the Contractor and shall not be deemed to be employees of the Employer, and nothing contained in the Contract or in any subcontract awarded by the Contractor shall be construed to create any contractual relationship between any such employees, representatives or Subcontractors and the Employer.

  - Joint Venture: Not Applicable

  - Non-Waiver

    - Subject to GCC Sub-Clause 2.10.2 below, no relaxation, forbearance, delay or indulgence by either party in enforcing any of the terms and conditions of the Contract or the granting of time by either party to the other shall prejudice, affect or restrict the rights of that party under the Contract, nor shall any waiver by either party of any breach of Contract operate as waiver of any subsequent or continuing breach of Contract.

    - Any waiver of a party‟s rights, powers or remedies under the Contract must be in writing, must be dated and signed by an authorized representative of the party granting  such waiver, and must specify the right and the extent to which it is being waived.

  - Severability

If any provision or condition of the Contract is prohibited or rendered invalid or unenforceable, such prohibition, invalidity or unenforceability shall not affect the validity or enforceability of any other provisions and conditions of the Contract.

  - Country of Origin : Not Applicable

  - Notices

    - Unless otherwise stated in the Contract, all notices to be given under the Contract shall be in writing, and shall be sent by personal delivery, special courier, telegraph, facsimile or Electronic Data Interchange (EDI) to the address of the relevant party set out in the Contract Agreement, with the following provisions:

      - Any notice sent by telegraph, facsimile or EDI shall be confirmed within two  (2) days after dispatch by  notice  sent by  special courier, except as otherwise specified in the Contract.

      - Any notice sent by special courier shall be  deemed (in the absence of evidence of earlier receipt) to have been delivered ten (10) days after dispatch. In proving the fact of dispatch, it shall be sufficient to show that the envelope containing such notice was properly addressed, stamped and conveyed to the postal authorities or courier service for transmission by special courier. Provided further that whenever the postal authorities or courier service provide a proof of delivery, the same shall also be applicable for presenting the fact of dispatch.

      - Any notice delivered personally or sent by telegraph, facsimile or EDI shall be deemed to have been delivered on date of its dispatch.

      - Either party may change its postal, facsimile or EDI address or addressee for receipt of such notices by ten (10) days‟ notice to the other party in writing.

    - Notices  shall   be   deemed   to   include   any   approvals,  consents, instructions, orders and certificates to be given under the Contract.

  - Governing Law & its Jurisdiction

The Contract shall be governed by and interpreted in accordance with laws of Union of India and the Courts of Lucknow shall have exclusive jurisdiction in all maters arising under this Contract.

# B.	Subject Matter of Contract

# Scope of Facilities

    - Unless otherwise expressly limited in the Technical Specifications, the Contractor's obligation  shall include  transportation of equipment, loading & unloading, in-transit insurance .

    - The Contractor shall, unless specifically excluded in the Contract, perform all such work and/or supply all such items and materials not specifically mentioned in the Contract but that can be reasonably inferred from the Contract as being required for completion of project as if such work and/or items and materials were expressly mentioned in the Contract.

# Time for Commencement and Completion

    - The Contractor shall commence work from the Effective Date of Contract and without prejudice to GCC Sub-Clause 21.2 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified in the corresponding Appendix – 4 (Time Schedule) to the Contract Agreement.

# Contractor’s Responsibilities

    - The Contractor shall Transport the equipment with due care and diligence in accordance with the Contract.

    - The Contractor confirms that it has entered into this Contract on the basis of a proper examination of the relevant data relating to the Equipment. The Contractor acknowledges that any failure  to acquaint itself with all such data and information shall not relieve its responsibility for properly estimating the difficulty or cost of successfully performing the Facilities.

    - The Contractor shall acquire in its name all permits, approvals and/or licenses from all local, state or national government authorities or public service undertakings in the country where the Site is located that are necessary for the performance of the Contract. The Contractor shall acquire all other permits, approvals and/or licenses that are not the responsibility of the Employer under GCC Sub-Clause 6.3 hereof and that are necessary for the performance of the Contract.

    - The Contractor shall comply with all laws in force in India. The laws will include all local,  state, national or other laws that affect the performance of the Contract and bind upon the Contractor. The Contractor shall indemnify and hold harmless the Employer from and against any and all liabilities, damages, claims, fines, penalties and expenses of whatever nature arising or resulting from the violation of such laws by the Contractor or its personnel, including the Subcontractors and their personnel, but without prejudice  to GCC Sub-Clause 6.1 hereof.

# Employer’s Responsibilities

    - The Employer shall ensure the accuracy of all information and/or data to be supplied by the Employer as described in the corresponding Appendix - 6 (Scope of Works and Supply by the Employer) to the Contract, except when otherwise expressly stated in the Contract.

# C.	Payment

# Contract Price

    - The Contract Price shall be as specified in Article 2 (Contract Price and Terms of Payment) of the Form of Contract Agreement.

    - The Contract Price shall be subject to adjustment in accordance with the provisions of Appendix 2 (Price Adjustment) to the Contract Agreement.  The  Contract  Price  shall  be  increased  or  reduced  on account of variation in quantity in accordance with Clause 33 of GCC.

    - Subject to GCC Sub-Clauses 5.2 and 6.1 hereof, the Contractor shall be deemed to have satisfied itself as to the correctness and sufficiency of the Contract Price, which shall, except as otherwise provided for in the Contract, cover all its obligations under the Contract.

# Terms of Payment

    - The Contract Price shall be paid as specified in the corresponding Appendix - 1 (Terms and Procedures of Payment) to the Contract Agreement. The procedures to be followed in making application for and processing payments shall be those outlined in the same Appendix.

    - All payments under the Contract shall be made in Indian Rupees.

# Securities

    - Issuance of Securities

The Contractor shall provide the securities specified below in favor of the Employer at the times, and in the amount, manner and form specified below.

    - Advance Payment Security: Not Applicable

  - Performance Security

    - The Contractor shall, within twenty-eight(28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten percent (10%) of the Contract Price, with a validity upto ninety (90) days beyond the Defect Liability Period. The same shall be extended by the Contractor from time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract.

Apart from the Contractor‟s performance security, the Contractor shall be required to arrange additional performance securities, as specified in SCC, within twenty-eight (28) days of the notification of award in favour of the Employer in the form acceptable to the Employer.

9.3.1.1 	Notwithstanding above, in case of the performance security (ies) for which the validity as per GCC Clause 9.3.1 is required to be more than 5 years, the Contractor may choose to submit the performance security with initial validity of 5 years. In such cases, the Contractor shall, however be required to extend the validity till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract at any time, but no later than 6 months, prior to expiry of the performance security failing which the said performance security shall be forfeited by the Employer.

9.3.1.2	If the Contractor delays submission of 	the performance security(ies) vis-à-vis the period specified in Clause GCC 9.3.1, then without prejudice to any other rights or remedies available with 	the Employer, following shall also be applicable:

a)	The Defect Liability Period pursuant to Clause GCC 22 for the Facilities or any relevant part thereof covered under the said performance security shall stand extended and the Contractor shall accordingly extend the validity of the Contract Performance Security to be furnished as per Clause GCC 9.3.1 by the period of delay as per Clause GCC 9.3.1.2 (c), over and above the period required as per the Contract.

b)	Alternatively, if the Contractor fails to extend the validity of the performance security pursuant to Clause GCC 9.3.1.1, an amount @prevailing SBI Card Rate applicable for Inland Bank Guarantee +2% per annum on the performance security amount corresponding to the Facilities or any relevant part thereof covered under the said performance security, for the period of delay as per Clause GCC 9.3.1.2 (c) shall be paid by the Contractor to the Employer.  The Employer may, without prejudice to any other method of recovery, deduct the amount worked out as above from any monies due or to become due to the Contractor under the Contract.

c)	The period of delay for the above purpose shall be the time elapsed between the due date for submission of performance security as per the Contract and the date of performance security.

d)	In case the Contractor fails to submit the performance security within 90 days of the Notification of Award, the Employer, without prejudice to any other rights or remedies it may possess under the Contract, may forfeit the bid security and/or may terminate the Contract forthwith pursuant to GCC Clause 36.

9.3.1.3	The above extension of Defect Liability Period or deduction shall not relieve the Contractor from any of his obligations and liabilities under the Contract.

9.3.1.4	The Employer shall be sole judge in  above regard.

9.3.1.5  	Apart from the performance security (ies) to be furnished as per Clause GCC 9.3.1 above, additional performance securities, as specified in the Bidding Documents, shall be arranged and furnished by the Contractor at any time after the Notification of Award. The submission of these performance securities to the Employer shall, however, be one of the conditions precedent for release of payment (other than Initial/Mobilisation advance) due against such equipment/ works for which the said performance security is required to be submitted.

    - The performance security shall, at the contractor’s option, be in the form of a crossed bank draft/ pay order/ banker certified cheque in favour of Employer as stipulated in SCC or in the form of unconditional bank guarantee attached hereto in the Section VI – Sample Forms and Procedures.

    - Reduction in the security pro rata to the Contract Price of any part of the Facilities is not admissible. However, if the Defects Liability Period has been extended on any part of the Facilities pursuant to GCC Sub-Clause 22.8 hereof, the Contractor shall issue an additional security in an amount proportionate to the Contract Price of that part. The security shall be returned to the Contractor immediately after its expiration, provided, however, that if the Contractor pursuant to GCC Sub-Clause 22, is liable for an extended warranty obligation, the performance security shall be reduced to ten percent (10%) of the value of the component covered by the extended warranty.

    - During execution of Contract the Contractor, after submission of Performance Security in form of a crossed bank draft/ pay order/ banker certified cheque, may opt to furnish the Performance Security in form of Bank Guarantee for the same amount and as per same terms of the Contract. On acceptance by the Employer of performance security submitted in the form of bank Guarantee following receipt of confirmation from the issuing Bank, the said amount shall be refunded.

  - Issuing Banks

The Bank Guarantee for Advance Payment Security and Performance Security are to be provided by the Contractor, which should  be issued either:

- by a Public Sector Bank located in India, or

- a scheduled Indian Bank having paid up capital (net of any accumulated losses) of Rs. 1,000 Million or above (the latest annual report of the Bank should support compliance of capital adequacy ratio requirement) as per attached list only [List is placed at Annexure-I to Special Conditions of Contract (SCC)], or

- by a foreign bank or a subsidiary of a foreign bank, acceptable to the Employer, with overall international corporate rating or rating of long term debt not less than A- (A minus) or equivalent by a reputed rating agency. Further, the Bank Guarantee should be confirmed by either (i) its corresponding bank located in India; or (ii) a Public Sector Bank located in India; or (iii) a scheduled commercial private bank located in India as per the attached list only [List is placed at Annexure-I to Special Conditions of Contract (SCC)].

  - Indemnity: Not Applicable

# Taxes and Duties

    - The Contractor shall be entirely responsible for payment of all taxes, duties, licence fees and other such levies legally payable/incurred until delivery of the contracted supplies to the Employer.

If it is statutory requirement to make deductions towards such taxes and duties or any other applicable taxes and duties, the same shall be made by the Employer and a certificate for the same shall be issued to the Contractor.

    - The Contractor shall be solely responsible for the taxes that may be levied on the Contractor's persons or on earnings of any of his employees and shall hold the Employer indemnified and harmless against any claims that may be made against the Employer. The Employer does not take any responsibility whatsoever regarding taxes under Indian Income Tax Act, for the Contractor or his personnel. If it is obligatory under the provisions of the Indian Income Tax Act, deduction of Income Tax at source shall be made by the Employer.

    - The Input Tax Credit (ITC) available, if any, under GST as per the relevant Government laws wherever applicable has been taken into account by the Contractor.

    - The price for supply of services viz. Transportation are excluding GST.

The GST will be reimbursed/ paid based on Forward Charge/ Reverse Charge mechanism, as indicated by the bidder in its bid.

    - Employer would not bear any liability on account of any other taxes, duties, levies applicable locally.

    - Employer shall, deduct taxes at source as per the applicable laws/rules, if any, and issue Tax Deduction at Source (TDS) Certificate to the Contractor.

    - Reimbursement of GST by the Employer shall be at the rate applicable on the HSN/SAC of the goods/ services supplied by the Contractor to the Employer. The reimbursement of GST except GST on advance payment shall be against Invoice/Debit Note containing particulars specified under the GST Act and related Rules, Notifications, etc as notified by the Government in this regard. In the event that the Contractor fails to provide the invoice in the form and manner prescribed under the GST Act and Rules, the Employer shall not be liable to make any payment against such invoice. Reimbursement of GST payment against Advance payment (applicable for Supply of Services) shall be against a proforma invoice. Further, the Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law.

If there is difference in HSN/SAC classification and corresponding rate of GST of an item as confirmed/deemed confirmed by the bidder in its bid and HSN/SAC and corresponding rate of GST as interpreted under any interpretation/ judgment/ Notification/ Circular issued under the GST law before or after the award of contract, GST reimbursable to the bidder/Contractor shall be lower of the GST applicable at the rate as confirmed/deemed confirmed in the bid or actual GST paid/payable by the bidder for that item.

    - The Contractor shall comply with all tax laws in force in India. The Contractor shall indemnify and hold harmless the Employer from and against any and all liabilities, interest, damages, claims, fines, penalties and expenses  of whatever nature arising or resulting from the violation of such tax laws by the Contractor or its personnel, including the Subcontractors and their personnel.

    - Owner’s GSTIN number in each state/UT is published on the Owner’s company website https://www.powergridindia.com. While raising invoice/proforma invoice, Contactor shall invoice the Owner using the GSTIN of Owner  in the state/UT in which the service or part thereof is to be rendered.

    - Notwithstanding anything above or elsewhere in the Contract, in the event that the input tax credit of the GST charged by the Contractor is denied by the tax authorities to the Employer for reasons associated with non-compliance/ incorrect compliance by the Contractor, the Employer shall be entitled to recover such amount from the Contractor by way of adjustment from any of the subsequent invoices submitted by the Contractor to the Employer. In addition to the amount of GST, the Employer shall also be entitled to recover interest and penalty, in case any interest and/or penalty are imposed by the tax authorities on the Employer for incorrect/wrong availment of Input Tax Credit.  The Employer shall determine whether the denial of credit is linked to the non-compliance/ incorrect compliance of the Contractor and the said determination shall be binding on the Contractor.

    - For the purpose of the Contract, it is agreed that the Contract Price specified in Article 2(Contract Price and Terms of Payment) of the Contract Agreement is based on the taxes, duties, levies and charges prevailing at the date seven (07) days prior to the last date of bid submission (hereinafter called “Tax” in this GCC Sub-clause 10.11). If any rates of Tax are increased or decreased, a new Tax is introduced, an existing Tax is abolished, or any change in interpretation except for classification related purpose, or application of any Tax occurs in the course of the performance of the Contract, which was or will be assessed on the Contractor in connection with performance of the Contract, an equitable adjustment of the Contract price shall be made to fully take into account any such change by addition to the Contract price or deduction therefrom, as the case may be, in accordance with GCC Clause 31 (Changes in Laws and Regulations) hereof. These adjustments shall be applicable for all transactions between the Employer and the Contractor for supply of goods and services under the Contract but shall not be applicable on procurement of raw materials, intermediary components etc. by the Contractor and on account of variation in taxes, duties & levies applicable locally.

# D.	Intellectual Property

# Copy Right: Not Applicable

# Confidential Information: Not Applicable

# E.	Execution of the Facilities

# Representatives

    - Project Manager name is indicated in SCC.

    - Contractor’s Representative

13.2.1      If the Contractor’s Representative is not named in the Contract, then within fourteen (14) days of the Effective Date, the Contractor shall appoint the Contractor’s Representative.

# Work Program: Not Applicable

# Subcontracting: Not Applicable

# Design and Engineering: Not Applicable

# Plant and Equipment: Not Applicable

# Installation: Not Applicable

# Test and Inspection: Not Applicable

# Completion of the Facilities and Operational Acceptance: Not Applicable

# F.	Guarantees and Liabilities

# Completion Time Guarantee:

    - The Contractor guarantees that it shall attain Completion of the Facilities (or a part for which a separate time for completion is specified in the SCC) within the Time for Completion specified in the SCC pursuant to GCC Sub-Clause 4.2, or within such extended time to which the Contractor shall be entitled under GCC Clause 34 hereof.

    - If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to half percent (0.5%) of the Contract Price plus GST payable thereon  for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each week or part thereof which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price plus GST payable thereon  for the whole of the facilities, (or a part for which a separate time for completion is agreed). The Employer may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the Contractor. The payment or deduction of such damages shall not relieve the Contractor from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract.

    - No bonus will be given for earlier Completion of the Facilities or part thereof.

# Defect Liability: Not Applicable

# Functional Guarantees: Not Applicable

# Equipment Performance Guarantees: Not Applicable

# Patent Indemnity: Not Applicable

# Limitation of Liability

    - Except in cases of gross negligence or willful misconduct,

      - the Contractor and the Employer shall not be liable to the other party for any indirect or consequential loss or damage, loss of use, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the Contractor to pay liquidated damages to the Employer and

      - the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed the total Contract Price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment, or to any obligation of the Contractor to indemnify the Employer with respect to patent infringement.

# G.	Risk Distribution

# Transfer of Ownership: Not Applicable

# Care of Facilities: Not Applicable

# Loss of or Damage to Property; Accident or Injury to Workers; Indemnification

    - The Contractor shall indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney‟s fees and expenses, in respect of the death or injury of any person or loss of or damage to any property (other than the Facilities whether accepted or not) and by reason of the negligence of the Contractor or its Subcontractors, or their employees, officers or agents, except any injury, death or property damage caused by the negligence of the Employer, its contractors, employees, officers or agents.

    - If any proceedings are brought or any claim is made against the Employer that might subject the Contractor to liability under GCC Sub-Clause 29.1, the Employer shall promptly give the Contractor a notice thereof and the Contractor may at its own expense and in the Employer’s name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim.

If the Contractor fails to notify the Employer within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Employer shall be free to conduct the same on its own behalf. Unless the Contractor has so failed to notify the Employer within the twenty-eight (28) day period, the Employer shall make no admission that may be prejudicial to the defense of any such proceedings or claim.

The Employer shall, at the Contractor’s request, afford all available assistance to the Contractor in conducting such proceedings or claim, and shall be reimbursed by the Contractor for all reasonable expenses incurred in so doing.

    - Notwithstanding anything in this Contract to the contrary, it is agreed that neither the Contractor nor the Employer shall be liable to the other party for loss of profit, loss of use or any other indirect or consequential damages.

# Insurance

    - To the extent specified in the corresponding Appendix-3 (Insurance Requirements) to the Contract Agreement, the Contractor shall at its expense take out and maintain in effect, or cause to be taken out and maintained in effect, during the performance of the Contract, the insurances set forth below in the sums and with the deductibles and other conditions specified in the said Appendix. The identity of the insurers and the form of the policies shall be subject to the approval of the Employer, who should not unreasonably withhold such approval.

      - Transit Insurance Policy:

(I)  Transit Insurance Policy for indigenous equipment

Transit Insurance Policy shall be taken for the movement of Plant and Equipment including mandatory Spares.  The policy shall cover movement of Plant and Equipment including mandatory Spares from originating station  to Destination Station. Inland Transit Clause (ITC) ‘A’ along with Strike Riots & Civil Commotion (SRCC) extension cover shall be taken.

        - If during the execution of Contract, the Employer requests the Contractor to take any other add-on cover(s)/ supplementary cover(s) in aforesaid insurance, in such a case, the Contractor shall promptly take such add-on cover(s)/ supplementary cover(s) and the charges towards such premium for such add-on cover(s)/ supplementary cover(s) shall be reimbursed to the Contractor on submission documentary evidence of payment to the Insurance company. Therefore, charges towards premium for such add-on cover(s)/ supplementary cover(s) are not included in the Contract Price.

        - The Contractor shall take the policy in the joint names of Employer and the Contractor. The policy shall indicate the Employer as the beneficiary. However, if the Contractor is having an open policy for its line of business, it should obtain an endorsement of the open cover policy from the insurance company indicating that the dispatches against this Contract are duly covered under its open policy and include the name of the Employer as jointly Insured in the endorsements to the open policy.

      - Contractor’s Plant and Machinery (CPM) Insurance

The Employer (including without limitation any consultant, servant, agent or employee of the Employer) shall not in any circumstances be liable to the Contractor for any loss of or damage to any of the Contractor’s Equipment or for any losses, liabilities, costs, claims, actions or demands which the Contractor may incur or which may be made against it as a result of or in connection with any such loss or damage.

    - The Employer shall be named as co-insured under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 30.1, except for the Third Party Liability, Workmen Compensation Policy Insurances, and the Contractor’s Subcontractors shall be named as co-insureds under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 30.1 except for the Cargo Insurance During Transport, Workmen Compensation Policy Insurances. All insurer‟s rights of subrogation against such co- insureds for losses or claims arising out of the performance of the Contract shall be waived under such policies.

    - The Contractor shall, in accordance with the provisions of the corresponding Appendix – 3 (Insurance Requirements) to the Contract Agreement, deliver to the Employer certificates of insurance (or copies of the insurance policies) as evidence that the required policies are in full force and effect. The certificates shall provide that no less than twenty-one (21) days‟ notice shall be given to the Employer by insurers prior to cancellation or material modification of a policy.

    - The Contractor shall ensure that, where applicable, its Subcontractor(s) shall take out and maintain in effect adequate insurance policies for their personnel and vehicles and for work executed by them under the Contract, unless such Subcontractors are covered by the policies taken out by the Contractor.

    - The Employer shall at its expense take out and maintain in effect during the performance of the Contract those insurances specified in the corresponding Appendix – 3 (Insurance Requirements) to the Contract Agreement, in the sums and with the deductibles and other conditions specified in the said Appendix. The Contractor and the Contractor’s Subcontractors shall be named as co-insureds under all such policies. All insurers‟ rights of subrogation against such co- insureds for losses or claims arising out of the performance of the Contract shall be waived under such policies. The Employer shall deliver to the Contractor satisfactory evidence that the required insurances are in full force and effect. The policies shall provide that not less than twenty-one (21) days‟ notice shall be given to the Contractor by all insurers prior to any cancellation or material modification of the policies. If so requested by the Contractor, the Employer shall provide copies of the policies taken out by the Employer under this GCC Sub-Clause 30.5.

    - If the Contractor fails to take out and/or maintain in effect the insurances referred to in GCC Sub-Clause 30.1, the Employer may take out and maintain in effect any such insurances and may from time to time deduct from any amount due the Contractor under the Contract any premium that the Employer shall have paid to the insurer, or may otherwise recover such amount as a debt due from the Contractor. If the Employer fails to take out and/or maintain in effect the insurances referred to in GCC 30.5, the Contractor may take out and maintain in effect any such insurances and may from time to time deduct from any amount due the Employer under the Contract any premium that the Contractor shall have paid to the insurer, or may otherwise recover such amount as a debt due from the Employer.

    - Unless otherwise provided in the Contract, the Contractor shall prepare and conduct all and any claims made under the policies effected by it pursuant to this GCC Clause 30, and the monies payable by any insurers under all the insurance except Third Party Liability Insurance and Workmen Compensation Policy, shall  be paid to the Special Account to be opened in the joint name of the Employer and the Contractor as mutually agreed and such amounts paid shall be apportioned between the Employer and the Contractor in accordance with the respective responsibilities under the Contract. The Employer shall give to the Contractor all such reasonable assistance as may be required by the Contractor. With respect to insurance claims in which the Employer's interest is involved, the Contractor shall not give any release or make any compromise with the insurer without the prior written consent of the Employer. With respect  to  insurance  claims  in  which  the  Contractor's  interest  is

involved, the Employer shall not give any release or make any compromise with the insurer without the prior written consent of the Contractor.

    - It will be the responsibility of the Contractor to lodge, pursue and settle all claims with the insurance company in case of any damage, loss, theft, pilferage or fire during execution of Contract and Employer shall be kept informed about it. The Contractor shall replace the lost/damaged materials promptly irrespective of the settlement of the claims by the underwriters and ensure that the work progress is as per agreed schedules. The losses, if any, in such replacement will have to be borne by the Contractor.

# Change in Laws and Regulations

31.1	If, after the date seven (07) days prior to the date of Bid Opening, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed in India (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the costs and expenses of the Contractor and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been affected in the performance of any of its obligations under the Contract. These adjustments shall be applicable for all transactions between the Employer and the Contractor for supply of goods and services under the Contract but shall not be applicable on procurement of raw materials, intermediary components etc. by the Contractor  for which the Employer shall be the sole judge.

Notwithstanding the foregoing, such additional or reduced costs  shall not be separately paid or credited if the same has already been accounted for in the price adjustment provisions where applicable, in accordance with the Appendix-2 to the Contract Agreement.

# Force Majeure

    - “Force Majeure” shall mean any event beyond the reasonable control of the Employer or of the Contractor, as the case may be, and which is unavoidable notwithstanding the reasonable care of the party affected, and shall include, without limitation, the following:

      - war, hostilities or warlike operations (whether war be declared or not), invasion, act of foreign enemy and civil war,

      - rebellion, revolution, insurrection, mutiny, usurpation of government, conspiracy, riot and civil commotion,

      - earthquake, landslide, volcanic activity, flood or cyclone, or other inclement weather condition, nuclear and pressure waves or other natural or physical disaster,

    - Neither party shall be considered to be in default or in breach of his obligations under the Contract to the extent that performance of such obligation is prevented by any circumstances of Force majure, which arises after date of Notification of Award.

    - If either party is prevented, hindered or delayed from or in performing any of its obligations under the Contract by an event of Force Majeure, then it shall notify the other in writing of the occurrence of such event and the circumstances thereof within fourteen (14) days after the occurrence of such event.

    - The party who has given such notice shall be excused from the performance or punctual performance of its obligations under the Contract for so long as the relevant event of Force Majeure continues and to the extent that such party‟s performance is prevented, hindered or delayed. The Time for Completion shall be extended in accordance with GCC Clause 34.

# H.	Change in Contract Elements

# Change in the Facilities

    - Introducing a Change

    - Subject to GCC Sub-Clauses 33.2.5 and 33.2.7, the Employer shall have the right to propose, and subsequently require, that the Project Manager order the Contractor from time to time during the performance of the Contract to make any change, modification, addition or deletion to, in or from the Facilities (hereinafter called “Change”), provided that such Change falls within the general scope of the Facilities and does not constitute unrelated work and that it is technically practicable, taking into account both the state of advancement of the Facilities and the technical compatibility of the Change envisaged with the nature of the Facilities as specified in the Contract.

    - The Contractor may from time to time during its performance of the Contract propose to the Employer (with a copy to the Project Manager) any Change that the Contractor considers necessary or desirable to improve the quality, efficiency or safety of the Facilities. The Employer may at its discretion approve or reject any Change proposed by the Contractor, provided that the Employer shall approve any Change proposed by the Contractor to ensure the safety of the Facilities.

    - Changes made necessary because of any default of the Contractor in the performance of its obligations under the Contract shall be not be deemed to be a Change, and such change shall not result in any adjustment of the Contract Price or the Time for Completion.

    - The procedure on how to proceed with and execute Changes is specified in GCC Sub-Clauses 33.2 and 33.3.

  - Changes Originating from Employer

    - The pricing of any Change shall, as far as practicable, be calculated in accordance with the rates and prices included in the Contract. If such rates and prices are inequitable, the parties thereto shall agree on specific rates for the valuation of the Change.

    - The Contract Price for (i) the items for which quantities have been indicated as lumpsum or lot or set and/or (ii) where the quantities are to be estimated by the Contractor shall remain constant unless there is change made in the Scope of Work by Employer. The quantities and unit prices (i) subsequently arrived while approving the Bill of  Quantities (BOQ)/Billing breakup of  lumpsum quantities/lot/Set and/or (ii) estimated by the Contractor shall be for on account payment purpose only. In case additional quantities, over and above the quantities in BOQ/billing breakup and /or estimated by the Contractor, are required for successful completion of the scope of work as per Technical Specification, the Contractor shall execute additional quantities of these items for which no additional payment shall be made over  and  above the lumpsum Contract Price. In case quantities of these items supplied at site are in excess of that required for successful completion of scope of work, such additional quantities shall be the property of the Contractor and they shall be allowed to take back the same from the site for which no deduction from the lumpsum Contract Price shall be made. Further, in case actual requirement of quantities for successful completion of scope of work is less than the quantities identified in the approved BOQ /billing breakup and/or estimated by the Contractor, the lumpsum contract price shall remain unchanged and no deduction shall be made from the lumpsum price due to such reduction of quantities.

It shall be the responsibility of the Contractor to pay all statutory taxes, duties and levies to the concerned authorities for such surplus material which would otherwise have been, lawfully payable in case of non-deemed export contracts. The Contractor shall submit an indemnity bond to keep Employer harmless from any liability, before release of such material to the Contractor by Employer.

Set/Lot/Lumpsum shall be governed as per the requirement of the corresponding item  description read  in conjunction  with relevant provisions of Technical Specifications and the Billing breakup referred to above shall be issued by the Employer based on Contractor’s request, if and as may be required during the currency of the Contract.

HSN/SAC has not been indicated in the Contract for lumpsum quantities/lot/Set as each of these consists of many items for which billing break up shall be furnished during contract execution. GST shall be reimbursed on these items based on HSN /SAC for these items furnished along with billing breakup. However, the reimbursement shall be limited to the amount derived based on the rate indicated in the contract or actual, whichever is less.

    - If before or during the preparation of the Change Proposal it becomes apparent that the aggregate effect of compliance therewith and with all other Change Orders that have already become binding upon the Contractor under this GCC Clause 33 would be to increase or decrease the Contract Price as originally set forth in Article 2 (Contract Price and Terms of Payment) of the Contract Agreement by more than the percentage specified in SCC, the Employer and the Contractor shall mutually agree on specific rates for valuation of the Change beyond the specified percentage.

For the said purpose, the Contract Price means the Contract Price of the Facilities notwithstanding the Construction of the Contract.

    - If rates and prices of any change are not available in the Contract, the parties thereto shall agree on specific rates for the valuation of the change and all matters therein related to the change. Based on the same, the Employer shall, if it intends to proceed with the Change, issue the Contractor with a Change Order.

    - The Employer shall issue the Contractor with a Change Order pursuant to GCC Sub-Clause 33.2 by way of amendment to the Contract or in any other manner deemed appropriate. Even if the Employer and the Contractor cannot reach agreement on the price for the Change, an equitable adjustment to the Time for Completion, or any other matters related to the Change Proposal, the Employer may nevertheless instruct the Contractor to proceed with the Change by issue of a “Pending Agreement Change Order” (“Pending Agreement Amendment”).

Upon receipt of a Pending Agreement Change Order, the Contractor shall immediately proceed with effecting the Changes covered by such Order. The parties shall thereafter attempt to reach agreement on the outstanding issues under the Change Proposal.

If the parties cannot reach agreement within sixty (60) days from the date of issue of the Pending Agreement Change Order, then the matter may be referred to the Arbitrator in accordance with the provisions of GCC Clause 38 & 39.

  - Changes Originating from Contractor: Not Applicable

# Extension of Time for Completion

    - The Time(s) for Completion specified in the SCC shall be extended if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following:

      - any Change in the Facilities as provided in GCC Clause 33

      - any occurrence of Force Majeure as provided in GCC Clause 32

      - any suspension order given by the Employer under GCC Clause 35 hereof or reduction in the rate of progress pursuant to GCC Sub-Clause 35.2 or

      - any changes in laws and regulations as provided in GCC Clause 31 or

      - any other matter specifically mentioned in the Contract

by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor.

    - Except where otherwise specifically provided in the Contract, the Contractor shall submit to the Project Manager a notice of a claim for an extension of the Time for Completion, together with particulars of the event or circumstance justifying such extension as soon as reasonably practicable after the commencement of such event or circumstance. As soon as reasonably practicable after receipt of such notice and supporting particulars of the claim, the Employer and the Contractor shall agree  upon the period  of such extension.  In  the event that the Contractor does not accept the Employer’s estimate of a fair and reasonable time extension, the Contractor shall be entitled to refer the matter to Arbitration, pursuant to GCC Sub-Clause 39.

    - The Contractor shall at all times use its reasonable efforts to minimize any delay in the performance of its obligations under the Contract.

# Suspension

    - The Employer may request the Project Manager, by notice to the Contractor, to order the Contractor to suspend performance of any or all of its obligations under the Contract. Such notice shall specify the obligation of which performance is to be suspended, the effective date of the suspension and the reasons therefor. The Contractor shall thereupon suspend performance of such obligation (except those obligations necessary for the care or preservation of the Facilities) until ordered in writing to resume such performance by the Project Manager.

If, by virtue of a suspension order given by the Project Manager, other than by reason of the Contractor’s default or breach of the Contract, the Contractor’s performance of any of its obligations is suspended for an aggregate period of more than ninety (90) days, then  at  any  time  thereafter  and  provided  that  at  that  time  such

performance is still suspended, the Contractor may give a notice to the Project Manager requiring that the Employer shall, within twenty-eight (28) days of receipt of the notice, order the resumption of such performance or request and subsequently order a change in accordance with GCC Clause 33, excluding the performance of the suspended obligations from the Contract.

If the Employer fails to do so within such period, the Contractor may, by a further notice to the Project Manager, elect to treat the suspension, where it affects a part only of the Facilities, as a deletion of such part in accordance with GCC Clause 33 or, where it affects the whole of the Facilities, as termination of the Contract under GCC Sub-Clause 36.1.

    - If the Contractor’s performance of its obligations is suspended or the rate of progress is reduced pursuant to this GCC Clause 35, then the Time for Completion shall be extended in accordance with GCC Sub- Clause 34.1, and any and all additional costs or expenses incurred by the Contractor as a result of such suspension or reduction shall be paid by the Employer to the Contractor in addition to the Contract Price, except in the case of suspension order or reduction in the rate of progress by reason of the Contractor’s default or breach of the Contract.

    - During the period of suspension, the Contractor shall not remove from the Site any Plant and Equipment, any part of the Facilities or any Contractor’s Equipment, without the prior written consent of the Employer.

# Termination

    - Termination for Employer’s Convenience

    - The Employer may at any time terminate the Contract for any reason by giving the Contractor a notice of termination that refers to this GCC Sub-Clause 36.1.

    - In the event of termination of the Contract under GCC Sub-Clause 36.1.1, the Employer shall pay to the Contractor the following amounts:

      - the Contract Price, properly attributable to the parts of the Facilities executed by the Contractor as of the date of termination

      - the costs reasonably incurred by the Contractor in the removal of the Contractor’s Equipment from the Site and in the repatriation of the Contractor’s and its Subcontractors‟ personnel

      - any amounts to be paid by the Contractor to its Subcontractors in connection with the termination of any subcontracts, including any cancellation charges

      - costs incurred by the Contractor in protecting the Facilities and leaving the Site in a clean and safe condition pursuant to paragraph (a) of GCC Sub-Clause 36.1.2

      - the cost of satisfying all other obligations, commitments and claims that the Contractor may in good faith have undertaken with third parties in connection with the Contract and that are not covered by paragraphs (a) through (d) above.

  - Termination for Contractor’s Default

    - The Employer, without prejudice to any other rights or remedies it may possess, may terminate the Contract forthwith in the following circumstances by giving a notice of termination and its reasons therefor to the Contractor, referring to this GCC Sub-Clause 36.2:

      - if the Contractor becomes bankrupt or insolvent, has a receiving order issued against it, compounds with its creditors, or, if the Contractor is a corporation, a resolution is passed or order is made for its winding up (other than a voluntary liquidation for the purposes of amalgamation or reconstruction), a receiver is appointed over any part of its undertaking or assets, or if the Contractor takes or suffers any other analogous action in consequence of debt

      - if the Contractor assigns or transfers the Contract or any right or interest therein in violation of the provision of GCC Clause 37.

      - if the Contractor, in the judgment of the Employer has engaged in corrupt or fraudulent practices in competing for or in executing the Contract.

For the purpose of this Sub-Clause:

“Corrupt Practice” means offering, giving, receiving, or soliciting anything of value to influence the action of Employer official(s) in the procurement process.

“Fraudulent Practice’” means any act including suppression/ misrepresentation of facts, submissions of forged/ false documents, making false declarations etc. that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial gain or benefit, or to avoid an obligation, or to influence procurement process to the detriment of interest of the Employer, including collusive practices among bidders (prior to or after bid submission) to establish bid prices at artificial, non-competitive levels and to deprive Employer of the benefits of competitive prices.

“collusive practice” shall also include an arrangement between two or more parties designed to achieve an illegitimate purpose to the detriment of interest of Employer.

“coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party;

“obstructive practice” is

(aa) deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a Employer’s investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation;

or

(bb) acts intended to materially impede the exercise of the  contractual rights or audit or access to information.

In persuasions of its policy, the Employer will sanction a firm or individual, including declaring ineligible, either indefinitely or for a stated period of time, to be awarded a contract if it at any time determines that the firm has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive or obstructive practices in competing for, or in executing, a contract.

    - If the Contractor

      - has abandoned or repudiated the Contract

      - has without valid reason failed to commence work

      - persistently fails to execute the Contract in accordance with the Contract or persistently neglects to carry out its obligations under the Contract without just cause

then the Employer may, without prejudice to any other rights it may possess under the Contract, give a notice to the Contractor stating the nature of the default and requiring the Contractor to remedy the same. If the Contractor fails to remedy or to take steps to remedy the same within fourteen (14) days of its receipt of such notice, then the Employer may terminate the Contract forthwith by giving a notice of termination to the Contractor that refers to this GCC Sub-Clause 36.2.

# Assignment: Not Applicable

# I.	Resolution of Disputes

# Settlement of Disputes

    - If any dispute of any kind whatsoever shall arise between the Employer and the Contractor in connection with or arising out of the Contract, including without prejudice to the generality of the foregoing, any question regarding its existence, validity or termination, or the execution of the Facilities, whether during the progress of the Facilities or after their completion and whether before or after the termination, abandonment or breach of the Contract, the parties shall seek to resolve any such dispute or difference, to the extent possible, amicably by mutual consultation.

    - If the parties fail to resolve such a dispute or difference by mutual consultation at  the execution  site level,  then the dispute shall be referred by the Contractor to the Project Manager, who, within a period of thirty (30) days after being requested by Contractor to do so, shall give written notice of his decision.

    - The decision/instruction of the Project Manager shall be deemed to have been accepted by the Contractor unless notified by the Contractor of his intention to refer the matter for Arbitration within thirty (30) days of such decision/instruction.

    - In the event the Project Manager fails to notify his decision as aforesaid within thirty (30) days, the Contractor, if he intends to go for Arbitration, shall notify his intention to the Project Manager within 30 days of expiry of the first mentioned period of thirty days failing which it shall be deemed that there are no dispute or difference between the Employer and the Contractor.

38.3	In case of dispute or difference between the Employer and the Contractor, if the Employer intends to go for Arbitration, he shall notify such intention to the Contractor.

# Arbitration

    - All disputes or differences in respect of which the decision, if any, of the Project Manager and/or the Head of the Implementing Authority has not become final or binding as aforesaid shall be settled by arbitration in the manner provided herein below:

39.2	The arbitration shall be conducted by a sole arbitrator in case the amount of claim is less than Rs. 25 Crore and by three member arbitral tribunal in case the amount of claim is greater than Rs. 25 Crore.

Sole Arbitration

The sole Arbitrator shall be chosen from a panel of empanelled Arbitrators maintained by POWERGRID. The same shall comprise of retired Judges and retired Senior executives of PSUs other than POWERGRID. Further, the  choice of sole Arbitrator shall be governed by the amount of claim in the following manner:

| Sl | Claim amount | Work Experience/Qualifications |
| --- | --- | --- |
| 1 | < Rs. 10 Crore | Sole arbitrator-Retired Senior Executives of PSUs other than POWERGRID/Retired Distt Judges/ High Court Judges. |
| 2 | Rs.10 Crore- Rs.25 Crore | Sole arbitrator- Retired High Court/Supreme Court Judges |

(a) In case of invocation of arbitration by POWERGRID, POWERGRID shall, within 30 days, send a list of names of 3 arbitrators from its list/database of Arbitrators and the contractor shall within the period of further 30 days select any one person to act as “Sole Arbitrator”, which will be confirmed by POWERGRID and matter will be referred to such appointed Arbitrator for further arbitration proceedings.

(b)  In case of invocation of arbitration by the Contractor, the Contractor shall request POWERGRID for its database of Arbitrators/ chose from the list of Arbitrators available on POWERGRID’s website, and the contractor shall, within 30 days, select any one Arbitrator from the above to act as “Sole Arbitrator”, which will be confirmed by POWERGRID within 30 days and matter will be referred to such appointed Arbitrator for further arbitration proceedings.

If the parties fail to appoint sole arbitrator within sixty (60) days after receipt of a notice from the other party invoking Arbitration, the appointment of sole arbitrator shall be done by Courts as per the provisions of Indian Arbitration and Conciliation Act, 1996 or any statutory modification thereof.

Three member arbitral tribunal

The arbitration shall be conducted by three arbitrators, who are retired High Court/Supreme Court Judges, one each to be nominated by the Contractor and the Employer and the third to be appointed by both the arbitrators in accordance with the Indian Arbitration & conciliation Act.  If either of the parties fails to appoint its arbitrator within sixty (60) days after receipt of a notice from the other party invoking the Arbitration clause, the arbitrator appointed by the party invoking the arbitration clause shall become the sole arbitrator to conduct the arbitration. In case of failure of the two arbitrators appointed by the parties to reach upon a consensus regarding appointment of presiding Arbitrator, within a period of 30 days from the appointment of the arbitrator appointed subsequently, the presiding arbitrator shall be appointed by Courts as per the provisions of Arbitration & conciliation Act.

39.3	The cost of arbitral proceedings inter-alia including the Arbitrators’ fee, logistics and any other charges shall be equally shared by both parties.

In case of Sole Arbitrator, the fees to be paid to the sole Arbitrator shall be as per the terms of empanelment in POWERGRID whereas in case of the three member tribunal, the Arbitrator’s fees shall be as agreed upon by the Arbitrators in line with the Arbitration & Conciliation Act.  However, the expenses incurred by each party in connection with the preparation, presentation, etc. of its proceedings shall be borne by each party itself.

    - The language of the arbitration proceedings and that of the documents and communications between the parties shall  be English. The arbitration shall be conducted in accordance with the provisions of the Indian Arbitration and Conciliation Act, 1996 or any statutory modification thereof. The venue of arbitration shall be New Delhi.

    - The decision of the sole arbitrator/ the majority of the arbitrators, as the case may be, shall be final and binding upon the parties. In the event of any of the sole arbitrator/ any of the aforesaid arbitrators dying, neglecting, resigning or being unable to act for any reason, it will be lawful for the parties to nominate another sole arbitrator/ another arbitrator in place of the outgoing arbitrator.

    - Notwithstanding the above, in case the contractor is a Central Public Sector Enterprise (CPSE)/ Government Organization or Department then the dispute or difference between the Employer and the Contractor shall be settled through Administrative Mechanism for Resolution of CPSEs Dispute (AMRCD) as mentioned in DPE OM No. 4(1)/ 2013 – DPE(GM)/FTS-1835 dated 22.05.2018. The decision through AMRCD will be final and binding on all the concerned.

    - During settlement of disputes and arbitration proceedings, both parties shall be obliged to carry out their respective.

----- End of Section-IV (GCC) ----