| Sl. No. | Clause Ref. No. | Existing provision | Amended as |
| --- | --- | --- | --- |
|  | ITB 24.1 (c), Section-III, BDS, Vol.-1 | The Time for Completion shall be as under : Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of. Procurement of 06 Nos. 397MVA Converter Transformers for Talcher and Kolar HVDC stations under Add-Cap 2024-29. Spec. No.: CC/NT/W-TR/DOM/A00/24/06359; 24 months (Twenty-Four Months). | The Time for Completion shall be as under : Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of. Procurement of 06 Nos. 397MVA Converter Transformers for Talcher and Kolar HVDC stations under Add-Cap 2024-29. Spec. No.: CC/NT/W-TR/DOM/A00/24/06359; 30 months (Thirty Months). |
|  | Clause 2.0 (b) & (c), Annexure-A(BDS), Section-III, Vol.-1 | Minimum Average Annual Turnover* (MAAT) for best three (3) years i.e. 36 months out of last five (5) financial years of the bidder should be INR 3695.93 million Bidder shall have liquid assets (L.A.) or/and evidence of access to or availability of credit facilities of not less than INR 615.99 million | Minimum Average Annual Turnover* (MAAT) for best three (3) years i.e. 36 months out of last five (5) financial years of the bidder should be INR 2956.74 million Bidder shall have liquid assets (L.A.) or/and evidence of access to or availability of credit facilities of not less than INR 492.79 million |
|  | GCC 1.1(e) & 1.1(ee), SCC, Section-V, Vol.-1 | Supplementing Sub-Clause GCC 1.1(e) & 1.1 (ee) The Time for Completion shall be as under: Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of. Procurement of 06 Nos. 397MVA Converter Transformers for Talcher and Kolar HVDC stations under Add-Cap 2024-29. Spec. No.: CC/NT/W-TR/DOM/A00/24/06359; 24 months (Twenty-Four Months). | Supplementing Sub-Clause GCC 1.1(e) & 1.1 (ee) The Time for Completion shall be as under: Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of. Procurement of 06 Nos. 397MVA Converter Transformers for Talcher and Kolar HVDC stations under Add-Cap 2024-29. Spec. No.: CC/NT/W-TR/DOM/A00/24/06359; 30 months (Thirty Months). |
|  | GCC 21.1, SCC, Section-V, Vol.-1 | Supplementing the Clause GCC 21.1 with the following: The Time for Completion shall be as under: Sl. No.; Activities; Duration in months from the effective date of NOA. 1.; Procurement of 06 Nos. 397MVA Converter Transformers for Talcher and Kolar HVDC stations under Add-Cap 2024-29. Spec. No.: CC/NT/W-TR/DOM/A00/24/06359; 24 months (Twenty-Four Months). | Supplementing the Clause GCC 21.1 with the following: The Time for Completion shall be as under: Sl. No.; Activities; Duration in Months from the date of Notification of Award. 1.; Procurement of 06 Nos. 397MVA Converter Transformers for Talcher and Kolar HVDC stations under Add-Cap 2024-29. Spec. No.: CC/NT/W-TR/DOM/A00/24/06359; 30 months (Thirty Months). |
|  | First para, Appendix-4 (TIME SCHEDULE), Section-VI, Vol.-1 | 1. The Project Completion Schedule shall be as follows: Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of:. Procurement of 06 Nos. 397MVA Converter Transformers for Talcher and Kolar HVDC stations under Add-Cap 2024-29. Spec. No.: CC/NT/W-TR/DOM/A00/24/06359; 24 months (Twenty-Four Months). | 1. The Project Completion Schedule shall be as follows: Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of:. Procurement of 06 Nos. 397MVA Converter Transformers for Talcher and Kolar HVDC stations under Add-Cap 2024-29. Spec. No.: CC/NT/W-TR/DOM/A00/24/06359; 30 months (Thirty Months). |
|  | Annexure-A(BDS), Vol.-1 | In view of the above (Sl. No. 2), revised Annexure-A(BDS) attached herewith. |  |
|  | First Envelope Bid Form & Attachment, Volume-3 | In view of the above, existing MS excel file (namely ‘First Envelope and Bid Forms’) containing 1st Envelope Bid form & Attachments is stand replaced with revised excel file (namely ‘First Envelope and Bid Forms_rev1’), which is attached herewith. Bidder is requested to consider revised excel file only. |  |

***