| Sl. No. | Tender Document Reference | Clause | Bidder’s Query | POWERGRID Reply |
| --- | --- | --- | --- | --- |
| 1 | Volume -I ITB 24.1(C) of BDS and GCC 1.1(e), 1.1(ee) and 21.1 of SCC | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract; Remark (Indicative Period in Months from Award). 1.; Taking Over by the Employer upon successful Completion of 400kV Transformer Package 4TR-11-BULK for procurement of 5 x 500 MVA, 400/220/33kV, 3-Ph Transformers under Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6).; 18 Months; Engineering: 0-7 months Dispatch: 13-15 months Receipt at site:14-16 months Erection & Ready for Commissioning:15-18 months (1st-5th) 5 units by 18 months. | Request to amend the clause below of subject tender for wider participation: Taking Over by the Employer upon successful Completion of 400kV Transformer Package 4TR-11-BULK for procurement of 5 x 500 MVA, 400/220/33kV, 3-Ph Transformers under Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities (Lot-6). – 30 Months Engineering: 0-7 months Dispatch: 25-27 months Receipt at site: 26-28 months Erection & Ready for Commissioning: 27-30 months (1st-5th) 5 units by 30 months | Provisions of Bidding Documents shall remain unchanged. |