## L1 BY PGCIL
L1 SCHEDULE
Sl No | Description of Activity | Period from date of LOA (in days)
|  | Commencment | Completion
1 | Date of Notification of award(NOA) shall be treated as zero date/Commencement date
2 | Contract Agreement, signing and submission of CPG
a | Site Handing over | 0 | 5
b | Site office establishment | 5 | 15
c | Labour licence, stuatory compliances lnsurance. | 5 | 30
d | Source approval of materials including all testing as per SFQP requirement to start the works | 5 | 40
3 | Repairing of Road ramp at entrance of Main Gate at 400kV Bareilly Substation | 30 | 90
a | Surface dressing | 30 | 40
b | PCC works | 40 | 50
c | Centering Shuttering | 50 | 55
d | Steel Reinforcement and Concreting works | 50 | 85
f | Miscellaneous/Balance works | 85 | 90
The Contractor/bidder shall submit L-2 schedule showing the above activities /milestone keeping the overall comnpletion period unchanged.Minor changes in the individual activity schedule are permissible which the contractor /bidder may suggest considering the volume of work as per their wisdom

## L1 BY Vendor
L1 SCHEDULE
Sl No | Description of Activity | Period from date of LOA (in days)
|  | Commencment | Completion
1 | Date of Notification of award(NOA) shall be treated as zero date/Commencement date
2 | Contract Agreement, signing and submission of CPG
a | Site Handing over
b | Site office establishment
c | Labour licence, stuatory compliances lnsurance.
d | Source approval of materials including all testing as per SFQP requirement to start the works
3 | Repairing of Road ramp at entrance of Main Gate at 400kV Bareilly Substation
a | Surface dressing
b | PCC works
c | Centering Shuttering
d | Steel Reinforcement and Concreting works
f | Miscellaneous/Balance works
The Contractor/bidder shall submit L-2 schedule showing the above activities /milestone keeping the overall comnpletion period unchanged.Minor changes in the individual activity schedule are permissible which the contractor /bidder may suggest considering the volume of work as per their wisdom