| Sl. No. | Volume/ Section/ Clause | Description as per Bid Document | Bidder’s Query / Clarification | POWERGRID’s Reply |
| --- | --- | --- | --- | --- |
|  | General | Zero date of project | We understand that Zero date of Project will start from the date of handing over of encumbrance free land to Contractor. Please confirm. | In this regard, the provisions of Bidding Documents are amply clear. Bidder may refer Clause 1.1(n) & Cluse 6 of GCC, Section – IV, Volume-I of the Bidding Documents. |
|  | ITB 9.1 (q)- VII, BDS, Section-III, Vol-I | Bidder shall submit a monthly cash flow projection for execution of the contract having regard to implementation schedule. Bidder should indicate how funding gap in each month is proposed to be met. | We request you to accept the submission of Cash flow projection after award of contract as for funding requirement we are already submitting bank certificate mentioning fund based & non fund based available limit. Please confirm. In case, it is mandatory to submit cashflow. We request you to provide the format for the same. | Provisions of Bidding Documents are amply clear. Bidder may give required information on it its own format. |
|  | ITB 9.1 (q)- VIII -a, BDS, Section-III, Vol-I | To be qualified for award, bidders shall provide evidence satisfactory to the employer of their capability and adequacy of resources to carry out the contract effectively. Bids shall include the following information (a) The qualification and experience of key personnel proposed for carrying out the work. | We understand that "key personnel proposed for carrying out the work" is referring to Proposed Project manager, whose qualification & experience details are to be furnished. Please confirm. | Provisions of Bidding Documents are amply clear. |
|  | Clause 22.8.1-Section V, SCC-Defect Liability | Supplementing Sub-Clause GCC 22.8.1 The Contractor's liability for latent defects warranty for 132kV/ 145kV/220KV/245kV/400kV/765kV Capacitive Voltage Transformer/ Current Transformer/Circuit Breaker shall be limited to period of five (05) years from the end of Defect Liability Period. | We understand that GCC clause 22.8.1 is replaced by SCC sl. no. 43. Accordingly, Latent DLP is applicable only for (132kV/220KV/400kV/765kV class) Current Transformer/ Capacitive Voltage Transformer / Circuit Breaker/ Reactor shall be limited to period of five (05) years from the end of Defect Liability Period. Please confirm. | The provisions of Bidding Documents are amply clear. |
|  | Clause 34.1 -Section IV, GCC, Vol-I-Extension of Time | The Time(s) for Completion specified in the SCC shall be extended if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: (a) ……………… (b) ……………… (c) ……………… (d) ……………… (e) any other matter specifically mentioned in the Contract by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor. | We request to add following clause under GCC 34, Extension of time for completion - In case of of any default by employer to execute any of its responsibilities under GCC 6, the Time for Completion shall be extended along with suitable cost compensation. | The provisions of the bidding documents shall remain unchanged. |
|  | Clause no. 32.1 of GCC - Force Majeure | “Force Majeure” shall mean any event beyond the reasonable control of the Employer or of the Contractor, as the case may be, and which is unavoidable notwithstanding the reasonable care of the party affected, and shall include, without limitation, the following: (a) war, hostilities or warlike operations (whether war be declared or not), invasion, act of foreign enemy and civil war, (b) rebellion, revolution, insurrection, mutiny, usurpation of government, conspiracy, riot and civil commotion, (c) earthquake, landslide, volcanic activity, flood or cyclone, or other inclement weather condition, nuclear and pressure waves or other natural or physical disaster, | Considering Covid-19 pandemic & lockdown history. We request you to include "Pandemic" in the acceptable events of force majeure. | Provisions of Bidding Documents are amply clear and same shall prevail. |
|  | GCC/SCC Clause 2.13.1 (b), Section-V, Vol-I of Bidding Documents | Any notice sent by special courier shall be deemed (in the absence of evidence of earlier receipt) to have been delivered ten (10) days after dispatch. In proving the fact of dispatch, it shall be sufficient to show that the envelope containing such notice was properly addressed, stamped and conveyed to the postal authorities or courier service for transmission by special courier. Provided further that whenever the postal authorities or courier service provide a proof of delivery, the same shall also be applicable for presenting the fact of dispatch | We Request you to delete this clause as the same is detrimental to contractor interest. | The provisions of the Bidding Documents shall remain unchanged. |
|  | GCC/SCC Clause 35, Section-IV & Section-V, Vol-I of Bidding Documents | 35. Suspension 35.1 The Employer may request the Project Manager, by notice to the Contractor, to order the Contractor to suspend performance of any or all of its obligations under the Contract. Such notice shall specify the obligation of which performance is to be suspended, the effective date of the suspension and the reasons therefor. The Contractor shall thereupon suspend performance of such obligation (except those obligations necessary for the care or preservation of the Facilities) until ordered in writing to resume such performance by the Project Manager. If, by virtue of a suspension order given by the Project Manager, other than by reason of the Contractor‟s default or breach of the Contract, the Contractor‟s performance of any of its obligations is suspended for an aggregate period of more than ninety (90) days, then at any time thereafter and provided that at that time such performance is still suspended, the Contractor may give a notice to the Project Manager requiring that the Employer shall, within twenty-eight (28) days of receipt of the notice, order the resumption of such performance or request and subsequently order a change in…………….. 35.1………. 35.2………… 35.3………….. | We request to add following clause as contractor's suspension rights - Suspension Rights - If Owner fails or delays to release the payments and or perform any other obligations under this Agreement, The Contractor may, after giving not less than [21] days’ notice to Owner, suspend work (or reduce the rate of work) unless and until the Contractor has received the Payment or the breach of Owner is remedied. The Contractor’s action shall not prejudice its other rights and entitlements including interest on delayed payments. If the Contractor suffers delay and/or incurs Cost as a result of suspending work (or reducing the rate of work), it shall be entitled to : (a) an extension of time for any such delay, if completion is or will be delayed, and (b) payment of any such Costs incurred as a result thereto. | The provisions of the Bidding Documents shall remain unchanged. |
|  | GCC/SCC Clause 36, Section-IV & Section-V, Vol-I of Bidding Documents | 36. Termination 36.1 Termination for Employer‟s Convenience 36.1.1 The Employer may at any time terminate the Contract for any reason by giving the Contractor a notice of termination that refers to this GCC Sub-Clause 36.1. 36.1.2 Upon receipt of the notice of termination under GCC Sub-Clause 36.1.1, the Contractor shall either immediately or upon the date specified in the notice of termination………….. …………………………………….. 36.1.3 In the event of termination of the Contract under GCC Sub-Clause 36.1.1, the Employer shall pay to the Contractor the following amounts: (a) the Contract Price, properly attributable to the parts of the Facilities executed by the Contractor as of the date of termination (b) the costs reasonably incurred by the Contractor in the removal of the Contractor‟s Equipment from the Site and in the repatriation of the Contractor‟s and its Subcontractors‟ personnel (c) any amounts to be paid by the Contractor to its Subcontractors in connection with the termination of any subcontracts, including any cancellation charges (d) costs incurred by the Contractor in protecting the Facilities and leaving the Site in a clean and safe condition pursuant to paragraph (a) of GCC Sub-Clause 36.1.2 (e) the cost of satisfying all other obligations, commitments and claims that the Contractor may in good faith have undertaken………………. …………………………………………………… | We request to add following clause as contractor's termination rights - Termination Rights: The Contractor shall be entitled to terminate the Contract if: a) The breach of Owner is not remedied and/or continues despite suspension of contract by the Contractor b) Owner assigns, sublets or transfers this Contract in contravention to the terms of this Contract. c) Owner becomes bankrupt, insolvent, goes into liquidation (voluntary or otherwise), has a receiving or administration order made against him, compounds with his creditors, or carries on business under a receiver, trustee or manager for the benefit of his creditors, an order for corporate insolvency resolution process or liquidation is passed by a court/ tribunal, change of Control, or if any act is done or event occurs which (under applicable Laws) has a similar effect to any of these acts or events. Except in events under (c ) where the termination shall be immediate, the Contractor may upon giving 14 days’ notice to Owner, terminate this Contract in any of the other events listed out hereinabove, without prejudice to its other rights under contract or otherwise; The contractor shall be entitled to: i) return of all performance securities furnished by the Contractor under this Contract ii) payments which shall include: (a) the amounts payable for any work carried out for which a price is stated in the Contract; (b) the Cost of Plant and Materials ordered for the Works which have been delivered to the Contractor, or of which the Contractor is liable to accept delivery; (c) any other Cost or liability which in the circumstances was reasonably incurred by the Contractor in the expectation of completing the Contract (d) reasonable loss of profit. | The provisions of the Bidding Documents shall remain unchanged. |
|  |  |  | We request to add following clause - In the event of termination of the Contract under GCC Sub-Clause 36.1.1, the Employer shall pay to the Contractor the following amounts: a) …..... b) ….... c) …..... d) ….... e) ….... f) Loss of profit |  |
|  | GCC/SCC Clause 39, Section-IV & Section-V, Vol-I of Bidding Documents | Arbitration 39.1 All disputes or differences in respect of which the decision, if any, of the Project Manager and/or the Head of the Implementing Authority has not become final or binding as aforesaid shall be settled by arbitration in the manner provided herein below: 39.2 The arbitration shall be conducted by a sole arbitrator in case the amount of claim is less than Rs. 25 Crore and by three member arbitral tribunal in case the amount of claim is greater than Rs. 25 Crore. Sole Arbitration …………………………………….. Three member arbitral tribunal The arbitration shall be conducted by three arbitrators, who are retired High Court/Supreme Court Judges, one each to be nominated by the Contractor and the Employer and the third to be appointed by both the arbitrators in accordance with the Indian Arbitration & conciliation Act. If either of the parties fails to appoint its arbitrator within sixty (60) days after receipt of a notice from the other party invoking the Arbitration clause, the arbitrator appointed by the party invoking the arbitration clause shall become the sole arbitrator to conduct the arbitration. In case of failure of the two arbitrators appointed by the parties to reach upon a consensus regarding appointment of presiding Arbitrator, within a period of 30 days from the appointment of the arbitrator appointed subsequently, the presiding arbitrator shall be appointed by Courts as per the provisions of Arbitration & conciliation Act. 39.3………………………………………… 39.4…………………………………………. 39.5………………………………………… 39.6………………………………………….. | We seek appointment of independent arbitrators (mutual appointment in case of a sole arbitrator) without reference to the panel maintained by the Employer. Pl confirm. We request for settlement of disputes arising out of contract or in connection with the contract, to be settled with panel of three arbitrators, one from each party and a presiding arbitrator. Also the claim about shall not be the basis of deciding the number of arbitrators. Please confirm. | The provisions of the Bidding Documents shall remain unchanged. |
|  | General | Delay in land handover/ ROW- issue not attributable to Contractor | We request to consider delay in Delay in land handover/ ROW issue for the reasons not attributable to Contractor as suspension period and below terms should be followed for this period: a) “If the total period of all such suspension exceeds thirty days, the Contractor shall, in addition be entitled to compensation, as the Engineer-in-Charge may consider reasonable, in respect of salaries and/or wages paid by the Contractor to his employees and labour and hired contractor’s equipments at Site remaining idle during the period of suspension, adding thereto 5% of the sum of the compensation, for suspension exceeding 30 days and not exceeding 90 days to cover indirect expenses of the Contractor, provided the Contractor submits his claim supported by details to the Engineer-In-Charge within 14 days of the expiry of the period of suspension.” b) If, by virtue of a suspension order given by the Employer, other than by reason of the Contractor’s default or breach of the Contract, the Contractor’s performance of any of its obligations is suspended for an aggregate period of more than ninety (90) days, then at any time thereafter and provided that at that time such performance is still suspended, the Contractor may give a notice to the Employer requiring that the Employer shall, within twenty-eight (28) days of receipt of the notice, order the resumption of such performance or order a change excluding the performance of the suspended obligations from the Contract. If the Employer fails to do so within such period, the Contractor may, by a further notice to the Employer, elect to treat the suspension, where it affects a part only of the Facilities, as a deletion of such part or, where it affects the whole of the Facilities, as termination of the Contract. | In this regard, provisions of the Bidding Documents are amply clear and same shall prevail. |