[bookmark: _Hlk139037506]Amendment No I dated 30/08/2024 to the Invitation for Bids (IFB) for 765kV GIS Pkg-SS58T for i) Establishment of 2x1500 MVA 765/400 kV Gopalpur (GIS) PS with 2x330 MVAR 765 kV bus reactor ii) Extn of 765kV Angul (AIS) & Bus extn (GIS) under ‘Eastern Region Expansion Scheme- XXXIX (ERES-XXXIX)’ through TBCB route; Spec. No.: CC/T/W-GIS/DOM/A06/24/07507.

	Sl. No.
	Clause Ref. 
	Existing Provision 
	Amended as

	1.
	Clause No. 3.2, IFB
	The completion period for the subject Package shall be 24 (Twenty-Four) Months.

	The completion period for the subject Package shall be 35 (Thirty-Five) Months as specified in ITB Sub-Clause 24.1(c).
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