## Sheet
Clarification No.-IV to the Bidding Documents for Substation Extension Package-SS69 for (i) 400/220 kV Muzaffarpur S/S extn including ICT, (ii) 400 kV Saharsa S/S extn, (iii) 400 kV Durgapur S/S extn and (iv) 400kV Kahalgaon S/S (NTPC) extn associated with Eastern Region Strengthening Scheme-XXIII. [Spec. No.: CC-CS/1010-ER1/SS-4083/3/G2]
Sr. No. | Reference | Clause | Bidder’s Query | POWERGRID REPLY
1 | Foundation work for repeater shelter system | Section- Telecommunication Cl. 1.1.25-foundation system & price Schedule- 3 Erection-Sl no. 150.151.153 & 161 | We understand that quantity required for repeater shelter foundation such as Excavation , PCC, RCC M25, Reinforcement steel, etc. will be paid as per respective unit rate items mentioned in sl. No. 150 to sl. No.153 of schedule -3 , we request you to please confirm the same. | Scope of Repeater shelter in technical specification of Telecommunication System includes shelter , associated items and required civil works. Bidder to quote accordingly.
2 |  |  | We also bring to your kind attention that most of the transformer suppliers are booked till March2021. Because of this, we are unable to get their delivery schedule to meet your tender requirements i.e.10.5 Month as well as best prices. Also, we bring to your kind attention that in Saharsa Substation there is huge earth filling works i.e. (Cum 1.64 Lakhs). We will also encounter a heavy monsoon during the project duration schedule, which will affect to complete the work within given completion schedule i.e. 10.5 Months. In view of above, we request you to kindly review your project schedule and revised it to at least 15 (fifteen) Months. | Provisions of bidding documents shall remain unchanged.